PROCEDURE

PROCEDURE

M

Market Manual 7: System Operations

Part 7.3: Outage Management

Issue 47.0

This market manual is provided for stakeholder engagement purposes.  Proposed changes, to be effective for the 2023 capacity auction, are indicated based on the current version of the market manual.  Please note that additional changes to this document may be incorporated as part of future engagement on design enhancements to the capacity auction or other IESO activities prior to this market manual taking effect.

PUBLIC

PUBLIC

IMP_PRO_0035

IMP_PRO_0035

Public

Public

This document outlines the process market participants must follow in submitting outage requests for facilities

This document outlines the process market participants must follow in submitting outage requests for facilities

d
Disclaimer

The posting of documents on this website is done for the convenience of market participants and other interested visitors to the IESO website. Please be advised that, while the IESO attempts to have all posted documents conform to the original, changes can result from the original, including changes resulting from the programs used to format the documents for posting on the website as well as from the programs used by the viewer to download and read the documents. The IESO makes no representation or warranty, express or implied, that the documents on this website are exact reproductions of the original documents listed. In addition, the documents and information posted on this website are subject to change. The IESO may revise, withdraw or make final these materials at any time at its sole discretion without further notice. It is solely your responsibility to ensure that you are using up-to-date documents and information.

This document may contain a summary of a particular market rule. Where provided, the summary has been used because of the length of the market rule itself. The reader should be aware, however, that where a market rule is applicable, the obligation that needs to be met is as stated in the market rules. To the extent of any discrepancy or inconsistency between the provisions of a particular market rule and the summary, the provision of the market rule shall govern.

Document ID	IMP_PRO_0035

Document Name	Part 7.3: Outage Management

Issue	Issue 47.0

Reason for Issue	Issue released in advance of Baseline 48.1

Effective Date	September 19, 2022

Document ID	IMP_PRO_0035

Document Name	Part 7.3: Outage Management

Issue	Issue 47.0

Reason for Issue	Issue released in advance of Baseline 48.1

Effective Date	September 19, 2022

Document Change History

| Issue | Reason for Issue | Date |
| --- | --- | --- |
| For changes prior to 2010, refer to versions 23.0 and prior. |  |  |
| For changes from 2011 through 2014, refer to versions 32.0 and prior. |  |  |
| 28.0 | Issue released in advance of Baseline 33.1 to update IESO logo | March 31, 2015 |
| 29.0 | Issue released for Baseline 34.1 | December 2, 2015 |
| 30.0 | Issue released in advance of Baseline 36.0 | June 21, 2016 |
| 31.0 | Issue released in advance of Baseline 36.1 | October 26, 2016 |
| 32.0 | Issue released for Baseline 37.1 | June 7, 2017 |
| 33.0 | Issue released for Baseline 39.0 | March 7, 2018 |
| 34.0 | Issue released for Baseline 39.1 | June 6, 2018 |
| 35.0 | Issue released for Baseline 40.0 | September 12, 2018 |
| 36.0 | Issue released in advance of Baseline 40.1 | November 14, 2018 |
| 37.0 | Issue released for Baseline 41.0 | March 6, 2019 |
| 38.0 | Issue released for Baseline 41.1 | June 5, 2019 |
| 39.0 | Issue released in advance of Baseline 42.1 | October 15, 2019 |
| 40.0 | Issue released in advance of Baseline 43.1. These changes are effective for obligations arising from the demand response auction held in December 2019, for the commitment period beginning May 1, 2020. | April 23, 2020 |
| 41.0 | Issue released in advance of Baseline 43.1. These changes are effective for obligations arising from the capacity auction and applicable to capacity obligations for any commitment period beginning on or after May 1, 2021. | May 4, 2020 |
| 42.0 | Issue released in advance of Baseline 44.0 | June 29, 2020 |
| 43.0 | Updated to meet accessibility requirements pursuant to the Accessibility for Ontarians with Disabilities Act. | December 2, 2020 |
| 44.0 | Issue released in advance of Baseline 45.0. Updated to include electricity storage participation. | February 26, 2021 |
| 45.0 | Issue released for Baseline 46.0. | September 15, 2021 |
| 46.0 | Issue released for Baseline 48.0 | September 14, 2022 |
| 47.0 | Issue released in advance of Baseline 48.1 | September 19, 2022 |

Related Documents

| Document ID | Document Title |
| --- | --- |
| N/A |  |

Table of Contents

Table of Contents	i

List of Figures	iv

List of Tables	iv

Table of Changes	vi

Market Manuals	1

Market Procedures	1

1.	Introduction	2

1.1	Purpose	2

1.2	Scope	2

1.3	Roles and Responsibilities	2

1.4	IESO Planned IT Outages	3

1.5	Confidentiality	3

1.6	Contact Information	4

2.	Outage Management Overview	5

2.1	Criticality Levels of Equipment	6

2.2	Priority Codes	7

2.2.1	Determining Outage Priority	8

2.3	Purpose Codes	11

2.4	Constraint Codes	13

2.5	Low-impact Attributes	14

2.6	Mapping Purpose, Constraint and Priority Codes	14

2.7	Timelines	16

2.7.1	General Requirements	16

2.7.2	Quarterly Advance Approval Process	17

2.7.3	Weekly Advance Approval Process	20

2.7.4	Three-Day Advance Approval Process	21

2.7.5	One-Day Advance Approval Process	22

2.7.6	Auto Advance Approvals	23

2.7.7	Final Approval in Advance	24

2.7.8	Submission Deadlines	25

3.	Procedural Workflow	26

3.1	Facility Registration	26

3.2	Outage Coordination	26

3.2.1	Undesirable Situations	27

3.2.2	Outage Planning Guidelines	27

3.2.3	Conflicting Constraint Codes	28

3.2.4	Conflict Checking	30

3.2.5	IESO Reports	31

3.3	Outage Coordination for Capacity Exports	32

3.3.1	Capacity Seller Requirement to Coordinate with Transmitters Prior to IESO Involvement	32

3.3.2	Capacity Seller Requirement to Coordinate with Transmitters Requiring IESO Involvement	33

3.4	Outage Coordination for Generator-Backed Capacity Import Resources	34

3.5	Outage Submission	35

3.6	Outage Assessment	37

3.6.1	Market Participant Updates	37

3.6.2	Outage Assessment Outcomes	38

3.7	Outage Implementation	41

3.7.1	Planned and Forced Extensions	41

3.7.2	Recall	41

3.7.3	Suspension of Non-Urgent Maintenance or Switching	42

3.8	Outage Completion	42

3.9	Outage Compensation	42

4.	Outage Reporting Requirements	45

4.1	Generation and Electricity Storage Facilities	45

4.1.1	Deratings	45

4.1.2	Tests	46

4.1.3	Commissioning Facilities	49

4.1.4	Segregated Mode of Operation	51

4.1.5	[Intentionally Left Blank]	52

4.2	Loads	52

4.2.1	Dispatchable Loads	52

4.2.2	Connected Wholesale Customers	52

4.2.3	Distributors and Transmitters	53

4.2.4	Non-Performance Event Management for Hourly Demand Response Resources	53

4.3	All Market Participants	54

4.3.1	Monitoring and Control Equipment	54

4.3.2	System Tests	54

4.3.3	Testing of Ancillary Services	55

4.3.4	Testing Operating Reserve Providers	56

4.3.5	Hold-offs	58

4.3.6	New and Replacement Facilities	58

5.	Replacement Energy to Support Planned Outages	59

6.	Disputes and Compliance	64

6.1	Disputes	64

6.2	Market Surveillance and Compliance	64

Appendix A: Forms	65

Appendix B: Outage Reporting Requirements	66

Appendix C: Equipment Classes and Applicable Constraint Codes	69

Appendix D: Criteria for 1-Day Advance Approval, Auto AA and FAA	71

References	77

List of Figures

Figure 2-1: Quarterly Advance Approval Timeline	18

Figure 2-2: Criteria for ‘At Risk’ Outage Retaining Original Priority	18

Figure 2-3: ‘At Risk’ Outage Reassessment – Example A	19

Figure 2-4: ‘At Risk’ Outage Reassessment – Example B	19

Figure 2-5: Weekly Advance Approval Timeline	20

Figure 2-6: Three-Day Advance Approval Timeline	21

Figure 2-7: One-Day Advance Approval Timeline	22

Figure 2-8: Outage Submission and IESO Review Timeline	25

Figure 3-1: Compensation Eligibility – Example A	43

Figure 3-2: Compensation Eligibility – Example B	43

Figure 3-3: Compensation Eligibility – Example C	44

Figure 4-1: Submitting Test Request during Outage	47

Figure 5-1: Purchase of Replacement Energy – Requirements and Confirmation Timeline	61

Figure 5-2: Precedence of Outages Based on Purchase of Replacement Energy	63

List of Tables

Table 1-1: Roles and Responsibilities	3

Table 2-1: Criticality Levels of Equipment	6

Table 2-2: Priority Codes	7

Table 2-3: Purpose Codes	11

Table 2-4: Constraint Codes	13

Table 2-5: Mapping of Purpose, Constraint and Priority Codes	15

Table 2-6: Advance Approval Timelines and Eligibility	17

Table 3-1: Seasonal Timeframe	27

Table 3-2: Sample Outage Planning Guideline	28

Table 3-3: Outage Request Constraint Code Conflicts	29

Table 3-4: Criteria for Conflict Rationale Acceptance	31

Table 3-5: Applicable Codes for Generator-backed Capacity Import Resources	34

Table 3-6: Information Requirement during Outage Submission	35

Table 3-7: Outage Assessment Outcomes and Next Steps	38

Table 4-1: Example Codes When Submitting Planned Derate Requests	46

Table 4-2: Example Codes When Submitting Planned Testing Requests	49

Table 4-3: Example Codes for Commissioning Generation Facilities and Commissioning Electricity Storage Facilities	50

Table 4-4: Example Codes When Requesting Planned Segregated Mode of Operation	52

Table 4-5: Example Codes for Planned Outages to Dispatchable Loads	52

Table 4-6: Applicable Codes for Wholesale Customers	52

Table 4-7: Example Codes for Distributors and Transmitters	53

Table 4-8: Example Codes for Planned Outages to Monitoring and Control Equipment	54

Table 4-9: Example Codes When Submitting Planned System Test Requests	55

Table 4-10: Implementing and Assessing Reserve Tests	57

Table 4-11: Example Codes When Submitting Planned Hold-off Requests	58

Table 4-12: Example Codes When Requesting Planned Outages to New and Replacement Facilities	58

Table B-1: Outage Reporting Requirements	66

Table C-1: Applicable Constraint Code per Equipment Class	69

Table D-1: Criteria for 1-Day Advance Approval, Auto AA and FAA	71

Table of Changes

| Reference (Section and Paragraph) | Description of Change |
| --- | --- |
| Sections 3.4 (new) and throughout | Updated to include outage provisions for generator-backed capacity import resources. |

Market Manuals

The market manuals consolidate the market procedures and associated forms, standards, and policies that define certain elements relating to the operation of the IESO-administered markets. Market procedures provide more detailed descriptions of the requirements for various activities than is specified in the market rules. Where there is a discrepancy between the requirements in a document within a market manual and the market rules, the market rules shall prevail. Standards and policies appended to, or referenced in, these procedures provide a supporting framework.

Market Procedures

The “System Operations Manual” is Series 7 of the market manuals, where this document forms “Part 7.3: Outage Management”.

– End of Section –

# Introduction

## Purpose

This document is provided for market participants as a guide to outage management for facilities and equipment connected to the IESO-controlled grid, or which may affect the operation of the IESO-controlled grid. This includes outages to transmission facilities defined as constituting elements of the IESO-controlled grid under the market rules and various operating agreements between the IESO and market participants.

## Scope

This procedure is intended to provide market participants with a summary of the steps and interfaces involved in the outage management process. The procedural workflows and steps described in this document serve as a roadmap for generation facilities, transmitters, distributors, electricity storage facilities, and wholesale customers that participate in the IESO-administered markets, and reflect the requirements set out in the market rules and applicable IESO policies and standards.

The IESO considers a piece of equipment to be in an outage state when it is removed from service, in a state other than its normal state, unavailable for connection to the system, temporarily derated, restricted in use, or reduced in performance. This includes de-staffing of a generation unit or an electricity storage unit during a period when market participants do not expect the unit to be scheduled to provide energy or operating reserve. Auxiliary equipment is also considered to be in an outage state when it is not available for use.

Outage management, based upon the set of permissions and requirements specified in the market rules, comprises the following aspects:

- Coordination and submission of outage requests by market participants,

- Assessment of outage requests by the IESO,

- Identification of reliability issues associated with outages, leading to actions including rejection, revocation, and at risk declarations of the outage request, and recall of the equipment on outage by the IESO,

- Compliance obligations, and

- Outage compensation in the event of revocation or recall.

In support of these aspects, this procedure details the conditions, actions and timelines required for outage management by market participants. The procedure is based on obligations expressed in the market rules, as well as standards established by the North American Electric Reliability Council (NERC) and criteria established by the Northeast Power Coordinating Council (NPCC).

## Roles and Responsibilities

The following table outlines the responsibilities of the groups involved in the outage management process:

Table 1-1: Roles and Responsibilities

| Group | Responsibility |
| --- | --- |
| Market participants that meet the IESO’s outage reporting requirements | Coordinate and submit outages using IESO reports and recommendations, Submit requests to implement outages to their facilities or equipment within the required timeframe to the IESO, Request final approval prior to start of the outage, Confirm the start of the outage, Confirm the completion of outage, Request permission to return equipment to service, Confirm the restoration of equipment to normal state with the IESO, and Register new equipment information and update information for existing equipment via Online IESO. |
| IESO | Assess outage requests for potential impact to reliability and/or operability of the IESO-controlled grid, Provide advance and final approval for outage requests, Reject an outage request, and revoke or recall previously approved outages for reliability reasons, Coordinate outages and tests if required, and Grant permission for equipment to return to service. |

## IESO Planned IT Outages

Market participants are normally notified about planned Information Technology (IT) outages to market-facing tools and applications through weekly bulletin emails.  Details for all planned IT outages are also posted on the IESO’s Planned IT Outages website.

For unforeseen IT outages, market participants are notified via an Advisory Notice and/or via a message through the Market Participant Interface.

## Confidentiality

Under the market rules, the IESO is required to publish planned outage information while respecting the confidentiality of market participants. As a result, outage requests submitted by market participants may be classified as confidential, and protected appropriately.

In addition, the Adequacy Reports will aggregate outage information to protect the confidentiality of market participants. All planned transmission system outages will be published for information. This may include transmission elements that are not owned by a transmitter.

Outage information will only be exchanged with Reliability Coordinators (RCs) and Balancing Authorities (BAs) who are signatories to the NERC confidentiality agreement or who are otherwise legally bound to withhold and keep confidential outage information from any person competing with a market participant who provided the information.

Market participants may choose to share outage information with other market participants by granting third party viewership of their equipment via Online IESO. A single outage request may contain both, equipment with and without third party viewership access. In such cases, third party viewers will only see the equipment to which they have access.

## Contact Information

Changes to this public market manual are managed via the IESO Change Management process. Stakeholders are encouraged to participate in the evolution of this market manual via this process.

To contact the IESO, you can email IESO Customer Relations at customer.relations@ieso.ca or use telephone or mail. Customer Relations staff will respond as soon as possible.

– End of Section –

# Outage Management Overview

Market participants are required to request permission and receive approval for planned outages from the IESO in order to ensure that equipment outages do not impact the reliability and/or operability of the IESO-controlled grid. Generator-backed capacity import resources are required to request permission and receive approval for planned outages from the IESO when that outage impacts the resource’s ability to provide its capacity obligation. Market participants with equipment that affects the operation of the IESO-controlled grid may not remove equipment or facilities from service except in accordance with the rules for Outage Coordination contained in Market Rule Chapter 5, Section 6.4.3 (MR Ch. 5, Sec. 6.4.3) and this market manual.

The IESO’s outage management system uses the the Control Room Operations Window (CROW) outage coordination and scheduling system. Market participants are required to submit information that provides the IESO with a better understanding of the priority, scope and impact of the outage request as described in Sections 2.1 to 2.5.

Market participants must submit their planned outages into one of four advance approval processes in order to receive advance approval. Each process has a unique set of eligibility criteria and submission/approval deadlines further described in Section 2.7.

Forced, urgent, information and opportunity outages are outages that market participants are unable to submit in accordance with the submission requirements for planned outages, however these types of outages must still be submitted to the IESO as either a notification or a late request for advance approval as described in Section 2.2.

## Criticality Levels of Equipment

The level of equipment criticality dictates the advance approval timeframe within which a planned outage request must be submitted (see Table 2-1). For example, planned outages to critical equipment must be submitted at least 17 days prior to the start of the coverage period (under the Weekly Advance Approval process), whereas planned outages to low-impact equipment must be submitted two days prior to the scheduled date of the outage (under the 1-Day Advance Approval process). Section 2.7 describes advance approval processes and eligible equipment in further detail.

The IESO notifies market participants of equipment criticality levels via Online IESO, upon completion of facility assessment. When submitting outage requests, market participants are required to identify the impacted equipment and the outage management system will auto-populate the criticality level.

Table 2-1: Criticality Levels of Equipment

| Criticality Level | Description | Examples | Advance Approval Submission Timeline |
| --- | --- | --- | --- |
| Critical Equipment | Equipment that has a material impact on the reliability and/or operability of the IESO-controlled grid or the interconnection when removed from service or restricted. | Equipment that impact power system stability limits | Must be submitted for Weekly Advance Approval May be submitted for Quarterly Advance Approval |
| Non-critical Equipment3 | Equipment that does not typically have a material impact on the reliability and/or operability of the IESO-controlled grid or the interconnection when removed from service or restricted. | Equipment in local areas Generation facilities or electricity storage facilities | Must be submitted for 3-Day Advance Approval May be submitted for Quarterly or Weekly Advance Approval |
| Low-impact Equipment | Equipment that has little to no impact on the reliability and/or operability of the IESO-controlled grid or the interconnection when removed from service or restricted. | Loads Duplicated protection relays | Must be submitted for 1-Day Advance Approval May be submitted for Quarterly, Weekly Advance Approval |

## Priority Codes

Priority codes identify the priority of the outage request. Refer to Table 2-2: Priority Codes below. The IESO uses this information to determine the level of urgency to implement the outage and to prioritize competing outage requests. For example, an urgent outage request gets a higher priority compared to an opportunity outage request.

Refer to Section 2.2.1 for more information on how the IESO determines outage priority.

Market participants are required to use one of the following Priority Codes when submitting their outage request.

Note: Priority Codes cannot be changed by market participants once they have been submitted.

Table 2-2: Priority Codes

| Priority Codes | Description | Examples | Obligation to Notify IESO |
| --- | --- | --- | --- |
| Forced | Non-discretionary outages on equipment that has been automatically or manually removed from service for equipment protection, public safety, environmental concerns or regulatory requirements are classified as forced outages. Such outages have little to no timing flexibility and have precedence over all Priority Codes. | Transformer forced out of service due to equipment failure | Market participants are required, as far in advance as possible, to promptly notify the IESO of any forced outage (MR Ch. 5, Sec. 6.3.4). |
| Urgent | Non-discretionary outages on equipment that must be manually removed from service for equipment protection, public safety, environmental concerns or regulatory requirements are classified as urgent outages. | SF6 breaker low gas alarm that requires a breaker outage for gas top-up within a limited timeframe | Market participants are required to coordinate outage timing with the IESO, where possible, to occur at a date and time that satisfies the market participant’s need and minimizes the impact to the IESO-controlled grid. |
| Planned | Discretionary outage requests that are scheduled to perform preventive maintenance, repairs, inspections, de-staffing and testing for facilities/equipment are classified as planned outages. | Generation facility or electricity storage facility scheduled maintenance Breaker trip coil test | Market participants must adhere to submission deadlines explained in Section 2.7 of this manual. (MR Ch. 5, Sec. 6.2.2K and 6.2.2L). |
| Opportunity | In cases where market participants are presented with an unexpected opportunity to accomplish work that was not previously planned, they may submit an outage request with the opportunity Priority Code. | Additional testing is required to expedite the completion of an in-progress forced outage to a generation facility or electricity storage facility. An opportunity to perform maintenance to a facility that is made grid-incapable by another outage. | The IESO is not obligated to consider such submissions, but may do so where the opportunity presents low to negligible risk to the reliability and/or operability of the IESO-controlled grid and or to the IESO. (MR Ch. 5, Sec. 6.4.6). |
| Information | Outages that are exempt from submission requirements outlined in Appendix B, but are submitted for informational purposes only, are classified as information outages. | Generation facility or electricity storage facility unavailable for condense Switch on manual operation only | No obligation. Market participants may, as far in advance as possible, notify the IESO of any information outage, using their outage submission tools. |
| Force Extended | This code is not available to market participants when submitting outage requests. However, if the end time of a planned, opportunity, or information outage requests get extended their Priority Code will be updated to forced extended. | Adverse weather conditions delay the completion of a scheduled outage | Market participants are required to notify the IESO of any forced extension as far in advance as possible, using their outage submission tools and by telephoning the IESO. |

### Determining Outage Priority

The IESO determines priority of outages in order to approve, reject, revoke and recall outages in a consistent and uniform manner.

Outage priority for approval (as per MR Ch. 5, Sec. 6.4.2) is based on the criteria listed below:

- Criteria 1: Priority Code

The Priority Code of an outage request is the primary determinant of outage priority. The order of precedence is as follows:

- Forced

- Urgent

- Planned

- Opportunity

For example, when approving outages, an urgent outage request gets priority over a planned or opportunity outage request.

- Criteria 2: Advance approval timeframe

Within planned outages, the order of precedence is as follows:

- Outages submitted for Quarterly Advance Approval

- Outages submitted for Weekly Advance Approval

- Outages submitted for 3-Day Advance Approval

- Outages submitted for 1-Day Advance Approval

For example, a planned outage request submitted for Weekly Advance Approval gets priority over a planned outage request submitted for 3-Day Advance Approval. However, an urgent outage request submitted five days ahead of the planned start time gets priority over a planned outage request submitted under the Weekly Advance Approval process.

- Criteria 3: Priority date

For urgent and opportunity outages, the submission date and time determine outage priority. The earlier the submission, the higher is the priority of the outage request.

For planned outages submitted within the same advance approval timeframe, the submission date and time determine outage priority.

For example:

| If… | Then… |
| --- | --- |
| The following outages are submitted for approval: Outage A: Opportunity outage submitted three days ahead of the planned start time Outage B: Urgent outage submitted five days ahead of the planned start time Outage C: Planned outage submitted for the Weekly Advance Approval process Outage D: Opportunity outage submitted five days ahead of the planned start time Outage E: Planned outage submitted for the 3-Day Advance Approval process | Outage priority will be as follows: - Outage B - Outage C - Outage E - Outage D - Outage A |

To determine priority when rejecting, revoking advance approval or recalling outages, the IESO shall follow the reverse order of the criteria listed above (MR Ch. 5, Sec. 6.4.13). Where an outage conflict exists and one or more conflicting outages are rejected or revoked, the IESO may facilitate communication between the parties.

For example:

| If… | Then… |
| --- | --- |
| The IESO determines a need to reject the following submitted outage requests: Outage A: Opportunity outage submitted three days ahead of the planned start time Outage B: Urgent outage submitted five days ahead of the planned start time Outage C: Planned outage submitted for the Weekly Advance Approval process Outage D: Opportunity outage submitted five days ahead of the planned start time Outage E: Planned outage submitted for the 3-Day Advance Approval process | Outages will be rejected in the following order: - Outage A - Outage D - Outage E - Outage C - Outage B |

If market participants make a significant change to the scope or time window of a previously submitted outage request, the IESO shall revise the priority date with the time at which such change notice was received by the IESO. Changes to the following outage request fields are considered to be significant changes:

- Planned Start (if changed to an earlier outage period level start date/time)

- Planned End (if changed to a later outage period level4 end date/time)

- Equipment Requested (if equipment is added or removed)

- Equipment Description

- Priority Code

- Constraint Information (if change in Constraint Code, value, and/or measure unit)

- Changes to any responses to low-impact questions (Refer to Section 2.5 for details)

- Change to the response to the Telemetry Scaling Impact question

The revised priority date will then be used to determine the priority for approval. In cases where market participants shorten the duration of a planned outage to remain within the original time window, the priority date associated with the initial submission will still be used to determine priority (MR Ch. 5, Sec. 6.4.15).

In cases where market participants wish to shorten the max recall time, they must verbally request the IESO to retain the original outage priority.

## Purpose Codes

Purpose Codes allow market participants to indicate the reason for the outage request. Refer to Table  below. This information is used by the IESO to determine the impact and purpose of the outage request. For example, an outage request submitted for a safety concern informs the IESO of the market participant’s urgent need compared to an outage request to conduct maintenance/repair testing which can be planned in advance.

Market participants are required to select one of the following Purpose Codes when submitting their outage request and input a description of the outage’s purpose in the outage management system.

Note: Selection of Purpose Codes is based on the Priority Code. For example, ‘Equipment Concern’ code is available only if the market participant is submitting a forced or urgent outage. Similarly, the ‘Repair’ code is available only for planned outages. Refer to Section 2.6 for a mapping of Purpose and Priority Codes.

Table 2-3: Purpose Codes

| Purpose Code | Description | Example |
| --- | --- | --- |
| Maintenance Repair | Outages implemented to facilitate routine equipment maintenance and repair. | Annual transformer maintenance |
| Replacement | Outages implemented to replace aging or faulty equipment/facilities. In such cases, market participants must ensure the replacement is registered with the IESO as per Market Manual 1.5: Market Registration Procedures. The outage to replace the equipment/facility is typically followed by a need to carry out a commissioning outage as explained below. | Breaker replacement |
| Commissioning | Outages implemented to test new or modified equipment/facilities being connected to the IESO-controlled grid for the first time. | Commissioning of new generation facility or electricity storage facility |
| Testing | Outages implemented to facilitate testing of equipment/facilities not considered to be commissioning tests or activities. | Generation facility minimum load point testing |
| Equipment/Safety/ Regulatory/ Environmental Concerns | Outages implemented for non-discretionary purposes such as public safety, equipment protection, environmental concerns or regulatory requirements. | Generation facility derate due to restrictive forebay operating ranges |
| Favourable (Generation/ Electricity Storage/ Transmission) Outage Condition/Favourable Adequacy Margin/ Expedite Return to Service | Outages having low to negligible risk to the reliability of the IESO-controlled grid and are implemented to accomplish work that would have otherwise been unable to proceed. Note: Market participants may select this code, however the IESO will assess and determine the outage’s impact on the IESO-controlled grid. | Transformer feeder outage during existing outage to connecting circuit |
| Manually/Automatically Removed From Service | Unforeseen outages that result in manual or automatic removal of equipment/facilities from service. | Unit trip from neutral overcurrent |
| Failed to Synch | Unforeseen outages resulting from a failure to synchronize generation or electricity storage equipment/facilities to the IESO-controlled grid. | Unit breaker failed to synch |
| Segregated Mode of Operation | Outage to indicate generation or transmission equipment/facilities being disconnected from the IESO-controlled grid and connected to an external system, i.e. Quebec. | Generation facility connected to Quebec |
| Cyber Asset Change/ Relay Setting Change | Outages to indicate hardware/software changes for RTUs, gateways, routers, protection relays etc. intended to separate such requests from other general planned outages. | Software changes for RTU |
| Transmission Equipment Derating | Outages to indicate that a piece of transmission equipment is operating at a reduced equipment rating. | Transformer derating for degraded cooling |
| Switching | Short duration outage required to support the removal of equipment for a separate outage request. | Circuit terminals required for 15 min to switch circuit out of service |
| Telco Third Party Threat | Telecommunication outages requested of Hydro One by a third party telecom provider | Third party company to perform protection and control maintenance of Access Multiplexer |
| Self-Bottling | Outages implemented to indicate that a variable generation resource is operating to a reduced maximum generation output due to constraints resulting from transmission element outages within the resource’s facility. Note: This is to ensure that the centralized forecast predicts output of the station proportionate to their available capacity but capped at a derated maximum, rather than proportionate to their derated maximum as would be the case with a normal derate outage request. | 100 MVA variable generation resource normally connected to two 50 MVA transformers, but one transformer is out-of-service |
| Icing | Outages implemented to indicate reduced generation capacity due to icing conditions. | Ice on wind turbines |
| Other | Market participants may use this Purpose Code for outages being requested for any reason other than those listed above. | Generation facility or electricity storage facility unavailable for Generation Rejection |

## Constraint Codes

Constraint Codes identify the status of the equipment when the outage is under implementation. This information is used to determine the limitations on the equipment to determine the impact of the outage request on the IESO-controlled grid. For example, an ‘In Service’ code indicates the equipment is available and functional, whereas an ‘Out of Service’ code indicates the equipment will be unavailable for the duration of the outage.

Appendix C lists applicable Constraint Codes based on equipment type.

Market participants are required to use one of the following Constraint Codes when submitting their outage request.

Note: Selection of Constraint Codes is based on the Priority Code. For example, INFO and ABNO codes are only available for information outages. Refer to Section 2.6 for a mapping of Purpose and Priority Codes.

Table 2-4: Constraint Codes

| Constraint Code | Description | Examples |
| --- | --- | --- |
| Out of Service (OOS) | Equipment is unavailable and removed from service. | Breaker out of service |
| In Service (IS) | Equipment is available and in-service. | Normally open switch required in-service |
| Derated To (DRATE) | Equipment cannot operate above a specified capability that is less than its rated capability. | Generation facility or electricity storage facility derated to 50 MW |
| Must Run At (MUSTRUN) | Equipment can only operate at a specified capability that is less than or equal to its rated capability. | Generation facility or electricity storage facility must run at 50 MW |
| Hold Off (HOLDOFF) | Equipment has its reclosing capability blocked. | Circuit hold off |
| Protection Out of Service (PROT OOS) | Equipment’s primary or back-up protection is unavailable in some capacity. | Circuit’s B Protection out of service |
| Breaker Fail Protection Out of Service (BF PROT OOS)6 | A breaker’s backup protection is unavailable in some capacity. | Breaker Fail Protection for Breaker A out of service |
| Automatic Voltage Regulation or Power System Stabilizer Out of Service (AVR/PSS OOS)6 | Generation facility’s or, if applicable, electricity storage facility’s AVR or PSS is unavailable in some capacity. | Generation facility or electricity storage facility AVR out of service |
| Breaker Trip Coil Test (BTCT) | Breaker is undergoing a protection relay-initiated test operation. | Breaker trip coil test for Breaker A |
| Ancillary Service Out of Service (ASP OOS)6 | Equipment’s ability to provide a contracted ancillary service is restricted in some capacity. | Generation facility or electricity storage facility unavailable for Black-start, Regulation or Voltage Control |
| Information (INFO) | Equipment has a condition or limitation that does not require approval from IESO. | Generation facility unavailable for condense Derated dispatchable loads with a demand response capacity obligation |
| Available But Not Operating (ABNO) | Mechanism for generation facilities and electricity storage facilities to report they do not expect to participate in the market. | Generation facility or electricity storage facility off-peak demand Generation facility or electricity storage facility de-staffing |

## Low-impact Attributes

During outage request submission, market participants are required to answer certain questions to determine if their outage contains low-impact attributes, thereby making the equipment eligible for 1-Day Advance Approval, Auto Advance Approval  and/or Final Approval in Advance (further explained in Section 2.7.5, Section 2.7.6 and Section 2.7.7, respectively). Low-impact attributes are used by the IESO to further define the scope and impact of the requested equipment.

Refer to Appendix D for a list of attributes and applicability.

For example: Market participants submitting an outage request for line protection out of service, they need to specify whether it is only a loss of redundancy. If they answer “Yes”, the equipment is considered to have low-impact attributes.

Submission Timelines

The following are the submission timelines for outages on equipment with low-impact attributes:

- Must be submitted for 1-Day Advance Approval

- May be submitted for Quarterly, Weekly or 3-Day Advance Approval

- May be eligible for Auto Advance Approval and/or Final Approval in Advance

## Mapping Purpose, Constraint and Priority Codes

Each Priority Code applies to a set of Purpose and Constraint Codes. Table 2-5 below presents a mapping of all codes.

Table 2-5: Mapping of Purpose, Constraint and Priority Codes

| Priority Code | Purpose Codes | Constraint Codes |
| --- | --- | --- |
| Planned | - Commissioning - Cyber Asset Change - Maintenance - Other - Relay Setting Change - Repair - Replacement - Segregated Mode of Operation - Switching - Telco Third Party Threat - Testing | All except INFO and ABNO |
|  | - Self Bottling | DRATE |
| Urgent | - Environmental Concerns - Equipment Concerns - Other - Regulatory Concerns - Safety Concerns - Switching - Telco Third Party Threat | All except INFO and ABNO |
|  | - Icing - Self Bottling | DRATE |
| Opportunity | - Commissioning - Expedite Return to Service - Favourable Adequacy Margin - Favourable Generation Outage /Electricity Storage Condition - Favourable Transmission Outage Condition - Other - Segregated Mode of Operation - Switching - Testing | All except INFO and ABNO |
|  | - Self Bottling | DRATE |
| Information | - Other - Transmission Equipment Derating | - INFO - ABNO |
| Forced | - Automatically Removed from Service - Environmental Concerns - Equipment Concerns - Failed to Synch - Manually Removed from Service - Other - Regulatory Concerns - Safety Concerns | All except INFO and ABNO |
|  | - Icing - Self Bottling | DRATE |

## Timelines

### General Requirements

Market participants may request Quarterly, Weekly, 3-Day or 1-Day Advance Approval for their planned outages (MR Ch. 5, Sec. 6.2.2K). This section explains the submission and assessment periods for each advance approval timeframe. Eligibility for advance approval is determined by equipment criticality, as explained in Section 2.1.

Each advance approval process is associated with distinct submission, study and coverage periods. For the purposes of outage submission guidelines described in this document:

- “Study period” refers to the period when the IESO assesses planned outage requests submitted for the associated advance approval process. The IESO will notify market participants of its assessment by the end of the study period.

- “Coverage period” refers to the implementation period for outages that receive advance approval within the associated study period.

- Market participants must submit outage requests before the start of the associated study period, in order to receive advance approval for implementation during the associated coverage period.

Market participants must submit forced outage notifications when they occur and these will be addressed by the IESO immediately.

Market participants may submit urgent outage requests at any time. The IESO will study such requests as soon as possible.

Market participants may submit opportunity outage requests at any time. Such requests are considered late planned outage requests. The IESO is not obligated to consider such submissions, but may do so where the opportunity presents low to negligible risk to the reliability and/or operability of the IESO-controlled grid and or to the IESO (MR Ch.5, Sec. 6.4.6).

Market participants may submit information outage requests at any time. The IESO will use reasonable efforts to study such requests.

Table 2-6: Advance Approval Timelines and Eligibility

| Advance Approval Process | Submission Requirement (Prior to Start of Coverage Period) | Approval Deadline (Prior to Start of Coverage Period) | Eligible Equipment |
| --- | --- | --- | --- |
| Quarterly | 3 months prior | 1 month prior | All equipment types may be submitted |
| Weekly | 17 days prior | 10 days prior | Critical equipment must be submitted Non-critical and low-impact equipment may be submitted |
| 3-Day | 5 business days prior | 3 business days prior | Non-critical equipment must be submitted Low-impact equipment may be submitted |
| 1-Day | 2 business days prior | 1 business day prior | Low-impact equipment must be submitted Critical and non-critical equipment with low-impact attributes must be submitted |

Submission Timelines for Outages Supporting External RCs

Market participants may be required to conduct outages to support work planned by external RCs. In cases where market participants are unable to submit such outage requests for advance approval within the deadlines for planned outages, they are required to submit such outages with an Urgent Priority Code and refer to the RC work request in the ‘Purpose Description’ field in the outage management system. The IESO will consider it as a planned outage when determining priority. Refer to Section 2.2.1 for details on determining outage priority.

Note: The IESO’s obligation to assess such outage requests is based on the interconnection agreement with the external RC.

### Quarterly Advance Approval Process

The IESO facilitates long-term planning by offering market participants the option to receive approval for all planned outages up to eight months prior to the scheduled start time via the Quarterly Advance Approval process.

Outages submitted within this process get the highest priority compared to planned outages submitted under other timeframes, thus granting greater certainty to market participants. Refer to Section 2.2.1 for details on determining outage priority.

If an outage request is submitted for the Quarterly Advance Approval process after the submission deadline, the outage management system will automatically place the outage for assessment under the next Quarterly, Weekly, 3-Day or 1-Day Advance Approval process, as eligible, based on equipment criticality, ‘Request Weekly AA’ flag and planned start time.

The study and coverage periods for the Quarterly Advance Approval process are as shown in 2-1.

Figure 2-1: Quarterly Advance Approval Timeline

Study period for the Quarterly Advance Approval process begins at 00:00:00 EST on the first day of the period month and ends at 23:59:59 EST on the last day of the period month as shown in Figure 2-1. Coverage period for the Quarterly Advance Approval process begins 00:00:00 EST on the first day of the period month and ends at 23:59:59 EST on the last day of the period month as shown in Figure 2-1.

Note: The timelines for submission and assessment are inclusive of statutory holidays in Ontario and Saturdays and Sundays (Saturdays and Sundays hereafter referred to as weekend days).

By the end of the study period, the IESO will either:

- Provide advance approval, or

- Place the outage request in the ‘At Risk’ status

Market participants may choose to resubmit an outage placed in the ‘At Risk’ status at the end of a Quarterly study period. Resubmitted outage requests will retain the priority date of the original outage request if:

the original outage was scheduled to begin in the first three months of the current coverage period, and

it is resubmitted before the next study period, and

the resubmitted outage is scheduled to begin during the corresponding six-month coverage period (MR Ch. 5, Sec. 6.4.20).

Figure 2-2: Criteria for ‘At Risk’ Outage Retaining Original Priority

The IESO will re-assess outages placed in the ‘At Risk’ status at the end of the Quarterly study period during the next Quarterly, Weekly, or 3-Day Advance Approval process, as applicable based on equipment criticality and the status of the ‘Request Weekly AA’ flag.

Example A:

Figure 2-3: ‘At Risk’ Outage Reassessment – Example A

In the above figure, the market participant submits a request in September for an outage to critical equipment beginning in April of the following calendar year. The IESO studies the request during the October-November study period and transitions the outage to ‘At Risk’ status.

The IESO will re-assess the request during the January-February study period for Quarterly Advance Approval.

| If… | Then… |
| --- | --- |
| The IESO transitions the request to ‘At Risk’ status during the January-February study period | The outage will be re-assessed in the next Weekly Advance Approval process |

Example B:

Figure 2-4: ‘At Risk’ Outage Reassessment – Example B

Using the same timelines as Example A, the market participant submits an outage request for non-critical equipment for Quarterly Advance Approval. If the IESO transitions it to ‘At Risk’ status during the October-November and the January-February study periods, the outage will be re-assessed during the next 3-Day Advance Approval process.

| If… | Then… |
| --- | --- |
| The outage request has the ‘Request Weekly AA’ flag | The IESO will re-assess the request in the next Weekly Advance Approval process following the February study period |

### Weekly Advance Approval Process

Planned outage requests for critical equipment must be submitted for Weekly Advance Approval.

Market participants may also submit planned outage requests containing only non-critical or low-impact equipment under this process by selecting the “Request Weekly AA” flag in the outage management system.

Outages submitted within this process get a higher priority compared to planned outages submitted under 3-Day and 1-Day timeframes, thus granting greater certainty to market participants for outages to non-critical or low-impact equipment (that are required to be submitted within the 3-Day and 1-Day processes respectively). Refer to Section 2.2.1 for details on determining outage priority.

The IESO will also study outages with critical equipment and non-critical or low impact equipment with the “Request Weekly AA” flag placed in the ‘At Risk’ status from the Quarterly Advance Approval process during this time.

The study and coverage periods for the Weekly Advance Approval process are as shown in 2-5.

Figure 2-5: Weekly Advance Approval Timeline

Study period for the Weekly Advance Approval process begins at 16:00:00 EST on Friday and ends at 15:59:59 EST on the following Friday as shown in Figure 2-5.

Coverage period for the Weekly Advance Approval process begins 00:00:00 EST on Monday and ends at 23:59:59 EST on the following Sunday as shown in Figure 2-5.

Note: The timelines for submission and assessment are inclusive of statutory holidays in Ontario and weekend days.

For example, if the outage is scheduled to start on a Monday, the request must be submitted at least 17 days prior to the start of the outage. If the outage is scheduled to start on a Friday, the request must be submitted at least 21 days prior to the start of the outage.

By the end of the study period, the IESO will either:

- Provide a Weekly Advance Approval, or

- Reject the outage request

Note: Outage requests rejected during the Weekly Advance Approval process will not be re-assessed by the IESO. Market participants may resubmit rejected outages as new requests.

At this stage, the IESO, based on significant changes in system conditions such as forced outages and changes to Ontario demand forecast, may also revoke Quarterly Advance Approvals if implementation of the outage will impact the reliability of the IESO-controlled grid (MR Ch. 5, Sec. 6.4.9).

### Three-Day Advance Approval Process

Planned outage requests for non-critical equipment must be submitted for 3-Day Advance Approval.

Market participants may also submit planned outage requests containing only low-impact equipment under this process. Outages submitted within this process get a higher priority compared to planned outages submitted under 1-Day timeframe, thus granting greater certainty to market participants for outages to low-impact equipment (that are required to be submitted within the 1-Day process). Refer to Section 2.2.1 for details on determining outage priority.

The IESO will also study outages with non-critical equipment placed in the ‘At Risk’ status from the Quarterly Advance Approval process during this time.

This process repeats daily on business days with study and coverage periods as shown in Figure 2-6.

Figure 2-6: Three-Day Advance Approval Timeline

Note: In Figure 2-6, the timeline on the left illustrates a coverage period that falls on a weekend, and the timeline on the right illustrates a coverage period that falls on a weekday.

Study period for the 3-Day Advance Approval process begins at 16:00:00 EST on business days and ends at 15:59:59 EST, two business days later as shown in Figure 2-6.

Coverage period for the 3-Day Advance Approval process begins 00:00:00 EST on the fifth business day after the beginning of the study period, and ends at 23:59:59 EST on the same business day, as shown in Figure 2-6.

By the end of the study period, the IESO will either:

- Provide an advance approval, or

- Reject the outage request

Note: Outage requests rejected during the 3-Day Advance Approval process will not be re-assessed by the IESO. Market participants may resubmit rejected outages as new requests.

At this stage, the IESO may also revoke Quarterly and Weekly Advance Approvals if implementation of the outage will impact the reliability and/or operability of the IESO-controlled grid (MR Ch. 5, Sec. 6.4.9).

### One-Day Advance Approval Process

Planned outage requests containing only low-impact equipment must be submitted for 1-Day Advance Approval.

Market participants may also submit planned outage requests containing critical and non-critical equipment with low-impact attributes under this process, if eligible. Appendix D lists eligibility criteria for 1-Day Advance Approval.

This provides additional flexibility to market participants who are otherwise required to submit outages to critical and non-critical equipment in the Weekly and 3-Day Advance Approval processes, respectively.

Refer to Appendix D for a list of eligibility criteria for 1-Day Advance Approval.

For example,

| If… | Then… |
| --- | --- |
| A market participant submits an outage request, less than five business days prior to the scheduled start time, to a generation facility or, if applicable, an electricity storage facility with a ‘Automatic Voltage Regulation or Power System Stabilizer Out of Service (AVR/PSS OOS)’ Constraint Code AND answers “Yes” to the “Only a Loss of Redundancy” question | The outage will be eligible for 1-Day Advance Approval. |

The 1-Day Advance Approval process repeats daily with study and coverage periods as shown in Figure 2-7.

Figure 2-7: One-Day Advance Approval Timeline

Note: In Figure 2-7, the timeline on the left illustrates a coverage period that falls on a weekend, and the timeline on the right illustrates a coverage period that falls on a weekday.

Study period for the 1-Day Advance Approval process begins at 16:00:00 EST on business days and ends at 13:59:59 EST, one business day later, as shown in Figure 2-7.

Coverage period for the 1-Day Advance Approval process begins 00:00:00 EST on the second business day after the beginning of the study period and ends at 23:59:59 EST on the same business day, as shown in Figure 2-7.

By the end of the study period, the IESO will either:

- Provide an advance approval, or

- Reject the outage request.

At this stage, the IESO may also revoke Quarterly, Weekly and 3-Day Advance Approvals if implementation of the outage will impact the reliability and/or operability of the IESO-controlled grid (MR Ch. 5, Sec. 6.4.9).

### Auto Advance Approvals

Outage requests for low-impact equipment or equipment containing low-impact attributes may be eligible for Auto Advance Approval (Auto AA) when submitted via the outage management system. Market participants are required to answer certain questions to determine their eligibility for Auto AA. Refer to Appendix D – Column D in the table lists the questions that will be asked to market participants during outage request submission to determine eligibility for Auto AA.

Based on the answers provided by market participants, the tool will establish eligibility for and grant Auto AA. The tool will also check that there are no conflicting outages, as explained in Section 3.2.3.

The IESO also has the ability to mark equipment for exclusion from the Auto AA process. For example, breaker failure protection outage to a critical breaker could be excluded from Auto AA despite correctly responding to the low-impact questions outlined in Appendix D.

Priority for outages that are granted Auto AA will be based on the time of submission and advance approval process they would have been manually studied in by the IESO. This ensures the priority is aligned with the IESO’s manual assessment of the outage.

For example, if an outage request with non-critical equipment was submitted and auto-approved within the Quarterly process it would have a Quarterly Advance Approval priority. However, if the same outage request was submitted and auto-approved after the Quarterly submission deadline, it would have a 3-Day Advance Approval priority, based on equipment criticality and submission timeframe.

Going back to the example stated in Section 2.7.5, the outage request for the generation facility or, if applicable, electricity storage facility, is deemed eligible for 1-Day Advance Approval. Now,

| If… | Then… |
| --- | --- |
| A market participant submits an outage request, less than five days prior to the scheduled start time, to a generation facility or, if applicable, electricity storage facility with a ‘Automatic Voltage Regulation or Power System Stabilizer Out of Service (AVR/PSS OOS)’ Constraint Code, AND The market participant answers the low-impact question as follows: Only a Loss of Redundancy? = YES | The outage will be granted Auto AA with a 1-Day Advance Approval priority |
| A market participant submits an outage request, 18 days prior to the scheduled start time, to a generation facility or, if applicable, electricity storage facility with a ‘Automatic Voltage Regulation or Power System Stabilizer Out of Service (AVR/PSS OOS)’ Constraint Code, AND The market participant answers the low-impact question as follows: Only a Loss of Redundancy? = YES | The outage will be granted Auto AA with a Weekly Advance Approval priority |

The tool offers certainty to market participants by way of the automated approval, however outage priority will be based on manual assessment.

### Final Approval in Advance

A subset of outages for low-impact equipment or equipment containing low-impact attributes that are deemed eligible for Auto AA may receive Final Approval in Advance (FAA). The IESO determines eligibility for FAA based on the impact to the IESO-controlled grid, on a case by case basis.

Refer to Appendix D for criteria used to grant FAA.

The outage management system will transition the outage request to ‘Auto AA’ status and display a flag for market participants to confirm the outage request is eligible for FAA. On the day of the outage, the tool will automatically transition the outage to ‘Final Approved’ status.

For example,

| If… | Then… |
| --- | --- |
| A market participant submits an outage request, five days prior to the scheduled start time, to a generation facility or electricity storage facility with a ‘Protection Out of Service (PROT OOS)’ Constraint Code and provides the following answer to the low-impact question: “Only a Loss of Redundancy?” = YES - and Max Recall is ≤ 15 minutes | The outage will be transitioned to ‘Auto AA’ status and a flag will be displayed to confirm the outage is eligible for FAA. On the day of the outage, the outage request will be automatically transitioned to ‘Final Approved’ status. The market participant is not required to request final approval to implement the outage. |

Market participants who have received FAA for their outages are not required to request final approval in order to implement the outage.

The IESO may revoke the FAA of an outage request if it impacts the reliability and/or operability of the IESO-controlled grid and notify the market participant. In such cases the market participant must verbally request final approval to commence the outage by telephoning the IESO.

Outage requests submitted for equipment that is already scheduled out-of-service under a single, planned outage request with an ‘Out of Service (OOS)’ Constraint Code will be eligible for FAA provided the new outage request:

Contains the same or a subset of the equipment scheduled out-of-service,

Has an overall and period level planned start and end date that is the same, or within the same time period, as the existing outage request, and

Has been manually selected by the IESO to be eligible for FAA.

### Submission Deadlines

Figure 2-8 displays outage submission and IESO review timelines:

| At least 3 months prior to coverage period start | Submit outage requests for Quarterly Advance Approval |
| --- | --- |
| 1 month prior to coverage period start | IESO approves or transitions the outage into At-Risk status for the quarterly period |
| By 16:00 EST at least 17 days prior to coverage period start | Submit outage requests for Weekly Advance Approval |
| By 16:00 EST 1 week prior to coverage period start | IESO approves or rejects the request for Weekly Advance Approval. |
| By 16:00 EST 5 business days prior to coverage period start | Submit outage request for 3-day Advance Approval |
| By 16:00 EST 3 business days prior to coverage period start | IESO approves or rejects the request for 3-day Advance Approval |
| By 16:00 EST 2 business days prior to coverage period start | Submit outage request for 1-day Advance Approval |
| By 14:00 EST 1 business day prior to coverage period start | IESO approves or rejects the request for 1-day Advance Approval |
| Just prior to outage start | Request final approval to begin outage (Not applicable for outages that receive final approval in advance) IESO provides final approval or revokes advance approval |
| After IESO provides final approval | Implement outage |

Figure 2-8: Outage Submission and IESO Review Timeline

– End of Section –

# Procedural Workflow

## Facility Registration

Market participants are required to submit information regarding new or changes to existing facilities and equipment to the IESO via the online registration process outlined in Market Manual 1.5: Market Registration Procedures.

The IESO will assess the submitted information to determine whether the equipment affects the operation of the IESO-controlled grid and communicate their assessment to market participants via Online IESO. Market participants are notified of their equipment’s criticality level at this point. Changes to the IESO-controlled grid or system operating limits may require the IESO to review and update criticality levels of equipment.

Market participants whose facilities or equipment are determined to impact the IESO-controlled grid’s reliability will be required to report outages to the IESO. Refer to Appendix B for the detailed criteria that the IESO uses to assess outage-reporting requirements. Outages to system auxiliaries associated with this equipment must also be reported as identified in Appendix B.

Market participants may submit an exemption application according to the process outlined in the Market Manual 2.2: Exemption Application and Assessment procedure to apply for facility equipment to be entirely or partially exempted. Requests for exemptions from outage reporting are assessed by the IESO on a case-by-case basis as specified in MR Ch. 1, Sec 14. Assessments are communicated to market participants via Online IESO.

Market participants may also register one or more control centres via the online registration process to represent the location of their real-time operations. This facilitates the submission of outages that are not associated to a particular station, e.g. SCADA systems.

## Outage Coordination

The IESO facilitates the outage coordination process for market participants by providing the following:

- Undesirable situations – outlined in this manual

- Outage planning guidelines – confidential reports published by the IESO and embedded in the outage management system

- Conflicting Constraint Codes– embedded in the outage management system

- Conflict checking feature– embedded in the outage management system

- Outage Coordination for Capacity Exports

- Outage Coordination for generator-backed capacity import resources

- IESO Reports – public reports published by the IESO

### Undesirable Situations

When assessing outage requests, the IESO will use the following general criteria to identify any undesirable situations the outage request may result in:

- Negative impacts on the reliability (security and/or adequacy) and/or operability of the IESO-controlled grid, or

- Capacity and energy shortfalls, or

- Material impact on the operation of the IESO-administered markets (MR Ch. 5, Sec. 6.1.1).

Market participants may request to reposition their scheduled outages based on their priority date, to avoid these undesirable situations.

### Outage Planning Guidelines

The IESO will issue confidential outage planning guidelines to facilitate the assessment of grid reliability. The outage planning guidelines will assist market participants to avoid undesirable situations when scheduling outages. The guidelines will provide the following information:

- Transmission Group: the category used to group associated transmission elements and/or generation facilities and/or electricity storage facilities, specified along with timeframe. There are some groups with the same name succeeded by a number. These were created to account for all possible combinations of the elements within that group. For example, if the original Transmission Grouping was defined as Group A, for implementation it was broken down into Group A (1) and Group A (2) as follows:

| Transmission Grouping | Transmission element | Threshold | Group |
| --- | --- | --- | --- |
| Group A | Line A/Line B | 1 | Original Group |
|  | Line C |  |  |
| Group A (1) | Line A | 1 | Implemented Groups |
|  | Line C |  |  |
| Group A (2) | Line B | 1 | Implemented Groups |
|  | Line C |  |  |

- Timeframe: the applicable seasonal timeframe, specified with the transmission group name. Where not specified, the group will apply throughout the year.  Table 3-1 defines seasonal timeframes:

Table 3-1: Seasonal Timeframe

| Timeframe | From | To |
| --- | --- | --- |
| All season | 01-Jan | 01-Jan |
| Summer | 15-May | 14-Sep |
| Winter | 15-Nov | 14-Mar |
| Spring | 15-Mar | 14-May |
| Fall | 15-Sep | 14-Nov |

- Element:  the specific piece of equipment within the group.

Note: The bus must be included in the outage request if all bus breakers are out of service. The line disconnect must be included in the outage request if all terminal breakers are out of service.

- Threshold: the number of elements from the list that are permitted out of service at one time.

For example, a threshold of 2 means only two elements from the list can be scheduled out of service at the same time without any conflict.

- Reason: the phenomena causing the conflict. This is based on the IESO’s assessment of situations that would:

  - compromise the reliability of the transmission system,

  - result in the inability to maintain the system within system operating limits using normal operating procedures, or

  - result in the inability to restore the transmission system to normal operating conditions following a respected contingency.

For example, phenomena might comprise of pre and post contingency thermal concerns, pre and post contingency voltage concerns, pre and post contingency stability concerns, black-start restoration paths, or resource constraints.

- Distribution: the list of market participants who will be notified of the outage planning guideline. The distribution list will only include those market participants that own or operate equipment in the transmission group.

For example, in Table 3-2 below, all market participants that own or operate any section of Line X will be on the distribution list. Outages for equipment tapped off Line X would not be restricted and therefore, would not be on the distribution list.

Table 3-2: Sample Outage Planning Guideline

| Transmission Group | Transmission Elements | Threshold | Reason | Distribution |
| --- | --- | --- | --- | --- |
| Group 1 | Line X | 1 | Thermal concerns |  |
|  | Line Y |  |  |  |

Market participants will be able to access the guideline at the IESO Reports webpage under Participant Reports. The IESO will periodically review the outage planning guideline and updates will be published as per the Baseline schedule.

### Conflicting Constraint Codes

Upon submission of outage requests, the outage management system will check outages for equipment with conflicting Constraint Codes for the same time period. For example, Generator A has an outage request with ‘ABNO’ Constraint Code that overlaps with another request for Generator A to be OOS.

Outage requests are considered to be in conflict when all of the following are true:

- The outage request priority codes are Forced, Forced Extended, Urgent, Planned or Opportunity, and

- the outage requests overlap for any length of time, and

- the outage requests have a status of Submitted, Study, Negotiate, At Risk, Advance Approved, or Implemented, and

- the outage request periods share the same equipment and have constraint codes that are flagged to be in conflict with each other as shown in Table 3-3 below:

Table 3-3: Outage Request Constraint Code Conflicts

|  | OOS | IS | DRATE | HOLD OFF | MUST RUN | BTCT | PROT OOS | BF PROT OOS | AVR/PSS OOS | ASP OOS | INFO | ABNO |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OOS |  | X |  |  |  |  |  |  |  |  |  | X |
| IS | X |  |  |  |  |  |  |  |  |  |  | X |
| DRATE |  |  |  |  |  |  |  |  |  |  |  |  |
| HOLDOFF |  |  |  |  |  |  |  |  |  |  |  |  |
| MUSTRUN |  |  |  |  |  |  |  |  |  |  |  | X |
| BTCT |  |  |  |  |  | X |  |  |  |  |  |  |
| PROT OOS |  |  |  |  |  |  | X |  |  |  |  |  |
| BF PROT OOS |  |  |  |  |  |  |  | X |  |  |  |  |
| AVR/PSS OOS |  |  |  |  |  |  |  |  | X |  |  |  |
| ASP OOS |  |  |  |  |  |  |  |  |  | X |  |  |
| INFO |  |  |  |  |  |  |  |  |  |  |  |  |
| ABNO | X | X |  |  | X |  |  |  |  |  |  | X |

In addition to the conditions described above, outage requests that meet any of the following conditions will also be considered to be in conflict:

- The outage request’s equipment are on the same undesirable outage combination, or

- UFLS validation fails, or

- Outage requests with BF PROT OOS constraint codes are overlapping at the same stations.

For example,

| If… | Then… |
| --- | --- |
| Outages for Line 1 A PROT OOS and Line 1 B PROT OOS overlap | The outage management system will display a conflict |
| Line 1 A PROT OOS and Line 2 B PROT OOS overlap | The outage management system will NOT display a conflict |

### Conflict Checking

The outage planning guidelines and conflicting constraint codes are embedded in the outage management system. If a submitted outage request is in conflict with another outage based on these criteria, the tool will display:

- An error message that the outage is in conflict,

- ID number of the outage(s) it is in conflict with (details regarding the conflicting outage are classified as confidential information and will be visible to market participants based on viewership rights), and

- Requirement to provide a rationale for the conflict to be allowed (details on conflict rationale are provided below).

Market participants may determine the planned times of the conflicting outage(s) (either via the outage ID number or by contacting the IESO) and reschedule the outage to avoid the conflict.

#### Conflict Rationale

Outage requests having conflicts may be submitted as long as market participants provide a rationale for doing so. A complete rationale is required for the IESO to consider the outage – that is, for clearance the market participant must identify how the pieces of equipment are related, physical proximity, and the reason why other control actions are not available. Table 3-4 below lists criteria for the IESO to consider outages based on conflict rationale.

Table 3-4: Criteria for Conflict Rationale Acceptance

| Advance Approval Process | Acceptable Conflict Rationale Description | Examples |
| --- | --- | --- |
| Quarterly Advance Approval process | Only non-discretionary rationale will be accepted | Clearance Degradation of protection or cooling Vacuum building outage |
| Weekly, 3-Day and 1-Day Advance Approval processes | Discretionary rationale may be considered provided there is valid justification | Favourable Ambient Conditions/Short Duration: the reason for the outage conflict is for thermal concerns, but the outage is scheduled overnight during lower load conditions. Pre-contingency Control Actions: transfer load to alleviate thermal concerns or reconfigure transmission system so the contingency sheds load by configuration. Partial Equipment Outages: Situations when only certain sections of the line are being taken out of service as shown in the diagram below, where the path critical to the transfer of power is not interrupted. Short Recalls: Conflicts for post-contingency concerns may be resolved by recalling the outage within 15 minutes. |
| Real-time process | Conflicts will only be considered for forced and urgent outages | Forced outage to equipment for safety or environmental concern |

The IESO will evaluate submitted rationale on a case-by-case basis and determine whether to allow the conflict to proceed or require the market participant to reschedule.

If the rationale does not meet the criteria described above and is deemed insufficient, the IESO will notify the market participant to reschedule the outage.

### IESO Reports

The IESO publishes near-term and long-term reports to assist market participants in scheduling their outages when they are more likely to receive approvals:

- Near-term reports: Adequacy Reports and Transmission Facility All in Service Limits Reports and Transmission Facility Outage Limits Reports contain demand forecasts and assessments for Ontario and are published by the IESO for informational purposes. Refer to Market Manual 7.2: Near-Term Assessments and Reports for further details on these reports.

- Long-term report: As per the market rules, the IESO prepares and publishes demand forecast, and a security and adequacy assessment for an 18-month period, on a quarterly basis (MR Ch. 5, Sec. 7.1.1.4 and 7.3.1.2). Refer to Market Manual 2.11: Reliability Outlook and Related Information Requirements for further details on this report.

## Outage Coordination for Capacity Exports

A Capacity Seller may have obligations with respect to the coordination of outages under applicable agreements with external control areas. Any such obligations are between the Capacity Seller and the external control area or capacity buyer, and are in addition to the obligations that the Capacity Seller has pursuant to the market rules and market manuals.

The IESO will continue to review outage requests in accordance with this market manual. Any additional review of outages by the external control area pursuant to the applicable agreements is independent of the IESO’s review.

All outages and/or derates to a Capacity Resource that have partially committed capacity will be applied proportionally between capacity committed to the external control area and the IESO-administered markets. For example, where there is an outage to a Capacity Resource that has committed a portion of its capacity to an external control area (e.g., 30% of installed capacity), the IESO will assess impacts to adequacy based on the uncommitted capacity portion (i.e., remaining 70% of installed capacity).

### Capacity Seller Requirement to Coordinate with Transmitters Prior to IESO Involvement

Refer to Market Manual 13.1: Capacity Export Requests, Section 3: Capacity Seller Requirement to Coordinate with Transmitters for information and requirements relating to coordination with transmitters regarding outages when submitting a capacity export request and prior to a Commitment Period.

- Should a planned outage to transmission facilities arise whereby a Capacity Resource would be rendered Grid-incapable during a Commitment Period, the IESO may reject or revoke the planned outage provided certain conditions are met, including the Capacity Seller having demonstrated that it has made best efforts to work with the transmitter to reschedule the planned outage. In order to demonstrate to the IESO that best efforts have been made in the event such circumstances arise, a Capacity Seller must communicate with the applicable transmitter as described in Section 3 of Market Manual 13.1, and as set out below. The following explains the general process that the Prospective Capacity Seller should follow with the transmitter during the Commitment Period to demonstrate to the IESO that best efforts have been made to reschedule a planned outage should such circumstances arise:

- Schedule a meeting (or multiple meetings, if necessary) in which it notifies the applicable transmitter of any capacity export commitments and determines if there are existing planned outages (unapproved or approved) that would render the Capacity Resource Grid-incapable at any time during the proposed Commitment Period.

- Update the outage request (visible to the applicable transmitter) in the IESO’s CROW system submitted in accordance with Market Manual 13.1, Section 3 with an information priority code, indicating the details of any capacity export commitments.

- Throughout the Commitment Period, continue to check with the transmitter by, among other things, monitoring the CROW system, to determine if there are any planned outages during the proposed Commitment Period that would render the Capacity Resource Grid-incapable.

  - Should there be planned outages during the proposed Commitment Period that would render a Capacity Resource Grid-incapable for, work with the transmitter to address the conflict, for instance:

    - The transmitter may agree to reschedule the planned outage.

    - The transmitter may accept the risk of potential rejection or revocation of the planned outage in the event that it is determined that the planned outage will, during the Commitment Period, pose an unacceptable risk of an adequacy shortfall to the external control area.

- Whenever applicable, update the applicable outage request with the information priority code indicating any changes or new information, including the resolution of any conflicting outages that may arise.

### Capacity Seller Requirement to Coordinate with Transmitters Requiring IESO Involvement

If the IESO is advised by the Capacity Seller that the external control area operator has determined that a transmitter’s planned outage that would render a Capacity Resource Grid-incapable would result in an unacceptable risk of an adequacy shortfall to the external control area and the transmitter and Capacity Seller are not able to come to an agreement to reschedule the planned outage, the Capacity Seller must contact the IESO. The IESO will assess whether the Capacity Seller has used its best efforts to reschedule the planned outage with the transmitter and whether any reliability concerns will arise if the transmitter’s planned outage is rejected or revoked.

Examples of transmission outages necessary for reliability include, but are not limited to:

Transmission outages that would prevent a future forced outage from occurring (e.g., a load supplied by a single transformer or line that would be forced out-of-service due to equipment concerns).

Transmission outages that would leverage opportune generation and load profiles (e.g., matching outages with seasonal generational support).

Transmission outages that would restore instantaneous protections and respective communication mediums.

If the IESO determines that the outage is for reliability purposes, the IESO will advise the Capacity Seller who may inform the external control area operator.

If the IESO determines that best efforts have been made and there is no reliability concern, the IESO may reject or revoke the planned outage pursuant to Market Rules Chapter 5, Section 6.4. The IESO will not, pursuant to this section, recall outages to facilitate called capacity exports or reject or revoke forced outages or urgent outages, or outages that bottle a resource’s output.

## Outage Coordination for Generator-Backed Capacity Import Resources

Generator-backed capacity import resources are required to submit planned outage requests to the IESO for approval prior to submitting the outage request to the external control area.

All derates to a generator-backed capacity import resource, whether a planned outage or forced outage, shall be applied proportionally between the capacity committed to the IESO and the external control area. Import offers associated with the generator-backed capacity import resource shall reflect the de-rated capacity to the extent that such generator-backed capacity import resource has been de-rated below its capacity obligation.

For example, in a scenario where a generator-backed capacity import resource commits 100MW to the external control area and 50MW to the IESO through a capacity obligation, and experiences a 30MW de-rate, the de-rate would be applied according to the 100:50 ratio representative of the allocation of the committed capacity between the external control area and the IESO. The 30MW de-rate would correspond to a respective 20MW and 10MW supply reduction in the external control area and the IESO, and could limit the transaction associated with the generator-backed capacity import resource to 40MW. In this example, the generator-backed capacity import resource would submit a 10MW de-rate (i.e. derate to 40MW) to the IESO.

Although import offers associated with a generator-backed capacity import resource shall be placed on the applicable boundary entity resource for generator-backed capacity import resources, traders are not excluded from submitting import offers on other boundary entity resources.

In cases where there is a planned transmission outage within the external control area that would directly disconnect the resource from the external grid, the generator-backed capacity import resource shall work with the transmission owner and or the external control area balancing authority/reliability coordinator to reschedule the planned outage, as per the requirements set out in the applicable external control area’s rules and regulations. Any such obligations are between the generator-backed capacity import resource and the external control area, and are in addition to the obligations that the generator-backed capacity import resource has with the IESO pursuant to the market rules and market manuals.

The IESO will continue to review outage requests in accordance with this market manual. Any additional review of outages by the external control area pursuant to the applicable agreements is independent of the IESO’s review.

Table 3-5 below provides example codes for generator-backed capacity import resources when submitting planned outage requests.

Table 3-5: Applicable Codes for Generator-backed Capacity Import Resources

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - DERATE or OOS | - Other |

## Outage Submission

Market participants submit outages through the outage management system and the IESO uses that tool to confirm receipt and communicate approval back to the market participant. Market participants access the outage management Application Programmatic Interface (API) either through:

- The IESO’s web link located in the IESO Portal, or

- Their own outage management program.

Typically, an outage request will include the following information:

Table 3-6: Information Requirement during Outage Submission

| Name of Field in the Tool | Information To Be Provided by Market Participants |
| --- | --- |
| Applicant | The market participant that is submitting the information. |
| Single Point of Contact (SPOC) | The request will identify a SPOC for the market participant, either an individual or a position, along with sufficient information to enable effective communication with that SPOC (such as phone, fax, or email). For market participants with direct input to the outage management system, contact information for responsible parties will be on file with the IESO. |
| Priority Code and Purpose Code | Each outage request must contain appropriate Priority and Purpose Codes. See Section 2 for more details. |
| Purpose Description | General information about the outage, such as a brief description of the purpose and specific requirements or information pertinent to the outage (for example “Loading levels for a generation facility test”). Any regulatory requirements for an outage must be included in this information. |
| Request Weekly AA | For non-critical or low impact equipment, indicate if the outage is submitted under the Weekly Advance Approval process. |
| Requested Equipment | Sufficient information must be provided to identify and describe, if required, the specific piece of equipment, using the equipment identification and location confirmed by the IESO in Market Manual 1.5: Market Registration Procedures. |
| Planned Start and End Date/Time | The submission must include the requested start date, start time, end date and end time. |
| Maximum Recall Time | The submission must include recall time, which is the total amount of time that would be required to return the equipment to service upon a request by the IESO. Market participants may submit optional comments to the IESO to provide more information. |
| Recurrence | This information will describe the periodic nature of the outage, that is, whether the outage is continuous, continuous except for weekends, daily, etc. |
| Constraint Code | Each piece of equipment on the outage request must contain a constraint code to specify the equipment limitations. This will be based on the status of the equipment when the outage is implemented (for example: OOS, IS, MUSTRUN). See Section 2.4 for more details. |
| Equipment Description (Mandatory for Constraint Codes specified in Table 2-4 and Equipment Classes specified in Table C-1.) | General information about the equipment, such as a brief description of the status and condition of the equipment pertinent to the outage (for example “Generation facility unavailable for Black-start”). Any regulatory requirements for an outage must be included in this information. |
| MW Impact | Indicate the impact, if any, on real power resources which will result from the outage. This would be the direct impact associated with the specific piece of equipment rather than an indirect impact. |
| MVAR Impact | Indicate the impact, if any, on reactive power resources that will result from the outage. This would be the direct impact associated with the specific piece of equipment rather than an indirect impact. |
| Conflict rationale | This information will be used by the IESO to verify the importance of scheduling the outage in case of conflicts. Note: This field will not be visible to market participants with third party viewership. |
| Market participant to IESO Comments | Market participants shall use this section to notify the IESO of any additional information, including details of their assessment, associated outage requests, switching details, etc. Generation facilities and electricity storage facilities shall also use this section to notify the IESO of any intent to arrange for replacement energy in the form of imports (MR Ch. 5, Sec. 6.3.6). When these arrangements are finalized, market participants shall provide the following information: - The MW amount and duration, - The intertie zone or zones through which the replacement energy is intended to be scheduled, - The boundary entity that shall submit the offers and schedule the replacement energy if dispatched by the IESO, and - Information regarding the e-Tag associated with the import, including a unique identifier, tag ID or tag format to be used. - Refer to Section 5 for details on arrangement of replacement energy. - Note: This field will not be visible to market participants with only third party viewership access. |
| Low-impact Questions | Based on the information submitted, market participants may be required to answer a few low-impact questions. This is to determine if the outage is eligible for 1-Day AA Auto AA, and/or FAA, as explained in Sections 2.7.5, 2.7.6 and 2.7.7, respectively. Refer to Appendix D – Column D in the table lists the questions that will be asked to market participants. |

## Outage Assessment

An outage request is assessed for its potential impact on the reliability and/or operability of the IESO-controlled grid with respect to the following:

- Reductions in system operating limits, interconnection reliability operating limits or changes in power transfers which encroach on a system operating limit,

- Will or is reasonably likely to have an adverse impact on the reliable operation of the IESO-controlled grid,

- Operating limits available and adequate monitoring tools available,

- Adequate system and area reserve,

- Adequate pre/post contingency assessment, voltage levels, islanding concerns, equipment limits and control actions,

- Adequate ancillary services requirements,

- System (global) and local area adequacy – capacity and energy,

- High-risk operating state, conservative operating state, or emergency operating state conditions, and

- Duplicated supply facilities including station service supply and protection systems

Refer to Market Manual 7.4: IESO-Controlled Grid Operating Policies for more details on the IESO’s reliability assessment. The IESO may provide details of their assessment under the ‘IESO to Market Participants Comments’ field in the outage management system.

Note: This field will not be visible to market participants with only third party viewership access.

### Market Participant Updates

Market participants may update an outage request while it is being assessed by the IESO. Changes other than the purpose description or comments require notification to the IESO by telephone. The IESO will assess the impact of the change. Revised outage requests will be assessed within the original study period.

| If the update is … | The IESO shall… |
| --- | --- |
| An insignificant change as explained in Section 2.2.1 | Allow the market participant to update the request. |
| A significant change as explained in Section 2.2.1 | Allow the market participant to update the request and revise the priority date. |

### Outage Assessment Outcomes

Table 3-7 below describes the next steps and associated obligations following the IESO’s assessment of outages.

Table 3-7: Outage Assessment Outcomes and Next Steps

| IESO Assessment Outcomes | Possible Next Steps | Associated Obligations |
| --- | --- | --- |
| Provide advance approval (as per timelines in Section 2.7 | Final Approval | On the day of the outage, market participants, must contact the IESO Control Room via telephone when they are ready to proceed with the outage. The IESO will, in general, provide final approval to a planned outage unless it foresees an adverse reliability impact, based on ongoing security and adequacy assessments. When requesting final approval, market participants should give due consideration to any adjustments, to generation patterns – or for electricity storage facilities, injection patterns – or system configuration required by the IESO prior to removal of equipment from service and the time required to effect these adjustments (MR Ch.5 Sec. 6.4.3.3). Outages that are eligible for FAA will be automatically granted Final Approval at the beginning of the planned start date of the outage. |
|  | Revocation | Market participants have the option of resubmitting or canceling the outage. The IESO will work with market participants to re-schedule the planned outage to a date and time at which the outage will not likely have an adverse impact on the reliability and /or operability of the IESO-controlled grid. Where practical, the IESO will consider date and time preferences of market participants when re-scheduling the outage (MR Ch.5, Sec.6.4.10) The original priority date is maintained if market participants re-submit the outage within five business days of being revoked (MR Ch. 5, Sec.6.4.10). |
|  | Outage Start Delays | Market participants must inform the IESO if they expect their outage to be delayed from starting as scheduled and whether the delay is expected to result in a planned extension. - Start of outage delayed by 30 minutes or less: Market participants must notify the IESO Control Room by telephone - Start of outage delayed by greater than 30 minutes: Market participants must notify the IESO Control Room by telephone and update their outage request. |
|  | Planned Extension | Market participants must submit requests for planned extensions as a new outage request. The new request must reference the outage ID of the on-going planned outage in the outage management system. The IESO will review planned extension requests on a reasonable effort basis if the outage request was scheduled to start and end on the same day. Otherwise the planned extension will be treated as a late submission and either rejected or revoked. The IESO will reject the request for planned extension if it is determined that the extension is likely to adversely impact the reliability and /or operability of the IESO-controlled grid or is likely to require the rescheduling, recall of revocation of a planned outage request previously submitted to the IESO (MR Ch.5, Sec 6.4.8). In such cases, market participants shall ensure the outage duration does not exceed the originally approved planned outage or the period as advised by the IESO when rejecting the outage request (MR Ch.5, Sec 6.4.8). |
| Negotiate to reschedule | Reschedule outage or advanced approval | Market participants must reschedule the outage following discussions with the IESO. The priority date of the original outage request will be retained during resubmission if completed within study timeframe. |
|  | Cancellation | Market participants must cancel the outage request in the outage management system. |
|  | Rejection (for outages submitted under the Weekly, 3-Day or 1-Day Advance Approval processes) | The IESO will provide market participants with the reason for rejection, subject to applicable confidentiality restrictions. Market participants may submit a new outage request. Original priority date will be retained if resubmitted within five business days and it was the first time that the outage was rejected (MR Ch. 5 Sec 6.4.17). If these conditions are not met, the resubmitted outage request will receive a new priority date. |
|  | ‘At Risk’(for outages submitted under the Quarterly Advance Approval Process) | The IESO will provide market participants with the reason for placing the outage ‘At Risk’, subject to applicable confidentiality restrictions. The IESO will review the outage during the next Quarterly, Weekly, 3-Day or 1-Day assessment window, as explained in Section 2.7.2. Market participants may choose to re-submit outages placed ‘At Risk.’ Refer to Section 2.7.2 for criteria for retaining original priority for re-submitted outage requests. |

## Outage Implementation

Outages that have received final advance approval from the IESO can be placed into implementation. Market participants are required to notify the IESO Control Room to confirm that the outage has commenced (MR Ch. 5, Sec. 6.4B.1) by providing actual start times through outage management system, unless otherwise determined by the IESO.

| If… | Then… |
| --- | --- |
| After implementation, the market participant wishes to adjust the actual start time of the outage | The market participant must call the IESO Control Room and request that the IESO clears their implementation and must provide the reason for the change. The IESO will assess the validity of the request and if approved, transition the outage to ‘Final Approved’ status which will delete the actual start time. The market participant must input the adjusted actual start time in the outage management system and transition the outage from ‘Final Approved’ to ‘Implemented’ status. |

### Planned and Forced Extensions

Market participants have the option of forced extensions, in cases where personnel safety or equipment damage may result. However, forced extensions for planned work will be reviewed for possible violations of the market rules. Forced extensions to planned or forced outages must be electronically updated in the outage management system by market participants and communicated via telephone to the IESO Control Room. If the forced extension is identified by 15:00 EST, one business day prior to the planned end time of the outage, market participants shall, on a reasonable effort basis, also communicate the forced extension to the IESO Market Forecasts & Integration department.

Planned extensions to planned outages must be submitted as new outage requests.

### Recall

Any time during implementation, the IESO may recall either the current period or the entire outage, based on sudden or unexpected impacts to the reliability and/or operability of the IESO-controlled grid. The IESO will provide affected market participants with the reason for the recall. Details regarding market participant compensation in cases of outage recall are provided in Section 3.8.

Market participants will be expected to meet the recall times specified in the original submission for the planned outage. No outage will be recalled unless the IESO has revoked or rejected all other planned outages that have not yet started and which could eliminate the need to recall the outage already in progress (MR Ch. 5, Sec. 6.4.11).

Generation facilities have the option to arrange for replacement energy to preclude being recalled. Further details on replacement energy are provided in Section 5.

### 3.7.3	Suspension of Non-Urgent Maintenance or Switching

If the IESO-controlled grid is in a conservative operating state, the IESO may direct market participants to suspend any non-urgent maintenance or switching activities.

## Outage Completion

Market participants are required to (MR Ch. 5, Sec. 6.4A):

- Notify the IESO by telephone when either the current period or the entire planned or forced outage has been completed,

- Request IESO approval by telephone to return equipment to service before doing so,

- Receive IESO approval to return the equipment to service. The IESO will notify market participants at this time if they wish to direct the operation of equipment to return it to service, and

- Notify the IESO when equipment that was the subject of a planned or forced outage has been fully restored to service by providing actual end times through the outage management system, unless otherwise determined by the IESO.

| If… | Then… |
| --- | --- |
| After completion, the market participant wishes to adjust the actual end time of the outage | The market participant must call the IESO Control Room and request that the IESO clears their completion and must provide the reason for the change. The IESO will assess the validity of the request and if approved, transition the outage to ‘Implemented’ status which will delete the actual end time. The market participant must input the adjusted actual end time in the outage management system and transition the outage from ‘Implemented’ status to ‘Completed’ status. |

## Outage Compensation

Generation facilities, electricity storage facilities, distributors and wholesale customers whose planned outages are revoked or recalled by the IESO are entitled to compensation for expenses associated with the revocation or recall, subject to the following conditions (MR Ch. 5, Sec. 6.7.2):

- the outage was originally provided advance approval by the IESO,

- the outage was recalled or had advance approval revoked because of a material error in the IESO’s demand forecast, a failure of generation facilities or electricity storage facilities within the IESO control area, a failure of facilities forming part of the IESO-controlled grid, or a failure of interconnection facilities, and

- the out-of-pocket expenses exceed $1,000.00.

Under the market rules, only out-of-pocket costs are eligible for compensation. These are sunk costs that are unrecoverable and will be incurred again by market participants in order to complete the outage. Items such as overtime costs and equipment rentals are eligible.

Market participants, whose Quarterly, Weekly or 3-Day Advance Approval for a planned outage on a generation facility or electricity storage facility is initially granted and then revoked by the IESO, will not be eligible for compensation if (MR Ch. 5, Sec. 6.7.3A):

- The IESO revoked the advance approval due to a forced outage of another generation facility or electricity storage facility with the same registered market participant as the generation facility or electricity storage facility that submitted the planned outage request and the forced outage occurred before 16:00 EST three business days prior to the scheduled start of the planned outage, or

- The IESO revoked the advance approval due to delayed return to service from a planned or forced outage of another generation facility or electricity storage facility with the same registered market participant as the generation facility or electricity storage facility that submitted the planned outage request, or

- A planned outage is granted Quarterly Advance Approval and scheduled to start in the last three months of a six-month coverage period, and the IESO revokes the Quarterly Advance Approval before the end of the next quarterly study period.

Example A: Market participant NOT entitled to compensation

As shown in Figure 3-1 below, the outage is scheduled for May and receives Quarterly Advance Approval in November. The IESO revokes quarterly approval in January. In this case, the market participant is not entitled to compensation because the revocation is done before the next quarterly study period ends in February.

Figure 3-1: Compensation Eligibility – Example A

Example B: Market participant entitled to compensation

In this example, the outage is scheduled for May and the IESO revokes Quarterly Advance Approval in March (i.e. after the next quarterly study period ends in February). Therefore, the market participant is entitled to compensation.

Figure 3-2: Compensation Eligibility – Example B

Example C: Market participant entitled to compensation

In this example, the outage is scheduled to start in March which is within the first three months of the quarterly coverage period, therefore even though the IESO revokes the outage before the end of the next quarterly study period in February, the market participant is entitled to compensation.

Figure 3-3: Compensation Eligibility – Example C

Generation facilities or electricity storage facilities whose planned outages have advance approval revoked or are recalled even though they had successfully arranged for replacement energy, are eligible for compensation. However, the generation facility or electricity storage facility will not be eligible for compensation for any lost opportunity costs associated with the import energy that was secured through the arranged replacement energy.

Claims for compensation must be submitted using the “Request for Outage Compensation” (IMO_FORM_1350) that is available on the IESO’s website (See Appendix A), and substantiated by receipts or statements detailing each line item. These claims will be subject to audit and verification by the IESO.

Transmitters are not entitled to compensation for any costs, losses or damages associated with the revocation or recall of a planned outage (MR Ch. 5, Sec. 6.7.1).

Each act of revocation or recall by the IESO shall be treated separately for compensation purposes (MR Ch. 5, Sec. 6.7.7).

– End of Section –

# Outage Reporting Requirements

This Section 4 outlines outage reporting requirements that are specific to certain classes of market participants when submitting outage requests to the IESO, unless granted exemption. Each sub-section provides sample Priority, Purpose and Constraint Codes that market participants may use when submitting outage requests via the outage management system. For detailed description of these codes, refer to Sections 2.2, 2.3, and 2.4. Refer to Section 2.6 for a mapping of these codes.

Note: The rules for submission, approval and determining priority as per market rules are applicable for all outage requests.

## Generation and Electricity Storage Facilities

Aggregated generation facilities and electricity storage facilities are required to report forced outages, unit limitations, deratings, de-staffing and any change in status that affects the maximum output of a generation unit, electricity storage unit, the minimum load of a generation unit, or the availability of a generation unit or electricity storage unit to provide ancillary services such as regulation, operating reserve, voltage support, black start capability or must run contracts (MR Ch. 5, Sec. 3.6.1 and 3.8.1).

All other outage requests related to the electricity storage facility’s injection capability should follow the applicable generation unit permissions and requirements outlined in this market manual.

An electricity storage facility wishing to report its inability to withdraw must update its dispatch data accordingly and submit outage requests as follows:

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - DERATE | - Repair |

Note: This section is intended for the reporting of all outages with the exception of state of charge capability changes in real-time; for such changes see Market Manual 4.2 - Submission of Dispatch Data in the Real-Time Energy and Operating Reserve Markets.

For electricity storage facilities wishing to undergo testing, see Section 4.1.2.

### Deratings

All generation facility and electricity storage facility deratings, including those resulting from generation facility or electricity storage facility start-up or shutdown, are required to report outages in the following circumstances:

- Any planned or forced material reduction in generation facility or electricity storage facility output that causes a derating equal to the greater of 2% of rated output or 10 MW,

- A component failure, operational limit or other circumstance that will cause the unit to trip if no control actions can be taken before the condition can be repaired as assessed by the generation facility or electricity storage facility, and

- A new potential change in unit/plant condition that can cause the loss of multiple units at its facility based on its internal assessment/forecast.

A generation facility or electricity storage facility wishing to ramp down for a planned outage is required to follow either of the following methods:

- Submit and get approval for a planned outage request. The generation facility or electricity storage facility will be ramped down at the submitted ramp rate in advance of the hour in which the outage commences, or

- Submit derate requests electronically to reflect the capability of the generation facility or electricity storage facility as it ramps down.

Normal loading delays during a generation facility or electricity storage facility start-up are not considered a derating if the generation facility or electricity storage facility is able to ramp towards full load without significant holds. Where a generation facility or electricity storage facility must hold at a specific load for greater than 30 minutes during start-up, this should be considered a derating. The IESO will assess planned deratings required to support a generation facility or electricity storage facility ramp down or start-up on a reasonable effort basis.

If fossil generation facilities having known start-up delays are scheduled by pre-dispatch within a timeframe that does not accommodate the start-up delay, market participants are required to cancel their offers for the hours in which their units are unavailable. Within the restricted and mandatory windows, the IESO Control Room shall allow these offers to be removed.

A generation facility or electricity storage facility whose outage or derating results in a change of the lesser of 2% of rated output or 10 MW, is not required to revise their offers if the derating/outage is expected to last less than two hours. Where their offer had been altered to reflect the capability of their resource, a quantity change or new offer will be allowed by the IESO. This change should reflect the capability of the resource in the pre-dispatch schedule. Changes to offers in the mandatory and restricted window will not affect the current hour.

Market participants are required to use the DRATE or MUSTRUN Constraint Code when submitting outage requests, Table 4-1 provides an example:

Table 4-1: Example Codes When Submitting Planned Derate Requests

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| Planned | - DRATE | - Maintenance |

### Tests

Generation facilities and electricity storage facilities may request approval for an Opportunity outage to conduct tests during a planned or forced outage. In order for the outage requests and tests to not have conflicting time spans in the outage management system, the following procedure should be followed:

- Revise the end time of the original outage request to coincide with the start of the first test.

- Ensure the first test request has a start time that corresponds to the end time of the outage in the revised outage request.

- Create a second outage request to accommodate all the outage time required in the original outage request and has a start time corresponding to the end time of the first test request. The end time corresponds to the end time of the original outage request, or

- Subsequent pairs of outage/test requests with matching start/end times to cover all the remaining tests as required.

Figure 4-1: Submitting Test Request during Outage

Where testing is extensive and is expected to continue for a minimum of two days, market participants may request that the IESO treat the generation facility or electricity storage facility as a commissioning generation facility or commissioning electricity storage facility (MR Ch. 7, Sec. 2.2A and 2.2D respectively). Requests to be treated as a commissioning generation facility or commissioning electricity storage facility should be made to the IESO through the outage process and to Facility Registration. Requests of this nature should be made with a minimum of six business days’ notice. See Section 4.1.3 for reporting details.

For tests of hydroelectric generation facilities within an aggregate, market participants must submit a test profile as part of the outage request. The aggregate will be offered to reflect the aggregate output during testing. The aggregate total generation will be maintained at the offer/dispatch level as the test generation facility loads or unloads.

Market participants having aggregate units with one of the units being tested would offer, ensuring that the associated price is appropriate to be scheduled, the maximum achievable output for the aggregate, excluding the testing unit and compensate for testing by adjusting units within the aggregate. Non-aggregated generation facilities and non-aggregated electricity storage facilities are required to offer the full capability of the facility and use outage requests to derate the facility to the appropriate test level (MR Ch. 5, Sec. 6.6.7).

Often generation facility and electricity storage facility tests are conducted where the test can be suspended and the generation facility or electricity storage facility is then capable of re-loading. These tests are treated differently than generation facility or electricity storage facility deratings in that no outage for a derating is required, however market participants are required to submit an outage request in accordance with the submission deadlines outlined in Section 2.7 indicating the planned test quantities as described in the example below.

For any hour in which a market participant’s generation facility or electricity storage facility is expected to undergo a test, market participants must submit an economical offer for the generation/injection that equals the expected hourly average energy delivery of that unit.

Example:

| If expected generation is… | Then the offer submitted for the hour will be… |
| --- | --- |
| 250 MW for 20 minutes, 175 MW for 10 minutes, and 135 MW for 30 minutes | = 180 MW at an offer price that would ensure the unit is scheduled to deliver 180 MW = 180 MW at an offer price that would ensure the unit is scheduled to deliver 180 MW |

However, since the unit is testing, it would not move to the dispatch target, and the IESO operator may have to intervene to adjust for the behaviour of the testing unit.

Electricity storage facilities wishing to undergo capability testing must submit an outage request outlining the test plan with respect to injection and withdrawal operations. The IESO shall review and coordinate real-time testing requirements including appropriate dispatch data submissions for the injection and withdrawal operation during testing.

Where the test is instantly recallable, generation facilities and electricity storage facilities are allowed to participate in the operating reserve market. This is acceptable as long as the market participant offers the energy as outlined above (and below) and if the market participant ensures that the operating reserve quantity offered each hour meets the following criteria:

(maximum energy expected to be provided during the hour) + (operating reserve quantity offered during the hour) = (maximum amount that the unit can provide that hour)

(maximum energy expected to be provided during the hour) + (operating reserve quantity offered during the hour) = (maximum amount that the unit can provide that hour)

Using the example above:

| If… | The offer submitted for the hour will be… |
| --- | --- |
| Maximum generation per hour is 450 MW |  |

This energy offer would be scheduled if operating reserve is activated or if there are a shortage of resources that required the energy (at which time, the market participant would be expected to abandon the test to meet their operating reserve dispatch).

Generation facilities and electricity storage facilities whose test outages are immediately recallable and participate in the operating reserve market are not expected to submit for compensation costs. Rather, it is expected that offers for energy and operating reserve will reflect any compensation for interrupting the test.

For tests of aggregate generation facilities and electricity storage facilities with immediate recall, market participants must provide a test profile via an information request to the IESO. Market participants must offer the aggregate as per the energy they desire to run but would adjust loading of units within the aggregate to obtain the required test levels. Market participants must request approval to synchronize and desynchronize the test unit, but may change the test unit MW as desired while maintaining the aggregate MW as offered.

Market participants are required to use the Testing Purpose Code when submitting outage requests, Table 4-2 provides an example:

Table 4-2: Example Codes When Submitting Planned Testing Requests

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - IS | - Testing |

### Commissioning Facilities

A commissioning generation facility or a commissioning electricity storage facility shall be treated as, respectively, a self-scheduling generation facility or a self-scheduling electricity storage facility for the purposes of outage coordination and shall follow the normal outage scheduling process (MR Ch. 7, Sec. 2.2A and 2.2D). The commissioning generation facility or commissioning electricity storage facility shall provide a detailed test plan including the following information, but not limited to:

- The expected time of synchronizing to or de-synchronizing from the IESO-controlled grid,

- Energy and reactive output levels,

- The timing of and ramp rates associated with changes in energy and reactive output levels,

- Run-back or trip tests for the commissioning generation facility or commissioning electricity storage facility, and

- Excitation and Power System Stabilizer (PSS) tests.

The IESO will attempt to provide scheduling flexibility for commissioning generation facilities and commissioning electricity storage facilities in the same manner as those generation facilities or electricity storage facilities performing routine testing as per Section 4.1.2. Market participants, whose generation units or electricity storage units with planned outages are returning to service from long-term outages, or are commissioning generation units or commissioning electricity storage units, , shall provide the IESO with a loading profile before synchronization.

The treatment of self-scheduling generation facilities and self-scheduling electricity storage facilities in the IESO’s security and adequacy assessments depends on the type of commissioning being performed as follows:

- New generation facilities and electricity storage facilities, or those returning from long-term outages (mothballing) that are registered as self-scheduling generation facilities or self-scheduling electricity storage facilities, will be treated as unavailable for the purpose of calculating available capacity in the IESO’s adequacy assessments.

  - A planned outage request should be submitted by market participants that define first synchronization and the expected date of commercial operation.

  - Market participants, who are not variable generation facilities, should submit, and keep up to date, the expected commissioning schedule (either via an outage request or other format as specified by the IESO) for the duration of the commissioning period.

  - Market participants, who are variable generation facilities, must submit, and keep up to date the expected commissioning schedule via an outage request for the duration of the commissioning period.

  - Commissioning generation facilities or commissioning electricity storage facilities that are not variable generation facilities should manage all commissioning activities, until commercial operation is declared, with the use of dispatch data as a self-scheduling generation facility or self-scheduling electricity storage facility. Dispatch data should reflect the most recent update to the commissioning schedule.

  - Commissioning generation facilities, that are variable generation facilities, shall offer a forecast output as provided by the IESO.

- Generation facilities that are registered as self-scheduling generation facilities or self-scheduling electricity storage facilities for the purpose of testing new or modified equipment associated with the generation facility or electricity storage facility will be treated as available for the purposes of calculating available capacity in the IESO’s adequacy assessments. In addition,

  - A planned outage request should be submitted by market participants that define the commissioning period.

  - While commissioning, market participants, who are not variable generation facilities, must manage their loading by the use of dispatch data as a self-scheduling generation facility or self-scheduling electricity storage facility. Market participants, who are variable generation facilities, must manage their loading via outage requests and offer a forecast output, as provided by the IESO.

  - Outage requests are to be submitted for each stage of the commissioning period that reflects expected output.

For generation facilities and electricity storage facilities beginning commissioning, the IESO requires at least three months advance notice of the expected synchronization date (MR Ch. 7, Sec. 2.2A.5 and 2.2D.5). This date may be revised by market participants as required.

For the purpose of submitting dispatch data, the commissioning generation facility or commissioning electricity storage facility shall apply to register as a self-scheduling generation facility or self-scheduling electricity storage facility and comply with applicable market rules, in order to submit the necessary dispatch data for testing. Requests to be registered as a self-scheduling generation facility or self-scheduling electricity storage facility should be made to the IESO within a minimum of six business days’ notice (MR Ch. 7, Sec. 2.2A and 2.2D). Any such registration for the purposes of commissioning tests shall expire on the completion of these tests, at which time registration as a generation facility or electricity storage facility is required to participate in the real-time markets.

Where the generation facility or electricity storage facility undergoing commissioning testing, forms part of an aggregate, the whole aggregate will be treated as self-scheduling generation facility. The IESO may not approve these requests where the loss of operating reserve from the aggregate causes a reliability concern (MR Ch. 7, Sec. 2.3.2).

In the event that the commissioning generation facility or commissioning electricity storage facility intends to increase its output above its self-schedule dispatch data for any reason, the offers should be updated outside the mandatory window. If the commissioning generation facility or commissioning electricity storage facility is unable to achieve the self-schedule offer for any reason, the offers should be updated as soon as possible. An outage request should also be submitted to reflect the reduced capability from the self-scheduled quantity.

Market participants are required to use the Commissioning Purpose Code when submitting outage requests, Table 4-3 provides an example:

Table 4-3: Example Codes for Commissioning Generation Facilities and Commissioning Electricity Storage Facilities

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - IS | - Commissioning |

### Segregated Mode of Operation

Outage requests to operate generation facilities in segregated mode of operation (SMO) must be submitted by the 1-Day Advance Approval deadline, unless otherwise agreed to by the IESO. Along with submitting an outage request, market participants are also required to notify the IESO by telephone of the request being submitted.

The IESO must approve them, by telephone or the outage management system, no later than 10:00 EST, one business day prior to the SMO start date to ensure inclusion in first run of Day-Ahead Commitment Process (DACP).

DACP-related processes for generation facilities operating in SMO are detailed in Market Manual 9.2: Submitting Operational and Market Data for the DACP.

Market participants may submit SMO requests as opportunity outages, two hours prior to the start of the outage. The IESO will approve or reject the outage requests no later than 90 minutes prior to the implementation of the segregated mode of operation.

When submitting a request for operation in segregated mode, generation facilities must:

- Submit an outage request for their units for the duration of the segregated mode.

- Submit a second outage request for the time required to ramp down the units to zero (to be submitted within the hour prior to the start of the first dispatch hour to which the segregated request pertains).

- Maintain the offers for their generation facilities for each dispatch hour in which these facilities will or are intended to operate in segregated mode of operation.

- Notify the IESO by phone that the Request for Segregation was submitted (MR App. 7.7, Sec. 1.3.5).

Where a Request for Segregation will require transmission system elements to be reconfigured or removed from service, the IESO will notify the transmitter and enter an outage request in the outage management system to reflect this reconfiguration for the duration required to support the Request for Segregation.

When units are returning from segregated mode of operation, generation facilities must ensure:

- The outage for their units ends at the same time the units are to be reconnected to the IESO-controlled grid.

- Valid offers are in the IESO systems for these units, for the hour they will be returning from segregated mode of operation. When submitting their offers, generation facilities must respect the short notice submission criteria as specified in the market rules.

- If necessary, to zero their revenue meter while in segregated mode of operation in order to be removed from the IESO’s settlements process.

- Notify the IESO by phone of the request for de-segregation (MR App. 7, Sec. 1.3.3, and 1.3.4).

Market participants are required to use the Segregated Mode of Operation Purpose Code when submitting outage requests, Table 4-4 provides an example:

Table 4-4: Example Codes When Requesting Planned Segregated Mode of Operation

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - OOS | - Segregated Mode of Operation (SMO) |

### [Intentionally Left Blank]

## Loads

### Dispatchable Loads

Dispatchable loads are required to submit information requests in the event of planned outages or tests that result in demand reduction of 20 MW or more relative to the average weekday demand of the facility. During an outage, loads are expected to consume according to their bid quantity. Upon change of plan, loads are expected to update bid and offer data and notify the IESO.

Any planned or forced outages, restrictions, deratings or changes in configuration of power system auxiliaries and transmission facilities operated at 50 kV or higher that form part of, or are, connected to the IESO-controlled grid and which affect the operation of the dispatchable load, must be submitted to the IESO. These outages shall be coordinated and submitted by the owner of the facility required to be on outage. For outages to the transmission element to which the dispatchable load is connected, the transmitter will apply for the outage and coordinate with the customer.

Table 4-5 provides example codes for dispatchable loads when submitting planned outage requests:

Table 4-5: Example Codes for Planned Outages to Dispatchable Loads

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - DERATE | - Repair |

### Connected Wholesale Customers

Wholesale customers are required to notify the IESO in the event of changes that result in reduction of 20 MW or more from the average weekday demand or supply. This requirement applies, for example, to large industrial customers that periodically shut down their plants for maintenance, holidays, etc.

Wholesale customers are required to submit information about the planned shutdown in advance, however, approval from the IESO is not required, the outage is supplied for information purposes only.

Market participants are required to use the codes in Table 4-6 when submitting outage requests:

Table 4-6: Applicable Codes for Wholesale Customers

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Information | - INFO | - Other |

### Distributors and Transmitters

Under the market rules, distributors are required to notify the IESO in the event of changes that result in change greater than 20 MW from the average weekday demand or supply. This requirement applies to distributors with embedded loads or generation that are not registered with the IESO (MR Ch. 5, Sec. 3.4.1, 3.5.2, and 3.7.1).

Distributors and transmitters are also required to notify the IESO in advance of demand control actions. Demand control actions include: demand management, voltage reductions and disconnections.

In the event of plans for demand control actions, market participants are required to submit outage information to the IESO by 10:00 EST each day, for the following day. Any emergency plans subsequent to this deadline must be submitted immediately.

The following information is required:

- Proposed date, time, and duration of the cuts by connection point on the IESO-controlled grid, by hour, and

- Proposed MW reduction of demand by connection point on the IESO-controlled grid, by hour.

The actual decrease in MW reduction of demand achieved through demand control actions must be communicated directly to the IESO Control Room, at the time that the reduction is implemented.

Table 4-7 provides example codes for distributors and transmitters when submitting planned outage requests:

Table 4-7: Example Codes for Distributors and Transmitters

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - OOS | - Switching |

### Non-Performance Event Management for Hourly Demand Response Resources

HDR Resources with a Capacity Obligation Acquired through the Capacity Auction

Capacity market participants with an hourly demand response resource that has a capacity obligation is required to maintain records of all reductions to demand response capacity of 5 MW or greater during an obligation period.  The IESO may request the records for a period of 1 year from the end of the associated commitment period. If requested, these records must be provided to the IESO by email by the deadline defined by the IESO. The records must contain the following details:

- Description of Event

- Resource name

- Trade Date

- Hours of reduced capacity

- Registered capacity of the HDR resource

- Amount of reduction (MW) to demand response capacity

- Action taken to manage energy bid

For any quantity, capacity market participants whose HDR resources received an activation report with an activation notice on the dispatch day are required to notify the IESO Control Room by telephone as soon as practical if they are unable to provide their activation amount.

Capacity market participants are required to update bids for HDR resources for any reduction to demand response capacity occurring on the pre-dispatch day or dispatch day to reflect the reduced demand response capacity.

Capacity market participants with an hourly demand response resource who wish to submit a contributor outage should do so in accordance with the procedures outlined in Market Manual 12: Capacity Auctions.

## All Market Participants

As per market rules and the operating agreements between transmitters and the IESO, IESO’s outage assessments will not include assessments of impacts to the reliability of individual customer connections. Assessing the reliability of individual customer connections is the role of the transmitter who is required to:

- Coordinate outages impacting customer connections, and

- Recommend changes to transmission configuration and or recall or cancel outages to secure the supply to customer connections during a high-risk operating state or conservative operating state.

### Monitoring and Control Equipment

Market participants are required to report planned and forced outages to monitoring and control equipment, data concentrating facilities that aggregate monitoring and control information from more than one facility.

For forced outages, market participants are required to respond and restore these facilities to a fully operational state within the time frames specified by Chapter 4, Section 7.7 of the market rules. Based on the impact of the equipment’s unavailability on the reliability and/or operability of the IESO-controlled grid, the IESO may notify market participants to respond within a longer or shorter period that those specified in Sections 7.7.2 and 7.7.3 of the market rules, provided that, where the time to respond and restore is less than 24 hours, the market participant will use commercially reasonable efforts to achieve such direction (MR Ch. 4, Sec. 7.7.4).

Table 4-8 provides example codes for market participants when submitting planned outage requests to monitoring and control equipment:

Table 4-8: Example Codes for Planned Outages to Monitoring and Control Equipment

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - OOS | - Other |

### System Tests

Power system tests typically involve abnormal configurations of the power system, extensive coordination during work, or unusual precautions to ensure the reliability and/or operability of the IESO-controlled grid. Tests covered by these requirements include, but are not limited to (MR Ch. 5, Sec. 6.6):

- The deliberate application of short circuits,

- Generation unit, electricity storage unit, and transmission system stability tests,

- Planned actions which cause abnormal voltage, frequency or overloads,

- Planned abnormal station or system setups with inherent risk, and

- Tests of equipment for which there is some real or potential risk of widespread impact on the IESO-controlled grid.

In order to gain approval for the test, market participants arranging the test must submit the following details (MR Ch. 5, Sec. 6.6.2):

- Equipment involved,

- The relevant details of contracts or agreements as they relate to the test activities,

- Preferred and alternative dates and times for the conduct of the test activities,

- Unusual system conditions or setup required,

- Any required changes in setup, power flow, voltage, frequency, etc., that could have an impact on the reliability and/or operability of the IESO-controlled grid,

- Details of special readings, observations, etc., to be recorded by operating personnel, and

- Identity of personnel who are directly involved in the test, their location and the means of communicating with them.

The IESO will approve the outage request if it is determined that the test will not have an adverse effect on the reliability and/or operability of the IESO-controlled grid or on the operation of the IESO-administered markets.

Where required, arrangements shall be made for a Test Coordinator to be appointed. The name and role of the Test Coordinator shall be specified in the outage submission. The duties of the Test Coordinator include:

- Defer, limit, or stop the System Test due to unfavorable system conditions or test results,

- Monitor test conditions in the area involved, and

- Act as a communicator, and other roles as agreed upon in the outage submission.

If the outage submission involves additional outages or safety code procedures, the requestor shall ensure that outage requests are submitted by the appropriate market participant(s).

Examples of requirements that will not be considered power system tests and should be arranged in the normal manner for outages include:

- Routine generation unit and electricity storage unit rejections,

- Routine protection and control maintenance and testing,

- Routine commissioning tests, and

- Work or testing on hydraulic waterways and storage.

Market participants are required to use the Testing Purpose Code when submitting outage requests, Table 4-9 provides an example:

Table 4-9: Example Codes When Submitting Planned System Test Requests

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - IS | - Testing |

### Testing of Ancillary Services

The IESO shall test facilities that intend to, or do, provide ancillary services to the IESO-controlled grid.

Note: During such testing, the IESO may submit outage requests on behalf of market participants. These will only be visible to the IESO and used for informational purposes.

Tests must be successfully completed prior to entering into a contracted ancillary services contract, for a facility providing regulation or black start services, and at least annually thereafter throughout the contract period. Tests shall be arranged and scheduled at a time mutually agreeable to both the ancillary service provider and the IESO in accordance with the outage scheduling processes outlined in this market manual.

For contracted providers of the Reactive Support and Voltage Control Service the IESO may require tests in accordance with MR Ch. 5, Sec. 4.9.

Performance standards and testing procedures are prescribed in the “IESO – Ancillary Service Provider (ASP) Agreements for Procurement of Certified Black Start Facilities”. Schedule 2 of this Agreement stipulates the required black start performance standards, with Schedule 3 articulating the required testing procedures.

The performance standards for contracted reactive support and voltage control are stipulated in MR Ch. 4, App 4.2.

### Testing Operating Reserve Providers

The IESO may conduct unannounced tests of any market participant’s facility registered to provide operating reserve and currently scheduled to provide operating reserve.

Note: 	During such testing, the IESO may submit outage requests on behalf of market participants. These will only be visible to the IESO and used for informational purposes.

The IESO will assess market participants’ compliance with the operating reserve dispatch instruction according to the respective operating reserve offer submission data. For the purposes of this manual, a failure to meet an operating reserve target during an operating reserve activation (ORA) will also be deemed as a test failure.

If dispatchable load facilities providing operating reserve identify special testing requirements, the IESO will coordinate testing within the first week of the market participant’s acceptance in the market as an operating reserve provider, or as soon as possible. Subsequent testing will occur on a periodic basis.

Tests shall be arranged in accordance with MR Ch. 5, Sec. 4.9 and 4.10.

Reserve testing is the responsibility of the IESO and is conducted by the control room operators (CROs). The CROs will implement unannounced tests taking into account any facilities with poor past performance that require additional testing.

If reserve testing is implemented on a resource that is part of an aggregate, compliance will be assessed on the output of the aggregate.

Note:	If there is non-compliance to actual reserve activations, the following approach will be used with respect to removing offers.

Table 4-10: Implementing and Assessing Reserve Tests

| If a market participant… | The IESO will… |
| --- | --- |
| Fails an initial reserve test or an ORA, (i.e., fails to meet dispatch target within prescribed time [10 or 30 minutes]) | 1. (At IESO discretion) direct the market participant to remove its reserve offers on the resource for the remainder of that day and the next day. 2. Allow these changes within the two-hour mandatory window. 3. Retest the unit, normally within a week after it submits reserve offers again. |
| Fails their first retest of the reserve test or an ORA, (i.e., fails to meet dispatch target within prescribed time [10 or 30 minutes]) | 1. Direct the market participant to remove its reserve offers on the resource for one week. 2. Allow these changes within the two-hour mandatory window. 3. Retest the unit, normally within a week after it submits reserve offers again. |
| Fails their second retest of the reserve test or an ORA, (i.e., fails to meet dispatch target within prescribed time [10 or 30 minutes]) | 1. Direct the market participant to remove its reserve offers on the resource indefinitely. 2. Allow these changes within the two-hour mandatory window. 3. Initiate follow-up with the involved market participant. As a result of this follow-up, a decision will be made as to whether the facility should be removed from the reserve market, and the circumstances for allowing the return to the reserve market. |
| - Fails a reserve test because of an unforeseen forced outage or equipment limitation, and - Is NOT a dispatchable load | Request the market participant to submit an outage to derate or force the equipment out-of-service. |
| - Fails a reserve test because of an unforeseen forced outage or equipment limitation, and - Is a dispatchable load | 1. Request the market participant to change its energy bid to reflect the derate or force the equipment out-of-service. 2. Request the dispatchable load to remove its reserve offers, as the DSO cannot handle derates on dispatchable loads. 3. (Once the forced outage condition has been repaired) allow the market participant to resubmit its reserve offers within the two-hour mandatory window. |

### Hold-offs

Hold-offs are restrictions in the use of transmission lines to facilitate maintenance activities. Automatic reclosure is blocked and manual reclosure is restricted until contact is made with the hold-off party. Single and multiple element hold-offs may be granted Auto AA or FAA.

Market participants are required to use the HOLDOFF Constraint Code when submitting outage requests, Table 4-11 provides an example:

Table 4-11: Example Codes When Submitting Planned Hold-off Requests

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - HOLDOFF | - Other |

### New and Replacement Facilities

Market participants are required to report an outage prior to (MR Ch. 5, Sec. 6.4A):

- Energization of any new facility, or

- Energization of any new facility equipment impactive on the reliability and/or operability of the IESO-controlled grid, or

- Returning into service replacements of any existing facility equipment impactive on the reliability and/or operability of the IESO-controlled grid.

Outage submissions that request the energization of new facilities are not eligible to be requested for the 1-Day Advance Approval process as the impact of introducing a new facility cannot be adequately assessed by the IESO within the timelines of the 1-Day Advance Approval process. In addition, market participants must ensure that all applicable facility registration requirements are complete, prior to the commencement of any such outage.

Table 4-12 provides example codes for market participants when submitting planned outage requests to new and replacement facilities:

Table 4-12: Example Codes When Requesting Planned Outages to New and Replacement Facilities

| Priority Code | Constraint Code | Purpose Code |
| --- | --- | --- |
| - Planned | - MUSTRUN | - Replacement |

– End of Section –

# Replacement Energy to Support Planned Outages

A generation facility or electricity storage facility may notify the IESO that it will arrange replacement energy offers in the form of an import to support a planned outage request or when requesting an extension to an outage. Such a notification does not obligate the generation facility or electricity storage facility to notify the IESO, and if so notified, the IESO to approve or accept any such arrangement. The generation facility or electricity storage facility may withdraw the arrangement for replacement energy offers at any time up to final approval of the outage or up to the final approval of the extension (MR Ch. 5, Sec. 6.3.6).

Where, based on the IESO’s assessment of security and adequacy, the IESO permits the generation facility or electricity storage facility to arrange for replacement energy, the IESO shall determine the minimum MW amount to be arranged as replacement energy (MR Ch. 5, Sec. 6.3.9) based on the following:

- The MW amount of replacement energy shall be no less than the forecast shortfall from the Adequacy Report as determined prior to advance approval being provided or based on more current information in the Adequacy Report,

- Where the shortfall occurs beyond the period of 14 days, the IESO will identify the weeks of shortfall and the maximum amount to be arranged for these weeks based on the day 15 to 34 Adequacy Reports or the Reliability Outlook report prior to advance approval being provided. The generation facility or electricity storage facility should wait until the shortfall is detailed in an Adequacy Report covering the day 0 to 14 period, to identify the specific shortfall hours and amounts to finalize the amount of replacement energy. In any case, replacement energy must be finalized by the generation facility or electricity storage facility no later than 16:00 EST three business days prior to the commencement of the shortfall week(s), and

- Shall not exceed the amount of energy that was agreed to at the time of finalization or 500 MW.

Generation facilities and electricity storage facilities shall convey to the IESO their arrangement for replacement energy by way of the comments field in the outage management system with the following information:

- The intertie where offers will be submitted,

- A unique identifier associated with the e-Tag or a unique e-Tag ID,

- The MW amount to be offered and the duration of the offers (if finalized), and the registered market participant associated with a registered facility that is a boundary entity that shall submit the offers.

Once the IESO has approved or provided additional direction to the generation facility or electricity storage facility specifying the details of the replacement energy import offers, the generation facility or electricity storage facility whose outage was approved is obligated to ensure that these offers are submitted to the IESO for pre-dispatch scheduling. The boundary entity who shall provide replacement energy and that is subject to dispatch instructions received from the IESO, is subject to the failed intertie transaction rules in MR Ch. 7, Sec. 7.5.8A and 7.5.8B and MR Ch. 3, Sec. 6.6.10A to 6.6.10C and the related compliance guidelines.

The IESO may specify the intertie(s) where the replacement energy is to be scheduled in order to meet reliability requirements.

The IESO shall have the right to specify the duration of offers necessary to support the outage request (MR Ch. 5, Sec. 6.3.9). The IESO shall make this determination based on the following:

- Reliability and/or operability impacts on the IESO-controlled grid,

- Forecast capabilities of the interconnections for the duration of the planned outage, and

- Forecast adequacy of neighbouring jurisdictions for the duration of the planned outage.

The duration that replacement energy offers to be submitted to the IESO as part of the pre-dispatch scheduling process shall be:

- No less than the period of the shortfall hours applied to each day of the week(s) of the shortfall, and

- No greater than the total duration of the outage.

For example,

A generation facility or electricity storage facility makes a request for a 300 MW outage over 3 weeks. A shortfall of 100 MW is identified on the Tuesday of the second week between 9 AM to 10 AM. The IESO will notify the market participant of the shortfall and reject the outage.

In order to get approval for the outage request, the market participant must agree to arrange for replacement energy from 9 AM to 10 AM (shortfall hours) for all days of the second week.

However, the market participant may wait until 16:00 EST 3 business days prior to the commencement of the second week of the outage, to finalize the amount and hours of replacement energy. By waiting to finalize the amount, the generation facility or electricity storage facility accepts that the purchase amount may increase from the amount forecast when the outage was given advance approval.

Figure 5-1: Purchase of Replacement Energy – Requirements and Confirmation Timeline

For example,

| If… | Then… |
| --- | --- |
| The following outages create a shortfall of 300 MW: | Unit B and Unit C are offered the opportunity to purchase replacement energy. |
| Unit B chooses to purchase replacement energy | Unit B is required to purchase 200 MW, to clear shortfall caused by forced outage plus its outage. Unit C is required to purchase 100 MW |
| Unit B does not choose to purchase replacement energy | Outage to Unit B is rejected. Shortfall is reduced to 200 MW Unit C is required to purchase 200 MW, to clear shortfall caused by forced outage plus its outage. |

Generation facilities and electricity storage facilities that have arranged replacement energy to support their planned outage are assessed based on priority according to the following:

- When requesting outage approvals during periods of adequacy concerns, generation facilities or electricity storage facilities who have arranged for replacement energy to support a planned outage will have a higher priority than outages that have chosen not to arrange replacement energy (and would otherwise be rejected).

- Where more than one generation facility and/or electricity storage facility has indicated that they wish to arrange for replacement energy and, because of security or adequacy concerns, advance approval cannot be given to all such generation facilities and/or electricity storage facilities, the generation facility or electricity storage facility with an earlier priority date will be given priority.

Figure 5-2: Precedence of Outages Based on Purchase of Replacement Energy

- Where a generation facility or electricity storage facility is identified to be at risk after the replacement energy confirmation timeline but before the advance approval timeline as detailed in Section 2.7, and then confirms the intent to arrange replacement energy before the advance approval timeline, the generation facility or electricity storage facility shall maintain its priority date relative to outages that confirmed replacement energy before the confirmation timeline.

- Where a generation facility has to be revoked or recalled due to energy shortfalls identified after the advance approval or final approval was granted, precedence will be given based on the priority date, regardless of whether the approval is based on arranging replacement energy.

- Where a generation facility or electricity storage facility indicates that they intend to arrange for replacement energy and they do not have priority date precedence over other generation facilities or electricity storage facilities who may elect to arrange for replacement energy they will be notified that they may not be eligible. A final decision regarding eligibility cannot be made until the outage submission deadline. In this situation, it would be prudent for market participants without priority date precedence to wait until the submission deadline before arranging replacement energy.

– End of Section –

# Disputes and Compliance

## Disputes

The IESO or an Applicant may initiate the Dispute Resolution process in accordance with MR Ch. 3, Sec. 2 if either believes the circumstances warrant such action. Specifically, market participants may dispute any decision of the IESO related to outage management, such as rejection of an outage submission, revocation or recall of an approved outage, or denial of outage compensation. However, market participants must continue to follow the direction of the IESO until such time as the Dispute Resolution panel renders a decision. For more information regarding the dispute resolution process, refer to Market Manual 2.1: Dispute Resolution.

## Market Surveillance and Compliance

A Market Surveillance Panel was established pursuant to the “Electricity Act, 1998” for the purpose of identifying inappropriate market conduct, market design flaws and to make sure that the IESO-administered market is fair and efficient. IESO staff may forward potential non-compliant actions of market participants to the IESO Market Assessment and Compliance division. Refer to Market Manual 2.6: Treatment of Compliance Issues and Market Manual 2.7: Treatment of Market Surveillance Issues for more information regarding the dispute resolution process.

– End of Section –

# Appendix A: Forms

The following form is used in connection with the outage management process. This form is available to market participants on the IESO website:

| Form Name | Form Number |
| --- | --- |
| Request for Outage Compensation | IMO_FORM_1350 |

– End of Section –

# Appendix B: Outage Reporting Requirements

Outages must be coordinated with the IESO (and reported to the IESO) when any of the conditions in the following table are met:

Table B-1: Outage Reporting Requirements

| Facility Group | Elements of the Facility Group for which Outages must be Reported |
| --- | --- |
| Transmission facilities operated at voltages ≥ 100 kV | All |
| Transmission facilities operated at voltages < 100 kV | - Removal of step-down transformers with a low side voltage< 100kV - Involve the unloading of step-down transformers or their individual windings - Require paralleling or separation of buses via operation of bus tie breaker - Result in a load transfer ≥ 20 MW between step-down transformer stations - Adversely affect a generation facility, dispatchable load or electricity storage facility |
| Transmission or Distribution Reactive resources | - 15 MVAR or greater in areas electronically south of Essa TS in Barrie - 10 MVAR or greater in areas electronically north of Essa TS in Barrie - Synchronous Condensers and Static VAR Compensators (SVC’s) |
| Power system auxiliaries | Control Systems designed to dynamically respond to system conditions such as: - Power System stabilizers (PSSs) - Automatic voltage regulation (AVR) |
|  | Operating aids such as: - Circuit auto-reclosure schemes - Voltage reduction facilities - Under-frequency load shedding (ULFS) facilities |
|  | Primary or backup protection systems designed to detect and isolate failed or faulted elements |
|  | Breaker failure Protection |
|  | Breaker Trip Coil Test |
|  | Special Protection Systems (SPS) that detect identified system conditions and take corrective actions such as: - Combined generation facility, or electricity storage facility, and load rejection schemes - Reactor tripping schemes |
|  | Communication facilities such as: - SCADA - RTU’s, ICCP links or telemetry facilities for display or quantities - Market participant dispatch tools and facilities |
|  | Switchyard auxiliaries such as: - AC and DC station services - Supervisory control facilities or Control Room bench-boards - Multi Breaker air supply systems including compressor plants and cable cooling systems |
| Non-registered facilities or embedded facilities | Result in a change of more than 20 MW in demand or supply in an hour from what is typical for that hour (i.e. large industrial customers that periodically shut down plants for maintenance or holidays) |
| Dispatchable load facilities/ Wholesale customers | Result in changes of more than 20 MW in demand or supply in an hour from what is typical for that hour. |
| Distributors and Transmitters | Result in changes of more than 20 MW in demand or supply in an hour from what is typical for that hour. Demand control actions, including demand management, voltage reductions and disconnections. |
| Generation Facilities or electricity storage facilities | All generation units or electricity storage units |
|  | Segregated Mode of Operation (SMO) |
|  | Available but not operating |
|  | Deratings: - Derating equal to the greater 2% of rated output or 10 MW - Holds at a specific load for >30 minutes during start-up |
|  | Affects the maximum output or minimum load of a generation unit or electricity storage unit |
|  | A component failure, operational limit or other circumstance that will cause the unit to trip |
|  | Plant auxiliaries that affect more than a single generation unit or electricity storage unit, or aggregate of generation units or electricity storage units where the loss of an additional element results in multiple unit/aggregate shutdowns within 48 hours such as: - Service air or instrument air - Boiler feed pumps - Station Service |
|  | Affects the availability to provide ancillary services such as: - Automatic Generation Control (AGC) - Voltage support - Black start service |
| Testing | All tests described in Section 4.3.2: System Tests |
|  | Testing of generation unit or electricity storage units, including: - In-service or commissioning tests - Testing of derated units at levels above the derated levels - Testing of units currently on outage - Tests of facilities providing ancillary services |
| All Equipment | Hold-off |
|  | Energization: - Energization of any new facility, or - Energization of any new facility equipment impactive on the reliability and/or operability of the IESO-controlled grid, or - Returning into service replacements of any existing facility equipment impactive on the reliability and/or operability of the IESO-controlled grid. |

– End of Section –

# Appendix C: Equipment Classes and Applicable Constraint Codes

Table C-1: Applicable Constraint Code per Equipment Class

| Equipment Class | Constraint Code |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | OOS | IS | DRATE | MUSTRUN | HOLDOFF | AVR/PSS OOS | ASP OOS | PROT OOS | BF PROT OOS | BTCT | INFO | ABNO |
| Line | x | x |  |  | x |  |  | x |  |  | x |  |
| Line Section | x | x |  |  | x |  |  | x |  |  | x |  |
| Breaker | x | x |  |  |  |  |  |  | x | x | x |  |
| Disconnect Switch | x | x |  |  |  |  |  |  |  |  | x |  |
| Bus | x | x |  |  |  |  |  | x |  |  | x |  |
| Transformer | x | x |  |  |  |  |  | x |  |  | x |  |
| Reactor | x | x | x |  |  |  |  | x |  |  | x |  |
| Capacitor | x | x | x |  |  |  |  | x |  |  | x |  |
| SVC | x | x | x | x |  |  |  | x |  |  | x |  |
| Converter | x | x | x | x |  |  |  | x |  |  | x |  |
| Filter | x | x | x |  |  |  |  | x |  |  | x |  |
| Phase Shifter | x | x |  |  |  |  |  | x |  |  | x |  |
| Voltage Regulator | x | x |  |  |  |  |  | x |  |  | x |  |
| UFLS Relay | x | x |  |  |  |  |  |  |  |  | x |  |
| Synchronous Condenser | x | x | x | x |  |  |  | x |  |  | x |  |
| Generation facility, Electricity Storage facility | x | x | x | x |  | x | x | x |  |  | x | x |
| Load | x | x | x | x |  |  | x | x |  |  | x |  |
| AC/DC Station Service | x | x |  |  |  |  |  |  |  |  | x |  |
| SPS21 | x | x |  |  |  |  |  |  |  |  | x |  |
| Tone Communication Channels21 | x | x |  |  |  |  |  |  |  |  | x |  |
| RTU/ICCP/HUB Equipment21 | x | x |  |  |  |  |  |  |  |  | x |  |
| Other Communication Equipment21 | x | x |  |  |  |  |  |  |  |  | x |  |
| Other Miscellaneous Equipment21 | x | x |  |  |  |  |  |  |  |  | x |  |

– End of Section –

# Appendix D: Criteria for 1-Day Advance Approval, Auto AA and FAA

Planned outage requests containing only low-impact equipment must be submitted for 1-Day Advance Approval. Outage requests containing eligible equipment, with no conflicting outage requests (See Section 3.2 for outage conflicts) and that satisfy low-impact criteria may be eligible to receive Auto Advance Approval (Auto AA) (i.e. automatically transition to Advance Approved status on submission) and in some cases may also receive Final Approval in Advance (FAA).  The eligibility criteria for 1-Day advance approval, Auto AA and FAA are described in the table below.

Table D-1: Criteria for 1-Day Advance Approval, Auto AA and FAA

| A Outage Type | B Equipment Class | C Constraint Code | D Low-impact Attributes | E Additional Conditions | F 1-Day Advance Approval | H Auto AA | I FAA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Generator outage or Electricity Storage facility outage | Generation facility or Electricity Storage facility | OOS, IS, DRATE, MUST RUN |  | Planned Start and End Date/Time are in the same day or Max Recall ≤ 15 min | Y | N | N |
| Available But Not Operating | Generation facility or Electricity Storage facility | ABNO |  | Priority Code = Information | N | Y | N |
| Automatic Voltage Regulation (AVR) or Power System Stabilizer (PSS) | Generation facility or Electricity Storage facility | AVR/PSS OOS | Only a Loss of Redundancy?” = YES (Answer) |  | Y | Y | Y |
| Ancillary Services | Generation facility, Load or Electricity Storage facility | ASP OOS |  | Planned Start and End Date/Time are in the same day or Max Recall ≤ 15 min | Y | N | N |
| Primary protections | Line, Line Section, Generation facility, Electricity Storage facility, Bus, Transformer, Reactor, Capacitor, SVC, Phase Shifter, Voltage Regulator, Synchronous Condenser, Converter, Filter, Load | PROT OOS | “Only a Loss of Redundancy?” = YES (Answer) “Only a Loss of Redundancy?” = YES (Answer) | Max Recall is ≤ 15 minutes Max Recall is > 15 minutes | Y Y | Y N | Y Y |
| Holdoffs | Line, Line Section | HOLDOFF |  |  | Y | Y | Y |
| Breaker failure protections | Breaker | BF PROT OOS |  |  | Y | N | N |
|  |  |  | - ”Adjacent breakers OOS?” = NO (Answer) - AND “Only a Loss of Redundancy?” = YES (Answer) - ELSE, IF Question: “Only a Loss of Redundancy?” = NO (Answer) - THEN “CTs on both sides of the breaker?” = YES (Answer) | Only one piece of Equipment is on the Outage Request Continuous and ≤ 4 hours in duration No overlapping BF PROT OOS outages at the same station | Y | Y | N |
| Breaker trip coil tests | Breaker | BTCT |  |  | Y | N | N |
| AC/DC station service | AC/DC Station Service | OOS | - “Only a Loss of Redundancy?” = YES (Answer) - “Does the SS supply Cooling to any equipment on the ICG?” = YES (Answer) | Max Recall is ≤ 15 minutes | Y | N | N |
|  |  | OOS | - “Only a Loss of Redundancy?” = YES (Answer) - “Does the SS supply Cooling to any equipment on the ICG?” = NO (Answer) | Max Recall is ≤ 15 minutes | Y | Y | Y |
|  |  | IS |  | Max Recall is ≤ 15 minutes | Y | N | N |
| Tone communication channels | Tone Communication Channels | OOS | - Only a Loss of Redundancy?” = YES (Answer) - “RTU or HUB Affected?” = YES (Answer) | Max Recall is ≤ 15 minutes | Y | N | N |
|  |  | OOS | - Only a Loss of Redundancy?” = YES (Answer) - “RTU or HUB Affected?” = NO (Answer) | Max Recall is ≤ 15 minutes | Y | Y | Y |
|  |  | IS |  | Max Recall is ≤ 15 minutes | Y | N | N |
| Radial lines | Transmission circuit | OOS, IS, DRATE |  | Facility Class = 3 (Low-impact) | Y | Y | N |
| Transmission facilities operated at voltages < 100 kV | Breaker, Bus, Disconnect Switch, Transformer, Load | OOS, IS, DRATE |  | Facility Class = 3 (Low-impact) | Y | Y | N |
| LV reactive devices | Capacitor, Reactor | OOS |  | Facility Class = 3 (Low-impact) | Y | N | N |
| UFLS equipment | UFLS Relay | OOS |  | Facility Class = 3 (Low-impact) UFLS Validation Threshold passes (i.e. Sum UFLS Area Outages < UFLS Area Outage Margin) | Y | Y | Y |
| Special Protection Scheme | SPS | OOS | Only a Loss of Redundancy?” = YES (Answer) | Max Recall is ≤ 15 minutes | Y | N | N |
|  |  | IS |  | Max Recall is ≤ 15 minutes | Y | N | N |
| RTU/ICCP/HUB Equipment | RTU/ICCP/HUB Equipment | OOS | Only a Loss of Redundancy?” = YES (Answer) | Max Recall is ≤ 15 minutes | Y | N | N |
|  |  | IS |  | Max Recall is ≤ 15 minutes | Y | N | N |
| Other Equipment | Other Communication Equipment, Other Miscellaneous Equipment | OOS | Only a Loss of Redundancy?” = YES (Answer) | Max Recall is ≤ 15 minutes | Y | N | Y |
|  |  | IS |  | Max Recall is ≤ 15 minutes | Y | N | N |

– End of Section –

References

| Document ID | Document Title |
| --- | --- |
| MDP_RUL_0002 | Market Rules for the Ontario Electricity Market |
| PRO-408 | Market Manual 1.5: Market Registration Procedures |
| MDP_PRO_0017 | Market Manual 2.1: Dispute Resolution |
| IMO_PRO_0019 | Market Manual 2.2: Exemption Application and Assessment |
| MDP_PRO_0022 | Market Manual 2.6: Treatment of Compliance Issues |
| MDP_PRO_0023 | Market Manual 2.7: Treatment of Market Surveillance Issues |
| IMP_PRO_0024 | Market Manual 2.11: Reliability Outlook and Related Information Requirements |
| MDP_PRO_0033 | Market Manual 5.5: Physical Markets Settlement Statements |
| IMP_PRO_0033 | Market Manual 7.2: Near-Term Assessments and Reports |
| IESO_MAN_0077 | Market Manual 9.2: Submitting Operational and Market Data for the DACP |
| MAN-44 | Market Manual 12.0: Capacity Auctions |
| PRO-357 | Market Manual 13.1: Capacity Export Requests |
| N/A | Electricity Act, 1998 |
| IESO_TPL_0020 | IESO – Ancillary Service Provider (ASP) Agreement for Procurement of Certified Black Start Facilities |
| GDE-259 | Outage Coordination and Scheduling System (OCSS) CROW Web Client User Guide |

– End of Document –

Online IESO is an online tool for market participants to submit data to the IESO.

For the purposes of this document, “operability” ensures the flexibility to safely operate the IESO-controlled grid considering, for instance, the risk of unplanned system or generation changes, and variable generation behaviour.

Refer to Section 2.7.5 for submission timelines for outage requests to critical and non-critical equipment with low-impact attributes.

Outage period level date/time refers to the date/times of the individual outage periods on the Details tab, not limited to the overall outage date/times.

While the ‘Must Run At’ and the ‘Derated To’ codes represent different limitations, the downstream software process at the IESO’s end will consider both values to mean the maximum capability for the duration of the outage request.

Market participants are required to input a description of the equipment when using this Constraint Code.

Refer to Section 2.7.5 for submission timelines for outage requests to critical and non-critical equipment with low-impact attributes

Statutory holidays and weekend days that precede a business day are included in that business day (i.e. Saturday, Sunday and Monday equal one business day).

Statutory holidays and weekend days that precede a business day are included in that business day (i.e. Saturday, Sunday and Monday equal one business day).

Capitalized terms in this section are defined in Market Manual 13.1: Capacity Export Requests, Appendix A: Glossary of Capacity Export Terms.

To setup Third Party Viewership in CROW which makes outage requests visible to the applicable transmitter, the Equipment Registration Specialist (ERS) must follow the steps outlined in the Online IESO Guide for all Contract Roles.

The resource is operating to a reduced maximum output due to constraints resulting from transmission element outages. This does not include constraints that limit the resource to 0 MW output.

Refer to the “Outage Management System CROW OCSS Web Client User Guide” for detailed instructions on how to submit an outage request.

The submission of the outage request will fulfill the obligations with respect to the submission of dispatch data as set out in MR, CH. 7, App, 7.7.

Discretion may be applied in determining whether or not to direct a market participant to remove its reserve offers after a failed activation. The following may be taken into consideration:

- System conditions may exist where available operating reserve is particularly limited (e.g., freshet, tight supply conditions). Removal of reserve offers may lead to potential shortfall.

- A resource that failed to meet the reserve target within the required time may have faced legitimate circumstances that led to the failed activation. If these circumstances have been, or are expected to be rectified, then future activation of reserve is expected to be met without failure.

For the purposes of outage replacement energy, week is defined as weekdays (Monday to Friday excluding holidays). Where shortfalls occur on a weekend or holiday, the IESO will identify this requirement to the generation facility or electricity storage facility and the generation facility or electricity storage facility will be required to arrange for replacement energy to cover these shortfalls.

Facilities that form part of or are connected to the IESO-controlled grid and used for the purpose of transmitting or distributing electricity. These facilities may be owned by a transmitter, wholesale customer, distributor or generator.

Where multiple facilities involve logic that require those facilities be operated together (i.e., both a switch and a breaker are arranged in series and the switch cannot be operated without first opening the breaker), it is only necessary to report on one of those facilities.

The following power system auxiliaries are excluded from outage reporting:

- Switchyard auxiliaries that do not affect, or the loss of an additional element that does not affect, the operation of the IESO-controlled grid or the operation or capability of components of the IESO-controlled grid.

- Step-down transformer station low voltage bus protections and low voltage reactive resource protections (capacitors), unless they cause unavailability of the component and/or a reconfiguration of the IESO-controlled grid.

- Feeder protections and feeder breaker auto-reclosures, unless they create a load transfer during system tests, or restrict access to the IESO-administered markets of embedded facilities.

If the facility is not registered with the IESO, this responsibility falls on the market participants (i.e. transmission customers for the facility).

Market participants are required to input a description of the equipment for this equipment class, in the outage management system.