## Accessibility Disclaimer Public
This is a locked, fillable form and not all of the content in this document may be captured by a screen-reading device. If you require additional assistance to complete and submit this form, please contact hydrogeninnovationfund@ieso.ca.

## Project Proposal Part B Cover
Project Proposal Part B Cover
Applicant:
Project Title:
| Part A: Document Checklist | Not Complete
| Part B: Budget Summary | Not Complete
| Part C: Milestone Summary | Not Complete
Part A: Document Checklist
Document ID | Worksheet Title | Description | Checklist (drop down selection)
1 | 1. Process Flow | The Process Flow is a process document that aims to provide structure and capture relationships between the project activities, project output, short term, intermediate and ultimate outcomes of the pilot project. | Not Complete
2 | 2. Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, applicant and IESO towards the pilot project. | Not Complete
3 | 3. Workplan | The workplan is a Gantt chart that provides a description of specific activities that will be taking place during the course of the project timeline. | Not Complete
4 | 4. Measuring Results | "Measuring Results" aims to capture the performance indicators of each activity/deliverable, its associated target results and the timeframe of the results. This is also reflected in Section 4A of the written proposal. | Not Complete
5 | 5. Project Risk Profile | The project risk profile is a document to capture all the associated risks of the project that may impact the project timeline,scope or budget. The applicant is encouraged to be as detailed as possible in completing this document and provide risk mitigation strategies for the risks identified. | Not Complete
6 | 6. Quantifiable Outcomes | This document captures all the quantifiable outcomes with associated confidence intervals of the outcome upon successful completion of the project. | Not Complete
Part B: Budget Summary
Row ID | Organization Structure (drop down selection) | Company Name | Industry (drop down selection) | Applicant / Project Partner (drop down selection) | In-Kind / Cash Contribution (drop down selection) | Status (drop down selection) | Amount (Numeric Value)
1
2
3
4
|  | Total |  |  |  |  | 0
Part C: Milestone Summary
Milestone ID | Milestone Completion Month (Numeric Value) | Brief Milestone Description | IESO Contribution Amount (Numeric Value) | Milestone Amount (Numeric Value)
1
2
3
4
5
|  | Total | 0 | 0

## 1. Process Flow
1. Process Flow
Activities
Ultimate Outcomes
Outputs
Intermediate Outcomes

## 2. Budget
2. Detailed Project Budget
Project Name:
Organization Name:
Summary | Expected Submission Date (Months from project start date) | IESO Contribution | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 |  | 0 | 0 | 0
Milestone 2 |  | 0 | 0 | 0
Milestone 3 |  | 0 | 0 | 0
Milestone 4 |  | 0 | 0 | 0
Milestone 5 |  | 0 | 0 | 0
Total |  | 0 | 0 | 0
Click red triangles on cells for important notes that will help you accurately complete this template.
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Total Contribution (All Funders)
1.1. | 1 |  | 1 | [9 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
1.. | 1 | [11 empty] | 0 | [8 empty] | 0
Milestone 1 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Total Contribution (All Funders)
2.1.1 | 2 |  | 1 |  | 1 | [7 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
2.. | 2 | [11 empty] | 0 | [8 empty] | 0
Milestone 2 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Total Contribution (All Funders)
3.1.1 | 3 |  | 1 |  | 1 | [7 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
3.. | 3 | [11 empty] | 0 | [8 empty] | 0
Milestone 3 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Total Contribution (All Funders)
4.1.1 | 4 |  | 1 |  | 1 | [7 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
4.. | 4 | [11 empty] | 0 | [8 empty] | 0
Milestone 4 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Total Contribution (All Funders)
5.1.1 | 5 |  | 1 |  | 1 | [7 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
5.. | 5 | [11 empty] | 0 | [8 empty] | 0
Milestone 5 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLEASE NOTE:
1.) Please refer to spreadsheet titled "2. Budget Example" for example content to demonstrate format.
2.) The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column.
3.) Unless specifically directed otherwise, do not include IESO services (such as M&V plan review) as an in-kind contribution.
4.) Please refer to the final page of the Proposal Guideline available on IESO Hydrogen Innovation Fund webpage for more information on eligible expenses.
5.) Final project milestone value must represent a minimum of 10% of Fund grant.
6.) Eligible labour costs are capped at a maximum $800/day (7.5 hours)
7.) In-kind and cash contributions consist of auditable, substantiated cash and non-cash contributions to the project that contribute substantially to the completion of the project.
8.) Add/Remove Milestones as required
Note on C14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on E14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 3. Work Plan
3. Work Plan
Project Name:
Organization Name:
Project Month # (Maximum project length is 36 months)
Milestone | Task Area | Activity / Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
E.g., Milestone 1 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 1 to Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 4 to Project Month # (Maximum project length is 36 months) 7
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 6 to Project Month # (Maximum project length is 36 months) 10
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3 to Project Month # (Maximum project length is 36 months) 4
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 5 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 15
E.g., Milestone 2 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 13
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 13 to Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 18
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 15 to Project Month # (Maximum project length is 36 months) 21
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 3 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 19
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 16 to Project Month # (Maximum project length is 36 months) 23
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 23 to Project Month # (Maximum project length is 36 months) 25
E.g., Milestone 3 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 26
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 24
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 24 to Project Month # (Maximum project length is 36 months) 27
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 28
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 29
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 33
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 33 to Project Month # (Maximum project length is 36 months) 36

## 4. Measuring Results
4. Measuring Results
Project Name:
Organization Name:
Click red triangles on cells for important notes that will help you accurately complete this template.
Ultimate Outcomes | Ultimate Objective | Intermediate Objective | Activity/Deliverable | Performance Indicator | Method of Measurement | Target Results | Target Completion Date/Month
Note on B6: This should match worksheet 6. Quantifiable Outcomes as described in this proposal template.
Note on E6: Deliverables are tangible products that are created as the result of an activity. Some activities may not result in a deliverable but are nevertheless important (e.g., participant recruitment)
Note on F6: Measuring results requires a performance indicator to be established for EACH project activity/deliverable as well as plan for how and when it will be measured.
Note on G6: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on H6: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on I6: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.

## 5. Project Risk Profile
5. Project Risk Profile
Risk ID | Milestone Impacted | Project Task | Project Impact (Scope, Budget,Timeline) | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Classification (Calculated - DO NOT ENTER) | Risk Mitigation Strategy
1
2
3
4

## 6. Quantifiable Outcomes
6. Quantifiable Outcomes
95% Confidence Interval
| Metrics | Section Referenced in Written Proposal | Lower Bound | Upper Bound | Expected Result | Units | Qualitatitive Description (if applicable)
Note: Add/Delete Metrics as required
Please note the difference between project outcome and objectives. Successful completion of project objectives advances the success of project outcomes. This spreadsheet aims to capture all the quantifiable outcomes upon successful completion of the pilot project, ranging from energy savings, economic stimulus to reliability improvement.

## Options (hidden)
Severity | Almost Certain | Likely | Possible | Unlikely | Rare
Critical | 1 | 1 | 1 | 2 | 3
Significant | 1 | 1 | 2 | 3 | 4
Moderate | 1 | 2 | 3 | 4 | 5
Minor | 2 | 3 | 4 | 5 | 5
Insignificant | 3 | 4 | 5 | 5 | 5
Scope
Budget
Timeline
Material / Equipment / Hardware
Labour
License Fees
Participant Incentives
3rd Party M&V
Accommodation and food services
Agriculture
Business, building and other support services
Construction
Educational services
Finance, insurance, real estate, rental and leasing
Forestry, fishing, mining, quarrying, oil and gas
Goods-producing sector
Health care and social assistance
Information, culture and recreation
Manufacturing
Other services (except public administration)
Professional, scientific and technical services
Public administration
Services-producing sector
Transportation and warehousing
Utilities
Wholesale and retail trade
Complete
Not Complete
Academia / University
Crown Corporation
Government - Federal Entity
Government - Municipal Entity
Government - Provincial Entity
Local Distribution Company
NGO
Private - For Profit
Private - Not For Profit
Transmission Company
Academia, University Research
Accommodation and Food Services
Administrative and Support, Waste Management and Remediation Services
Agriculture, Forestry, Fishing and Hunting
Arts, Entertainment and Recreation
Construction
Consultants
Educational Services
Electricity System Operator
Energy
Finance and Insurance
Health Care and Social Assistance
Information and Cultural Industries
Manufacturing
Mining, Quarrying, and Oil and Gas Extraction
Public Administration
Real Estate and Rental and Leasing
Research
Retail Trade
Technology
Transportation and Warehousing
Utilities
Wholesale Trade
In Kind
Cash
Applicant
Project Partner
Confirmed
Unconfirmed

## Examples-->
This spreadsheet is left intentionally blank. Examples of each deliverable can be found in subsequent worksheets. Please note that each worksheet example is an independant example.
Good luck!

## Proj. Prop. Pt. B Cover EXAMPLE
Appendix A Cover
Applicant: | ABC Inc.
Project Title: | Hydrogen Demonstration
Part A: Document Checklist | Complete
Part B: Budget Summary | Complete
Part C: Milestone Summary | Complete
Part A: Document Checklist
Document ID | Title | Description | Checklist
1 | Logic Model | The logic model is a process document that aims to provide structure and capture relationships between the project activities, project output, short term, intermediate and ultimate outcomes of the pilot project. | Complete
2 | Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, applicant and IESO towards the pilot project. | Complete
3 | Workplan | The workplan is a Gantt chart that provides a description of specific activities that will be taking place during the course of the project timeline. | Complete
4 | Measuring Results | "Measuring Results" aims to capture the performance indicators of each activity/deliverable, its associated target results and the timeframe of the results. This is also reflected in Section 4A of the written proposal. | Complete
5 | Project Risk Profile | The project risk profile is a document to capture all the associated risks of the project that may impact the project timeline,scope or budget. The applicant is encouraged to be as detailed as possible in completing this document and provide risk mitigation strategies for the risks identified. | Complete
6 | Quantifiable Outcomes | This document captures all the quantifiable outcomes with associated confidence intervals of the outcome upon successful completion of the project. | Complete
Part B: Budget Summary
ID | Organization Structure | Company Name | Industry | Applicant / Project Partner | In-Kind / Cash Contribution | Status | Amount
1 | Private - For Profit | ABC Inc | Manufacturing | Applicant | In Kind | Confirmed | 100000
2 | Private - For Profit | Supplier A | Manufacturing | Applicant | Cash | Confirmed | 80000
3 | Local Distribution Company | Utility ABC | Utilities | Project Partner | In Kind | Confirmed | 95000
4 | Private - For Profit | Private Co. | Consultants | Project Partner | In Kind | Confirmed | 50000
5 | Private - For Profit | Meter Inc. | Research | Project Partner | In Kind | Unconfirmed | 85000
6 | Private - For Profit | Meter Inc. | Research | Project Partner | Cash | Confirmed | 45000
7 | Crown Corporation | IESO | Electricity System Operator | Project Partner | Cash | Unconfirmed | 125000
|  | Total |  |  |  |  | 580000
Part C: Milestone Summary
Milestone ID | Milestone Completion Month Ending | Brief Milestone Description | IESO Contribution Amount | Total Milestone Amount
1 | 5 | Project Design | 22500 | 87000
2 | 8 | Project Implementation | 35000 | 203000
3 | 15 | Analysis | 39500 | 116000
4 | 36 | M&V Results and Reporting | 28000 | 174000
|  | Total | 125000 | 580000

## 1. Process Flow EXAMPLE
1. Process Flow
√√ and
Activities
Outputs
Intermediate Outcomes
A functional turnkey facility that can produce hydrogen and test for grid services
Ultimate Outcomes
Intallation of 10 MW Electrolyzer
Install and commission electrolyser at facility, including all necessary approvals
Develop Test Plans
Identify the grid services that will be tested (OR, energy, capacity, ancillary services such as regulation service, testing of renewable smoothing and demonstrating following a real-time marginal emissions signal). Include relevent evaluation, measurement and verification approaches and data output steams.
Testing
Conduct testing in acoordance with IESO market rules, capturing appropriate data to support tests.
External Comms &
Knowledge Transfer:
Share learnings with broader sector, including targeted audience - e.g. project developers, facility owners, working groups, government /agencies, as appropriate.
Test plans
List of data sources
List of IESO market rules / manuals to be considered
EM&V Plan
Capture testing data, analyse data and present data in a comprehensive way (e.g. Report)
Confirmation of whether the facility was able to perform as planned and in accordance with IESO Market Rules.
Knowledge dissemination to raise awareness of the capabilities of the electrolyzer facility, its pontential contribution to grid services and the broader future hydrogen landscape. Inform future hydrogen project decision-making.
Barriers identified and further explored (where appropriate), and/or removed (where appropriate)
Understanding of performance capabilites, and the potential for this resources to provide grid services, support intermittent generation, respond to marginal emissions signals.
Awareness increases of turnkey solutions in the commercial sector
Evaluation results demonstrate technical capabilities of this new resource.
Additional companies implement similar solutions and contribute towards developing the hydrogen landscape in Ontario and supporting Ontario's electricity grid
Verified performance demonstrating that the technology can provide grid services in accordance to IESO Market Rules.
Verified performance of other services (e.g. supporting renewables, respnding to marginal emissions signals).
Costs, barriers, opportunities associated with implementing this technology are identified, including policy/regulatory.
Broader awareness and understanding of this technology and its pontential role in Ontario.
Understand the challenges and opportunities of installating an electrolyzer
Clear understanding of targeted tests, expected outputs and how performance will be measured

## 2. Budget EXAMPLE
2. Detailed Project Budget (EXAMPLE)
Project Name: | Hydrogen Demonstration
Organization Name: | ABC Inc.
Summary | Expected Submission Date (Months from project start date) | IESO Contribution | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 | 11 | 6370 | 21610 | 27980
Milestone 2 |  | 0 | 0 | 0
Milestone 3 |  | 0 | 0 | 0
Milestone 4 |  | 0 | 0 | 0
Milestone 5 |  | 0 | 0 | 0
Total |  | 6370 | 21610 | 27980
Click red triangles on cells for important notes that will help you accurately complete this template.
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) | Applicant Company (Cash) | Gadget Co. (In-Kind) | Gadget Co. (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
1.1.1 | 1 | Milestone 1: Demonstration Preparation | 1 | Task 1: Develop M&V Plan | 1 | Activity 1: Develop detailed M&V Plan | Month 1 | Labour | Utilities | Applicant Company / LDC | 154 | 18 | 2772 | 0 | 550 | 800 | 820 | 102 | 0 | 500 | 2772
1.1.2 | 1 | Milestone 1: Demonstration Preparation | 1 | Task 1: Develop M&V Plan | 2 | Activity 2: Review detailed M&V Plan with IESO | Month 2 | Labour | Agriculture | Applicant Company | 410 | 2 | 820 | 0 | 140 | 0 | 530 | 150 | 0 | 0 | 820
1.2.1 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 1 | Activity 1: Develop metering plan | Month 2 | Labour | Agriculture | Applicant Company | 288 | 5 | 1440 | 550 | 150 | 0 | 0 | 740 | 0 | 0 | 1440
1.2.2 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 2 | Activity 2: Acquire submeters | Month 2 | Material / Equipment / Hardware | Manufacturing | Meter Co. | 266 | 18 | 4788 | 4000 | 0 | 0 | 788 | 0 | 0 | 0 | 4788
1.2.3 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 3 | Activity 3: Meter installation | Month 3 | Labour | Business, building and other support services | Demonstration Facility | 115 | 15 | 1725 | 0 | 0 | 295 | 230 | 0 | 1200 | 0 | 1725
1.3.1 | 1 | Milestone 1: Demonstration Preparation | 3 | Task 3: Establishing baseline | 1 | Activity 1: Data collection (6 months) | Month 9 | Labour | Business, building and other support services | Demonstration Facility | 32 | 214 | 6848 | 0 | 6000 | 848 | 0 | 0 | 0 | 0 | 6848
1.3.2 | 1 | Milestone 1: Demonstration Preparation | 3 | Task 3: Establishing baseline | 2 | Activity 2: Data analyis and weather normalization | Month 10 | Labour | Agriculture | Applicant Company | 95 | 61 | 5795 | 1400 | 1400 | 0 | 500 | 2495 | 0 | 0 | 5795
1.4.1 | 1 | Milestone 1: Demonstration Preparation | 4 | Task 4: Reporting | 1 | Activity 1: Draft report on baseline establishment | Month 11 | Labour | Agriculture | Applicant Company | 632 | 6 | 3792 | 420 | 0 | 0 | 210 | 3162 | 0 | 0 | 3792
Milestone 1 Summary | [11 empty] | 339 | 27980 | 6370 | 8240 | 1943 | 3078 | 6649 | 1200 | 500 | 27980
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
2.1.1 | 2 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
Milestone 2 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
3.1.1 | 3 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
Milestone 3 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
4.1.1 | 4 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
Milestone 4 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
5.1.1 | 5 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
Milestone 5 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Note on C14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on E14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 3. Work Plan EXAMPLE
3. Project Work Plan (EXAMPLE)
Project Name: | Hydrogen Demonstration
Organization Name: | ABC Inc.
Project Month # (Maximum project length is 36 months)
Milestone | Task Area | Activity/ Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
E.g., Milestone 1 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 1 to Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 4 to Project Month # (Maximum project length is 36 months) 7
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 6 to Project Month # (Maximum project length is 36 months) 10
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3 to Project Month # (Maximum project length is 36 months) 4
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 5 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 15
E.g., Milestone 2 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 13
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 13 to Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 18
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 15 to Project Month # (Maximum project length is 36 months) 21
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 3 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 19
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 16 to Project Month # (Maximum project length is 36 months) 23
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 23 to Project Month # (Maximum project length is 36 months) 25
E.g., Milestone 3 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 26
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 24
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 24 to Project Month # (Maximum project length is 36 months) 27
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 28
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 29
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 33
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 33 to Project Month # (Maximum project length is 36 months) 36

## 4. Measuring Results EXAMPLE
4. Measuring Results (EXAMPLE)
Project Name: | Hydrogen Demonstration
Organization Name: | ABC Inc.
Click red triangles on cells for important notes that will help you accurately complete this template.
Ultimate Outcome | Ultimate Objective | Intermediate Objective | Activity/Deliverable | Performance Indicator | Method of Measurement | Target Results | Target Completion Date/Month
Hydrogen facility (electrolyzer) to participate in the IESO-Administered Markets (IAMs) on an enduring basis with the provision of grid services, for example regulation service, operating reserve (OR), and following a marginal emissions signal. | Demonstrate that the facility is able to provide grid services, for example regulation service and OR in accordance with existing IESO market rules. Demonstrate new capabilities e.g. following a marginal emissions signal. | Run numerous tests for the provision of existing grid services under different circumstances and grid conditions. | Run test case for regulation service, OR and marginal emissions signal and provide data, analysis and report | Tests complete and analysis provided to the IESO | Data collection, analysis and verification | Follow signal on a 4-second basis | 2024-06-01
[6 empty] | Demonstrate dispatchability and ability to hold for 12 intervals | 2024-08-01
[6 empty] | Follow marginal emissions signal on a x-second basis | 2024-10-01
Note on A6: This should match worksheet 6. Quantifiable Outcomes as described in this proposal template.
Note on B6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on C6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on D6: Deliverables are tangible products that are created as the result of an activity. Some activities may not result in a deliverable but are nevertheless important (e.g., participant recruitment)
Note on E6: Measuring results requires a performance indicator to be established for EACH project activity/deliverable as well as plan for how and when it will be measured.
Note on F6: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on G6: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on H6: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.
Note on C7: Each project outcome (e.g. increasing staff enthusiasm for reducing electricity consumption, or replacing all inefficient lighting) may consist of several smaller, more immediate outcomes, for which there may be several tasks or activities. Outcomes are states or conditions of the people or things that are necessary for the project to succeed.

## 5. Project Risk Profile EXAMPLE
5. Project Risk Profile (EXAMPLE)
Risk ID | Milestone Impacted | Project Task | Project Impact (Drop down selection - Scope, Budget,Timeline) | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Classification (Calculated - DO NOT ENTER) | Risk Mitigation Strategy
1 | Milestone 1 | Site Confirmation | Timeline | Non-confirmation of project site prior to project kick-off | Significant | Unlikely | 3 | Engage with demonstration facility early, and ensure that all parties are aligned with the scope of the project to enable a fast reponse on demonstration site confirmation.
2 | Milestone 1 | Equipment Procurement | Timeline | Delays in delivery of equipment | Moderate | Likely | 2 | Factor in the expected lead time and add a buffer to compensate uncertainties in equipment delivery.
3 | Milestone 2 | Equipment Installation | Budget | Failure of equipment post installation | Moderate | Unlikely | 4 | Complete QA testing prior to equipment installation
4 | Milestone 2 | Equipment Installation | Timeline | Failure of equipment post installation | Moderate | Unlikely | 4 | Complete QA testing prior to equipment installation
5 | Milestone 3 | Reporting | Timeline | Inability to report statistically significant results | Critical | Unlikely | 2 | M&V plan will be completed and approved prior to data collection and analysis period.

## 6. Quantifiable Outcome EXAMPLE
6. Quantifiable Outcomes (EXAMPLE)
|  | 95% Confidence Interval | 95% Confidence Interval
Metric | Section and Equations Referenced in Written Project Proposal Part A | Lower Bound | Upper Bound | Expected Result | Unit | Qualitatitive Description (if applicable)
Provision of Operating Reserve | Section 1.7.G Equations (2) - (9) | 8 | 10 | 10 | MW | Performance in accordance with IESO Market Rules for Operating Reserve
5-Min Dispatchability | Section 1.7.G Equations (10) - (15) | 3 | 5 | 3 | min | Ability to respond to a dispatch instruction on a 5-min basis
Marginal Emissions Following | Section 1.7.G Equations (16) - (17) | 3 | 5 | 3 | min | Ability to follow a real time marginal emissions signal
Frequency regulation | Section 1.7.G Equations (18) | <1 | 4 | <1 | second | Ability to provide frequency regulation in accordance with IESO market rules, or fast frequency regulation
Peak Load Reduction | Section 1.7.G Equations (10) - (15) | 2920 | 4380 | 3650 | kWh | N/A
Peak Load Shifting | Section 1.7.G Equations (16) - (17) | 2320 | 3480 | 2900 | kWh | N/A
Reliability Improvement SAIFI | Section 1.7.G Equations (20) | 0.16 | 0.24 | 0.2 | hours | N/A
Reliability Improvement SAIDI | Section 1.7.G Equations (21) | 0.08 | 0.12 | 0.1 | hours | N/A
Jobs Supported | Section 4.B | 36 | 54 | 45 | Jobs | N/A
Jobs Created | Section 4.B | 14 | 22 | 18 | Jobs | N/A
Additional Available Capacity | Section 1.8.1 | 696 | 1044 | 870 | kW | N/A
Policy/Regulatory Change | Section 1.8.4 | N/A | N/A | N/A | N/A | Results from this project will be used to support X policy or Y regulatory decision.
Please note the difference between project outcome and objectives. Successful completion of project objectives advances the success of project outcomes. This spreadsheet aims to capture all the quantifiable outcomes upon successful completion of the pilot project, ranging from energy savings, economic stimulus to reliability improvement.