## Accessibility Disclaimer Public
This is a locked, fillable form and not all of the content in this document may be captured by a screen-reading device. If you require additional assistance to complete and submit this form, please contact gridinnovationfund@ieso.ca.

## Project Proposal Part B Cover
Project Proposal Part B Cover
Applicant:
Project Title:
| Part A: Document Checklist | Not Complete
| Part B: Budget Summary | Not Complete
| Part C: Milestone Summary | Not Complete
Part A: Document Checklist
Document ID | Worksheet Title | Description | Checklist (drop down selection)
1 | 1. Process Flow | The Process Flow is a process document that aims to provide structure and capture relationships between the project activities, project output, short term, intermediate and ultimate outcomes of the pilot project. | Not Complete
2 | 2. Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, applicant and IESO towards the pilot project. | Not Complete
3 | 3. Workplan | The workplan is a Gantt chart that provides a description of specific activities that will be taking place during the course of the project timeline. | Not Complete
4 | 4. Measuring Results | "Measuring Results" aims to capture the performance indicators of each activity/deliverable, its associated target results and the timeframe of the results. | Not Complete
5 | 5. Project Risk Profile | The project risk profile is a document to capture all the associated risks of the project that may impact the project timeline,scope or budget. The applicant is encouraged to be as detailed as possible in completing this document and provide risk mitigation strategies for the risks identified. | Not Complete
6 | 6. Quantifiable Outcomes | This document captures all the quantifiable outcomes with associated confidence intervals of the outcome upon successful completion of the project. | Not Complete
Part B: Budget Summary
Row ID | Organization Structure (drop down selection) | Company Name | Industry (drop down selection) | Applicant / Project Partner (drop down selection) | In-Kind / Cash Contribution (drop down selection) | Status (drop down selection) | Amount
1
2
3
4
5
6
|  | Total |  |  |  |  | 0
Part C: Milestone Summary
Milestone ID | Milestone Completion Month (Numeric Value) | Brief Milestone Description | IESO Contribution Amount (Numeric Value) | Milestone Amount (Numeric Value)
1
2
3
4
5
|  | Total | 0 | 0

## 1. Process Flow
1. Process Flow
Intermediate Outcome
Activites
Output
Short-Term Outcome
Ultimate Outcome

## 2. Budget
2. Detailed Project Budget
Project Name:
Organization Name:
Summary | Expected Submission Date (Months from project start date) | IESO Contribution | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 |  | 0 |  | 0
Milestone 2 |  | 0 | 0 | 0
Milestone 3 |  | 0 | 0 | 0
Milestone 4 |  | 0 | 0 | 0
Milestone 5 |  | 0 | 0 | 0
Total |  | 0 | 0 | 0
Click red triangles on cells for important notes that will help you accurately complete this template. | [16 empty] | Cot
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
1.. | 1 | [11 empty] | 0 | [9 empty] | 0
Milestone 1 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
2.. | 2 | [11 empty] | 0 | [9 empty] | 0
2.. | 2 | [11 empty] | 0 | [9 empty] | 0
Milestone 2 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
.. | [12 empty] | 0 | [9 empty] | 0
Milestone 3 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
4.. | 4 | [11 empty] | 0 | [9 empty] | 0
Milestone 4 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
5.. | 5 | [11 empty] | 0 | [9 empty] | 0
Milestone 5 Summary | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLEASE NOTE:
1. Please refer to spreadsheet titled
2. Budget EXAMPLE" for example content to demonstrate format.
3. All budget line items must be clearly linked to a deliverable outlined in the Milestones (Proposal Template Part A)
4. The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column.
5. Please refer to the final page of the Proposal Guide available on IESO Grid Innovation Fund webpage for more information on eligible expenses.
6. Final project milestone value must represent a minimum of 10% of Fund grant.
7. Eligible labour costs are capped at a maximum $800/day (7.5 hours)
8. In-kind and cash contributions consist of auditable, substantiated cash and non-cash contributions to the project that contribute substantially to the completion of the project.
9. Add/Remove Milestones as required
Note on C14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on E14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Y14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Y25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Y36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Y47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Y58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 3. Work Plan
3. Work Plan
Project Name:
Organization Name:
Project Month # (Maximum project length is 36 months)
Milestone | Task Area | Activity / Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36

## 4. Measuring Results
4. Measuring Results
Project Name:
Organization Name:
Click red triangles on cells for important notes that will help you accurately complete this template.
Ultimate Outcomes | Ultimate Objective | Project/ Intermediate Objective | Immediate Objective | Activity/Deliverable | Performance Indicator | Method of Measurement | Target Results | Target Completion Date/Month
Note: Add/Delete Metrics as required
Note on B6: This should match worksheet 6. Quantifiable Outcomes as described in this proposal template.
Note on F6: Deliverables are tangible products that are created as the result of an activity. Some activities may not result in a deliverable but are nevertheless important (e.g., participant recruitment)
Note on G6: Measuring results requires a performance indicator to be established for EACH project activity/deliverable as well as plan for how and when it will be measured.
Note on H6: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on I6: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on J6: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.

## 5. Project Risk Profile
5. Project Risk Profile
Risk ID | Milestone Impacted | Project Task | Project Impact (Scope, Budget,Timeline) | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Classification (Calculated - DO NOT ENTER) | Risk Mitigation Strategy
Note: Add/Delete Metrics as required

## 6. Quantifiable Outcomes
6. Quantifiable Outcomes
95% Confidence Interval
| Metrics | Section Referenced in Written Proposal | Lower Bound | Upper Bound | Expected Result | Units | Qualitatitive Description (if applicable)
Note: Add/Delete Metrics as required
Please note the difference between project outcome and objectives. Successful completion of project objectives advances the success of project outcomes. For example, the installation of 20 heat pumps at residential homes is a project objective, not a project outcome. If the heat pumps leads to energy and/or cost savings, then the outcome of the project is the energy and cost savings realised from using the heat pumps. This spreadsheet aims to capture all the quantifiable outcomes upon successful completion of the pilot project, ranging from energy and/or cost savings, economic stimulus to reliability improvement.

## Options (hidden)
Severity | Almost Certain | Likely | Possible | Unlikely | Rare
Critical | 1 | 1 | 1 | 2 | 3
Significant | 1 | 1 | 2 | 3 | 4
Moderate | 1 | 2 | 3 | 4 | 5
Minor | 2 | 3 | 4 | 5 | 5
Insignificant | 3 | 4 | 5 | 5 | 5
Scope
Budget
Timeline
Material / Equipment / Hardware
Labour
License Fees
Participant Incentives
3rd Party M&V
Accommodation and food services
Agriculture
Business, building and other support services
Construction
Educational services
Finance, insurance, real estate, rental and leasing
Forestry, fishing, mining, quarrying, oil and gas
Goods-producing sector
Health care and social assistance
Information, culture and recreation
Manufacturing
Other services (except public administration)
Professional, scientific and technical services
Public administration
Services-producing sector
Transportation and warehousing
Utilities
Wholesale and retail trade
Complete
Not Complete
Academia / University
Crown Corporation
Government - Federal Entity
Government - Municipal Entity
Government - Provincial Entity
Local Distribution Company
NGO
Private - For Profit
Private - Not For Profit
Transmission Company
Academia, University Research
Accommodation and Food Services
Administrative and Support, Waste Management and Remediation Services
Agriculture, Forestry, Fishing and Hunting
Arts, Entertainment and Recreation
Construction
Consultants
Educational Services
Electricity System Operator
Energy
Finance and Insurance
Health Care and Social Assistance
Information and Cultural Industries
Manufacturing
Mining, Quarrying, and Oil and Gas Extraction
Public Administration
Real Estate and Rental and Leasing
Research
Retail Trade
Technology
Transportation and Warehousing
Utilities
Wholesale Trade
In Kind
Cash
Applicant
Project Partner
Confirmed
Unconfirmed

## Examples-->
This spreadsheet is left intentionally blank. Examples of each deliverable can be found in subsequent worksheets. Please note that each worksheet example is an independant example.
Good luck!

## Proj. Prop. Pt. B Cover EXAMPLE
Appendix A Cover
Applicant: | Widget Inc.
Project Title: | Widget Demonstration
Part A: Document Checklist | Complete
Part B: Budget Summary | Complete
Part C: Milestone Summary | Complete
Part A: Document Checklist
Document ID | Title | Description | Checklist
1 | Logic Model | The logic model is a process document that aims to provide structure and capture relationships between the project activities, project output, short term, intermediate and ultimate outcomes of the pilot project. | Complete
2 | Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, applicant and IESO towards the pilot project. | Complete
3 | Workplan | The workplan is a Gantt chart that provides a description of specific activities that will be taking place during the course of the project timeline. | Complete
4 | Measuring Results | "Measuring Results" aims to capture the performance indicators of each activity/deliverable, its associated target results and the timeframe of the results. | Complete
5 | Project Risk Profile | The project risk profile is a document to capture all the associated risks of the project that may impact the project timeline,scope or budget. The applicant is encouraged to be as detailed as possible in completing this document and provide risk mitigation strategies for the risks identified. | Complete
6 | Quantifiable Outcomes | This document captures all the quantifiable outcomes with associated confidence intervals of the outcome upon successful completion of the project. | Complete
Part B: Budget Summary
ID | Organization Structure | Company Name | Industry | Applicant / Project Partner | In-Kind / Cash Contribution | Status | Amount
1 | Private - For Profit | Widget Inc. | Manufacturing | Applicant | In Kind | Confirmed | 350000
2 | Private - For Profit | Widget Inc. | Manufacturing | Applicant | Cash | Confirmed | 150000
3 | Local Distribution Company | Utility ABC | Utilities | Project Partner | In Kind | Confirmed | 105000
4 | Private - For Profit | Gadget Co. | Consultants | Project Partner | In Kind | Confirmed | 40500
5 | Private - For Profit | Meter Inc. | Research | Project Partner | In Kind | Unconfirmed | 90000
6 | Private - For Profit | Meter Inc. | Research | Project Partner | Cash | Confirmed | 55000
7 | Crown Corporation | IESO | Electricity System Operator | Project Partner | Cash | Unconfirmed | 202500
|  | Total |  |  |  |  | 993000
Part C: Milestone Summary
Milestone ID | Milestone Completion Month Ending | Brief Milestone Description | IESO Contribution Amount | Total Milestone Amount
1 | 8 | Marketing and Participant Outreach | 35000 | 203000
2 | 15 | Software Development and DERMS integration | 39500 | 116000
3 | 20 | Demonstration and Analysis | 100000 | 500000
4 | 36 | Final Report and Lessons Learned | 28000 | 174000
|  | Total | 202500 | 993000
0

## 1. Process Flow EXAMPLE
1. Process Flow
√√ and
Intermediate Outcomes
Activities
Outputs
Short-Term Outcomes
A functional turnkey mechanism to engage employees to implement an electricity reduction program that can track results
Ultimate Outcomes
Develop Tools:
Develop guidelines and resources
Build web delivery and tracking mechanism
Introduce metering to illustrate electricity use
Organizational and
Operational Structure:
Secure project reps. -executive, IT, and grassroots
Direct support to company reps
Host forums for all participating companies to share and reapply learnings
Motivation/Incentives:
Track & leverage results
Validate Workplace Committee’s action compliance
Stimulate and seed group challenges
Secure real & compel-ling incentives
Celebrate leaders and champions
External Comms &
Knowledge Transfer:
Celebrate leaders
Media relations/PR
Direct promotion to WWF partners
General promotion at business conference
3rd party evaluation of support tools
8 WWF/Company MOUs
Project teams – IT & Workplace Cttee
EM&V plan
Quarterly mtgs with Workplace Committee
3 workshops
Co-specific on-line info hub that reflects all corp. activity registered through project
Energy saving challenges between departments
Giveaways and prizes for actions taken
Awards for top performers
Promotional materials
Profiles
Case study
EM&V report
3rd party evaluation report
Barriers identified and removed, uptake made easy & employees participate
Senior-level buy-in
Committee supports commitment at all levels by working within workplace culture
Landlords aware and involved as needed
Heightened aspirations to pursue corporate targets
Understanding of electricity use increases
Desire to engage with colleagues for reward and recognition
Increased staff enthusiasm for reducing electricity consumption
Innovative ideas for reducing electricity consumption generated
Perceived collective commitment to conserve
Perceived benefits of participation drives results
Awareness increases of turnkey solutions in the commercial sector
Evaluation results demonstrate link between project and savings
Knowledge of opportunity and benefits stimulates desire of commercial sector to engage
Introduction of new technologies and/or settings modified on existing technology
Change in individual behaviour relating to electricity use
Electricity targets established and aligned with co.’s CSR goals
Executive(s) accountable for savings/results
Companies take greater advantage of programs in the marketplace that reward the adoption of electricity savings
Employees sign-up to TGL@Work
Additional companies apply toolkit in their offices
Real reduction in electricity use in 8 pilot companies based on actions taken and estimates of electricity and cost savings
Companies consider energy costs and opportunities as business decisions
Employees proactively choose actions that lead to electricity savings at home and work
Refined turnkey engagement tool is embraced by other companies to save electricity
Understanding of opportunities for electricity savings increases
Workplace Committee empowered as implementation team
Feedback on what works/ what doesn’t
Employee support corporate initiatives to save electricity
8 pilot businesses serve as resources to guide/advise/promote energy saving tools

## 2. Budget EXAMPLE
2. Detailed Project Budget (EXAMPLE)
Project Name: | Widget Demonstration
Organization Name: | Widget Co.
Summary | Expected Submission Date (Months from project start date) | IESO Contribution | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 | 11 | 6370 | 21610 | 27980
Milestone 2 |  | 0 | 0 | 0
Milestone 3 |  | 0 | 0 | 0
Milestone 4 |  | 0 | 0 | 0
Milestone 5 |  | 0 | 0 | 0
Total |  | 6370 | 21610 | 27980
Click red triangles on cells for important notes that will help you accurately complete this template.
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) | Applicant Company (Cash) | Gadget Co. (In-Kind) | Gadget Co. (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
1.1.1 | 1 | Milestone 1: Demonstration Preparation | 1 | Task 1: Develop M&V Plan | 1 | Activity 1: Develop detailed M&V Plan | Month 1 | Labour | Utilities | Applicant Company / LDC | 154 | 18 | 2772 | 0 | 550 | 800 | 820 | 102 | 0 | 500 | 2772
1.1.2 | 1 | Milestone 1: Demonstration Preparation | 1 | Task 1: Develop M&V Plan | 2 | Activity 2: Review detailed M&V Plan with IESO | Month 2 | Labour | Agriculture | Applicant Company | 410 | 2 | 820 | 0 | 140 | 0 | 530 | 150 | 0 | 0 | 820
1.2.1 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 1 | Activity 1: Develop metering plan | Month 2 | Labour | Agriculture | Applicant Company | 288 | 5 | 1440 | 550 | 150 | 0 | 0 | 740 | 0 | 0 | 1440
1.2.2 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 2 | Activity 2: Acquire submeters | Month 2 | Material / Equipment / Hardware | Manufacturing | Meter Co. | 266 | 18 | 4788 | 4000 | 0 | 0 | 788 | 0 | 0 | 0 | 4788
1.2.3 | 1 | Milestone 1: Demonstration Preparation | 2 | Task 2: Meter Installation | 3 | Activity 3: Meter installation | Month 3 | Labour | Business, building and other support services | Demonstration Facility | 115 | 15 | 1725 | 0 | 0 | 295 | 230 | 0 | 1200 | 0 | 1725
1.3.1 | 1 | Milestone 1: Demonstration Preparation | 3 | Task 3: Establishing baseline | 1 | Activity 1: Data collection (6 months) | Month 9 | Labour | Business, building and other support services | Demonstration Facility | 32 | 214 | 6848 | 0 | 6000 | 848 | 0 | 0 | 0 | 0 | 6848
1.3.2 | 1 | Milestone 1: Demonstration Preparation | 3 | Task 3: Establishing baseline | 2 | Activity 2: Data analyis and weather normalization | Month 10 | Labour | Agriculture | Applicant Company | 95 | 61 | 5795 | 1400 | 1400 | 0 | 500 | 2495 | 0 | 0 | 5795
1.4.1 | 1 | Milestone 1: Demonstration Preparation | 4 | Task 4: Reporting | 1 | Activity 1: Draft report on baseline establishment | Month 11 | Labour | Agriculture | Applicant Company | 632 | 6 | 3792 | 420 | 0 | 0 | 210 | 3162 | 0 | 0 | 3792
Milestone 1 Summary | [11 empty] | 339 | 27980 | 6370 | 8240 | 1943 | 3078 | 6649 | 1200 | 500 | 27980
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
2.1.1 | 2 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
2.. | 2 | [11 empty] | 0 | [7 empty] | 0
Milestone 2 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
3.1.1 | 3 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
3.. | 3 | [11 empty] | 0 | [7 empty] | 0
Milestone 3 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
4.1.1 | 4 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
4.. | 4 | [11 empty] | 0 | [7 empty] | 0
Milestone 4 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task].[Activity] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Industry (NAICS) Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (IESO) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
5.1.1 | 5 |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
5.. | 5 | [11 empty] | 0 | [7 empty] | 0
Milestone 5 Summary | [11 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
PLEASE NOTE:
1. Please refer to spreadsheet titled "2. Budget EXAMPLE" for example content to demonstrate format.
2. All budget line items must be clearly linked to a deliverable outlined in the Milestones (Proposal Template Part A)
3. The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column.
4. Please refer to the final page of the Proposal Guide available on IESO Grid Innovation Fund webpage for more information on eligible expenses.
5. Final project milestone value must represent a minimum of 10% of Fund grant.
6. Eligible labour costs are capped at a maximum $800/day (7.5 hours)
7. In-kind and cash contributions consist of auditable, substantiated cash and non-cash contributions to the project that contribute substantially to the completion of the project.
8. Add/Remove Milestones as required
Note on C14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on E14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: This field indicates which industry is associated with this project activity cost based on the North American Industry Classification System (NAICS).
Note on L58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on M58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on Q58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 3. Work Plan EXAMPLE
Grid Innovation Fund Project Work Plan (Proposal Section 2.1)
Project Name
Organization Name
Project Month # (Maximum project length is 36 months)
Milestone | Task Area | Activity/ Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
E.g., Milestone 1 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 1 to Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 4 to Project Month # (Maximum project length is 36 months) 7
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 6 to Project Month # (Maximum project length is 36 months) 10
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 3 to Project Month # (Maximum project length is 36 months) 4
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 5 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 14
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 15
E.g., Milestone 2 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 12 to Project Month # (Maximum project length is 36 months) 13
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 13 to Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 18
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 15 to Project Month # (Maximum project length is 36 months) 21
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 14
| E.g., Task Area 3 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 14 to Project Month # (Maximum project length is 36 months) 19
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 16 to Project Month # (Maximum project length is 36 months) 23
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 23 to Project Month # (Maximum project length is 36 months) 25
E.g., Milestone 3 | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 26
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 24
E.g., Activity 3 | bar: Project Month # (Maximum project length is 36 months) 24 to Project Month # (Maximum project length is 36 months) 27
E.g., Activity 4 | bar: Project Month # (Maximum project length is 36 months) 25 to Project Month # (Maximum project length is 36 months) 28
E.g., Activity 5 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 29
| E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 36 months) 28 to Project Month # (Maximum project length is 36 months) 33
E.g., Activity 2 | bar: Project Month # (Maximum project length is 36 months) 33 to Project Month # (Maximum project length is 36 months) 36

## 4. Measuring Results EXAMPLE
Grid Innovation Fund - Measuring Results (Example)
Project name:
Organization Name:
Click red triangles on cells for important notes that will help you accurately complete this template.
Ultimate Outcome | Ultimate Objective | Project/ Intermediate Objective | Immediate Objective | Activity/Deliverable | Performance Indicator | Method of Measurement | Target Results | Target Completion Date/Month
Reduce energy consumption of the workplace by 15%, saving 15MWh in a year | Workplace has incorporated effective energy management into its corporate culture and policies. | Individuals within organization have internalized conservation goals | Employee awareness of conservation opportunities measured | Initial employee survey | Initial employee conservation survey completed | Survey | 70% employee response rate to survey | 2025-10-01
|  |  |  | Analysis of survey results | Analysis provided to IESO | Receipt of survey results by IESO | Analysis sufficient to inform education | 2020512/01
|  |  |  | Post-education employee survey | Post-education component employee survey complete | Survey | 70% employee response rate to survey | 2020512/01
|  |  | Employee education on conservation opportunities | Development of education package | Completed packages | Packages completed | 70% employee response rate to survey | 2025-01-01
|  |  |  | Training of educators | Trained educators | Participation in training sessions | 10 educators trained | 2025-03-01
|  | Increased efficiency of machinery | Machines run only when necessary | Fine-tune automatic machine controls | Variation between machinery output and machine run-time | Submeter and data logger | Machine run-time exceeds production run-time by less than 5% | 2026-03-01
|  |  |  | Instruct machine operators to eliminate machine idling | Machines turned off when not in use | Weekly surprise site inspection | 90%+ of machines are turned off when not in use | 2026-05-01
|  |  | Machines operate within 5% of stated efficiency (from operator's manual) | Mechanic services machines regularly | Quarterly service call complete | Service sheet submitted to Facilities dept. | Servicing completed within first two weeks of each quarter | 2026-01-01
Note on B6: This should match worksheet 6. Quantifiable Outcomes as described in this proposal template.
Note on C6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on D6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on F6: Deliverables are tangible products that are created as the result of an activity. Some activities may not result in a deliverable but are nevertheless important (e.g., participant recruitment)
Note on G6: Measuring results requires a performance indicator to be established for EACH project activity/deliverable as well as plan for how and when it will be measured.
Note on H6: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on I6: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on J6: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.
Note on D7: Each project outcome (e.g. increasing staff enthusiasm for reducing electricity consumption, or replacing all inefficient lighting) may consist of several smaller, more immediate outcomes, for which there may be several tasks or activities. Outcomes are states or conditions of the people or things that are necessary for the project to succeed.

## 5. Project Risk Profile EXAMPLE
5. Project Risk Profile (EXAMPLE)
Risk ID | Milestone Impacted | Project Task | Project Impact (Drop down selection - Scope, Budget,Timeline) | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Classification (Calculated - DO NOT ENTER) | Risk Mitigation Strategy
1 | Milestone 1 | Site Confirmation | Timeline | Non-confirmation of project site prior to project kick-off | Significant | Unlikely | 3 | Engage with demonstration facility early, and ensure that all parties are aligned with the scope of the project to enable a fast reponse on demonstration site confirmation.
2 | Milestone 1 | Equipment Procurement | Timeline | Delays in delivery of equipment | Moderate | Likely | 2 | Factor in the expected lead time and add a buffer to compensate uncertainties in equipment delivery.
3 | Milestone 2 | Equipment Installation | Budget | Failure of equipment post installation | Moderate | Unlikely | 4 | Complete QA testing prior to equipment installation
4 | Milestone 2 | Equipment Installation | Timeline | Failure of equipment post installation | Moderate | Unlikely | 4 | Complete QA testing prior to equipment installation
5 | Milestone 3 | Reporting | Timeline | Inability to report statistically significant results | Critical | Unlikely | 2 | M&V plan will be completed and approved prior to data collection and analysis period.

## 6. Quantifiable Outcome EXAMPLE
6. Quantifiable Outcomes (EXAMPLE)
|  | 95% Confidence Interval | 95% Confidence Interval
Metric | Section and Equations Referenced in Written Project Proposal Part A | Lower Bound | Upper Bound | Expected Result | Unit | Qualitatitive Description (if applicable)
Energy Savings | Section 1.6.2.2 Equations (2) - (9) | 9600 | 14400 | 12000 | kWh | N/A
Peak Load Reduction | Section 1.6.2.2 Equations (10) - (15) | 2920 | 4380 | 3650 | kWh | N/A
Peak Load Shifting | Section 1.6.2.2Equations (16) - (17) | 2320 | 3480 | 2900 | kWh | N/A
Bill Savings | Section 1.6.2.2 Equations (18) - (19) | 12 | 18 | 15 | CAD$ per Bill | N/A
Reliability Improvement SAIFI | Section 1.6.2.2Equations (20) | 0.16 | 0.24 | 0.2 | hours | N/A
Reliability Improvement SAIDI | Section 1.6.2.2Equations (21) | 0.08 | 0.12 | 0.1 | hours | N/A
Jobs Supported | Section 1.8.2.4 | 36 | 54 | 45 | Jobs | N/A
Jobs Created | Section1.8.2.4 | 14 | 22 | 18 | Jobs | N/A
Additional Available Capacity | Section 1.6.1 | 696 | 1044 | 870 | kW | N/A
Active Participants | Section 1.7.2.3 | 438 | 658 | 548 | Participants | N/A
Policy/Regulatory Change | Section 1.9 | N/A | N/A | N/A | N/A | Results from this project will be used to support the update of Building Envelope Requirements as referenced in O.Reg. 332/12 MMA Supplementary Standard B-10
Please note the difference between project outcome and objectives. Successful completion of project objectives advances the success of project outcomes. For example, the installation of 20 widgets in residential homes is a project objective, not a project outcome. If the widget leads to energy savings, then the outcome of the project is the energy savings realised from using the widgets. This spreadsheet aims to capture all the quantifiable outcomes upon successful completion of the pilot project, ranging from energy savings, economic stimulus to reliability improvement.