## Instructions
End-to-End Testing- Issue Log Template
End-to-End Testing Objective: to provide Market Participants and their service providers an opportunity to validate their ability to execute key business processes and system interactions that are affected by the Market Renewal Program.
The worksheet(s) in this file correspond to a specific test case document that is available on the Market Participant Testing webpage (https://www.ieso.ca/en/Market-Renewal/Market-Participant-Readiness/Market-Participant-Testing). Below is a mapping of the worksheets to their related test case files:
S1 - FRL Change Request: Scenario 1: Financial Reference Level (FRL) Change Request S4 - Notice of Disagreement(NOD): Scenario 4: Notice of Disagreement S11 - 1-Day Advance Approval: Scenario 11: 1-Day Advance Approval Outage S12 - Hourly Demand Response - HDR: Test Scenario 12 - Hourly Demand Response (HDR) Activation S13 - OR Activation: Test Scenario 13 - Operating Reserve (OR) Activation S17 - GOG Commitment Advancements and Extensions: Scenario 17: GOG Commitment Advancements and Extensions S18 - GOG with more than 4 hours: Scenario 18: GOG Commitment withdrawn by MP with more than 4 hours advance notice S19 - GOG with less than 4 hours: Scenario 19: GOG Commitment withdrawn by MP with less than 4 hours advance notice S21 - SEAL Constraint: Scenario 21: SEAL Constraint
If your organization has opted out of using qTest, record the status of your testing using this Issue Log Template. Ensure any anomalies, disruptions, or irregularities discovered while testing are documented in the corresponding spreadsheet. This will contribute significantly to the overall improvement of the IESO tools. For convenience, a description of the fields on each worksheet are provided in the table below.
Once you complete your testing and have documented all results, please email IESO Customer Relations (customer.relations@ieso.ca) with the updated Issue Log Template file attached.
Note: Not all applications may be relevant or used by your organization. For those applications, please record "Not Applicable" as the status of the test steps on the corresponding worksheet.
Worksheet Instructions
Column Name: Description of Fields | Populated By
Test Step No.: Step number of the test case that the user is expected to execute | IESO
Test Step Description: Description of the task that the user must execute for the associated test step | IESO
Test Step Expected Result: Details on the expected outcome of the test step | IESO
Status: Status of the test step: Passed, Passed with Issues, Failed, or Not Applicable | Market Trial Participant
Organization Name: Market Participant Name | Market Trial Participant
User Name: Tester Name/Username | Market Trial Participant
Detected Date: Date when the test step was executed and when the issue was encountered | Market Trial Participant
Additional Comments: Any additonal information related to an issue, error message, and/or unexpected behaviour detected should be mentioned here. | Market Trial Participant
Attachments / Screenshots: Users can provide an image or attachment of the issue, error message, and/or unexpected behaviour they encountered during the execution of the test step. Ensure that the images do not contain confidential information. If a Market Participant wishes to send confidential information, they can inform the IESO by sending an email to customer.relations@ieso.ca. An MRP Business Advisor will contact the Market Participant directly with further instructions. | Market Trial Participant

## S1 - FRL Change Request
End-to-End Testing: | Test Scenario 1: Financial Reference Levels (FRL) Submissions in Online IESO
Prerequisites: | 1. Access to Online IESO sandbox application with Dispatch Data Submitter role
2. This test case applies to market participants with dispatchable generator resources which have a high-low FRL profile with no average cost reference level registered and are eligible to submit temporary cost profile change requests. Please refer to MM 14.2, section 5 Temporary Reference Level Change Requests
3. No ‘In-flight’ request for high profile usage has been submitted for the resource being tested for the same dispatch day and for the same set of hours.
Test Case Name: | S1-TC01: Market Participant submits a temporary high-cost profile change request for an eligible dispatchable generator resource type for Dispatch Day = Today.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | User should login into ONLINE IESO application with the following credentials: - Username: - Password: | User able to login into ONLINE IESO application successfully.
2 | 'Select the navigation button and choose the "Market Power Mitigation" option. Click on "Submit Temporary Financial Reference Level Change Request" tile. | The ‘Submit Temporary Financial Reference Level Change Request’ form is displayed.
3 | Under the section labeled "Please Select Organization, Request Type, and Resource", select an organization from the Organization list. | The list of organizations under the Market Participant is displayed, and the selected organization is reflected on the field.
4 | Select Request Type = 'Cost-Profile Change.' | The 'Cost-Profile Change' option is selected under the Request Type, and the list of resources that are eligible for this request are displayed under the Resource field.
5 | Select at least one dispatchable generation resource from the Resource field and then click on the "Proceed with Cost Profile Change Request" button. | The selected resource is displayed and the user is directed to the next step to select dispatch information.
6 | Select dispatch day = 'Today' and the affected dispatch hours. Note: User must be able to select the hours except the current dispatch hour + 150 Minutes in EST (pre-dispatch restricted window). | Dispatch day is set 'Today' and the selected dispatch hours are displayed.
7 | Upload supporting documentation to the request. | File is successfully uploaded and attached to the form.
8 | Click the "Submit" button. | The cost profile change request is successfully submitted.
9 | Click on the "Temporary FRL Change Requests" tile on the MPM dashboard | A list of all submitted temporary FRL change requests are displayed.
10 | Verify that the submitted cost profile change request is reflected on the Realtime FRL reports from the IESO Private Reports site that are published on the same day. | The submitted change request is included in the RT FRL reports.
Test Case Name: | S1-TC02: Market Participant submits a temporary fuel cost change request for an eligible dispatchable generator resource for Dispatch Day = Today.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | User should login to ONLINE IESO application with the following credentials: - Username: - Password: | User able to login into ONLINE IESO application successfully.
2 | 'Select the navigation button and choose the "Market Power Mitigation" option. Click on "Submit Temporary Financial Reference Level Change Request" tile. | The ‘Submit Temporary Financial Reference Level Change Request’ form is displayed.
3 | Under the section labeled "Please Select Organization, Request Type, and Resource", select an organization from the Organization list. | The list of organizations under the Market Participant is displayed, and the selected organization is reflected on the field.
4 | Select Request Type = 'Fuel Cost Change.' | The 'Fuel Cost Change' option is selected under the Request Type, and the list of resources that are eligible for this request are displayed under the Resource field.
5 | Select at least one dispatchable generator resource and click on "Select Parameter." | The selected resource is displayed, and the user is directed to the next section to select a parameter.
6 | Select a parameter and click on "Proceed with Fuel Cost Change Request." | The selected parameter is displayed, and the user is directed to the next step to select dispatch information.
7 | Select dispatch day = 'Today' and the affected dispatch hours. Note: User must be able to select the hours except the current dispatch hour + 150 Minutes in EST (pre-dispatch restricted window). | Dispatch day is set 'Today' and the selected dispatch hours are displayed.
8 | Upload supporting documentation to the request. | File is successfully uploaded and attached to the form.
9 | Click the Submit. | The fuel cost change request is successfully submitted.
10 | Click on the "Temporary FRL Change Requests" tile on the MPM dashboard | A list of all submitted temporary FRL change requests are displayed.
11 | Verify that the submitted cost profile change request is reflected on the Realtime FRL reports from the IESO Reports site that are published on the same day. | The submitted change request is included in the MPM RT FRL reports. Note: For hydro resources, the report should reflect the new fuel cost for the requested resource and resources downstream of it.
Test Case Name: | S1-TC03: Market Participant submits a temporary high-cost profile change request for an eligible dispatchable generator resource for Dispatch Day = Tomorrow.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | User should login into ONLINE IESO application with the following credentials: - Username: - Password: | User able to login to ONLINE IESO application successfully.
2 | Select the navigation button and choose the "Market Power Mitigation" option. Click on "Submit Temporary Financial Reference Level Change Request" tile. | The ‘Submit Temporary Financial Reference Level Change Request’ form is displayed.
3 | Under the section labeled "Please Select Organization, Request Type, and Resource", select an organization from the Organization list. | The list of organizations under the Market Participant is displayed, and the selected organization is reflected on the field.
4 | Select Request Type = 'Cost-Profile Change.' | The 'Cost-Profile Change' option is selected under the Request Type, and the list of resources that are eligible for this request are displayed under the Resource field.
5 | Select at least one dispatchable generation resource from the Resource field and then click on the "Proceed with Cost Profile Change Request" button. | The selected resource is displayed, and the user is directed to the next step to select dispatch information.
6 | Select the dispatch day = 'Tomorrow' and the affected dispatch hours. Note: users can only submit a day-ahead request during the DAM timeframe (from 6:00 AM EPT to 9:30 AM EPT). | Dispatch day is set 'Tomorrow' and the selected dispatch hours are displayed.
7 | Upload supporting documentation to the request. | File is successfully uploaded and attached to the form.
8 | Click the "Submit" button. | The cost profile change request is successfully submitted.
9 | Click on the "Temporary FRL Change Requests" tile on the MPM dashboard | A list of all submitted temporary FRL change requests are displayed.
10 | Verify that the submitted cost profile change request is reflected on the DA FRL reports from the IESO Private Reports site that are published on the same day to be applied for the next trade date. | The submitted change request is included in the DA FRL reports.
Test Case Name: | S1-TC04: Market Participant submits a temporary fuel cost change request for an eligible dispatchable generator resource for Dispatch Day = Tomorrow.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | User should login to ONLINE IESO application with the following credentials: - Username: - Password: | User able to login to ONLINE IESO application successfully.
2 | Select the navigation button and choose the "Market Power Mitigation" option. Click on "Submit Temporary Financial Reference Level Change Request" tile. | The ‘Submit Temporary Financial Reference Level Change Request’ form is displayed.
3 | Under the section labeled "Please Select Organization, Request Type, and Resource", select an organization from the Organization list. | The list of organizations under the Market Participant is displayed, and the selected organization is reflected on the field.
4 | Select Request Type = 'Fuel Cost Change.' | The 'Fuel Cost Change' option is selected under the Request Type, and the list of resources that are eligible for this request are displayed under the Resource field.
5 | Select at least one dispatchable generator resource and click on "Select Parameter." | The selected resource is displayed and the user is directed to the next section to select a parameter.
6 | Select a parameter and click on "Proceed With Fuel Cost Change Request." | The selected parameter is displayed and the user is directed to the next step to select dispatch information.
7 | Select the dispatch day = 'Tomorrow' and the affected dispatch hours. Note: users can only submit a day-ahead request during the DAM timeframe (from 6:00 AM EPT to 9:30 AM EPT). | Dispatch day is set 'Tomorrow' and the selected dispatch hours are displayed.
8 | Upload supporting documentation to the request. | File is successfully uploaded and attached to the form.
9 | Click the "Submit" button. | The cost profile change request is successfully submitted.
10 | Click on the "Temporary FRL Change Requests" tile on the MPM dashboard | A list of all submitted temporary FRL change requests are displayed.
11 | Verify that the submitted cost profile change request is reflected on the DA FRL reports from the IESO Private Reports site that are published on the same day to be applied for the next trade date. | The submitted change request is included in the DA FRL reports.

## S4- Notice of Disagreement(NOD)
End-to-End Testing: | Test Scenario 4 - Notice of Disagreements (NODs)
Prerequisites: | 1. Valid login credentials for Online IESO, IESO Confidential Reports site.
2. Testing User for that MP needs to have Notice of Disagreement Contact role assigned in Online IESO Sandbox.
3. MP must submit the NOD within six business days after the IESO issued the settlement statement. Note: MP may submit the NOD only during the NOD window of 6 business days. During End-to-End testing MPs can perform functional testing for NODs (see End to End Settlement Schedule for dates) and the IESO will not be providing any resolution to these NODs.
4. MP must have participated in the market and triggered a PSS to be able to submit a NOD.
Test Case Name: | S4-TC01: Market Participant is able to perform functional testing for the process: "Submission of Notice of Disagreement form" for a given trade date on Online IESO
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Login to the Online IESO Sandbox application with the correct credentials. | User Login is Successful.
2 | Using the Actions menu, select-> Submit a Settlement Disagreement, and then specify a trade date. | The NOD form submission window opens up.
3 | Select the Disagreement Channel and fill out all the forms, • Organization Selection form • Statement Selection form • Line Items Selection form • Missing Line Items form • Additional Information form | All MRP Charge Types listed on the Settlement Statement for this NOD are available for selection in the form and all of the required forms are filled out.
4 | Select the Submit button, to submit the 'Notice of Disagreement' to the IESO. | Submission is successful.
5 | Check for IESO’s acknowledgment of receipt. | Acknowledgement receipt will include: a unique identifier for the submission, and a date and time stamp of when the Notice of Disagreement was received.

## S9-Fuel Cost Compensation Form
End-to-End Testing: | Scenario 9 - Fuel Cost Compensation Form
Prerequisites: | 1. User has access to Online IESO Sandbox.
2. User is assigned the contact role "Settlement Data and File Submitter" in Online IESO.
3. User has performed "Connectivity Testing: Access Online IESO" with User ACCOUNT_ID #1. (https://www.ieso.ca/-/media/Files/IESO/Document-Library/market-renewal/Market-Participant-Testing/Test-Cases-for-Connectivity-Testing.zip). Note: Refer to Section 1 of the Market Trials Job Aid for Testing of the Fuel Cost Compensation Form in Online IESO (https://www.ieso.ca/-/media/Files/IESO/Document-Library/market-renewal/Market-Participant-Testing/Market-Trail-Test-Cases/JobAid-ONLSF-FCC-Final.pdf)
Test Case Name: | S9-TC01: Online IESO:Verify that user (with a Settlement Data and File Submitter contact role) is able to submit the claim for a trade date within the submission window.
Note: a claim for a trade date can only be submitted within the first 30 calendar days (excluding statutory holidays) after the trade date.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Log in to Online IESO Sandbox by logging in to the IESO Gateway (https://gateway-sbx.ieso.ca) or using the direct URL (https://onlinesandbox.ieso.ca/) | User is able to access Online IESO Sandbox.
2 | Navigate to Actions and click the Submit Settlement Claim link from the list of forms. | User is redirected to the Submit Settlement Claim form.
3 | Select an organization from the "Organization" drop-down field. | User is able to select an organization.
4 | Select Fuel Cost Compensation from the "Claim Form" drop-down field and click the CONTINUE button. | User is redirected to the Fuel Cost Compensation form.
5 | Select a "Trade Date" within the submission window | Verify that the "+ Add New" link is displayed.
6 | Click the "+ Add New" link to display more fields. | Two drop-down fields are displayed: (1) "Resource Name (Resource ID)*" and (2) "Time Frame*"
7 | Select a resource from the "Resource Name (Resource ID)*" drop-down field. | Verify that the Resource ID for the selected resource is displayed. Note: the user should only see GOG-eligible resources that belong to their organization in this drop-down list.
8 | Select Day-Ahead Market from the "Time Frame*" drop-down field. | The Day-Ahead Market value is selected, and the "+ Add Item" link is displayed on the form.
9 | Click "+ Add Item" link to display more fields. | The following fields are displayed: (1) # (2) Operational Commitment Start Hour Ending EST (mandatory) (3) Fuel Type (mandatory) (4) Compensation Amount ($) (mandatory) (5) Supporting Document (mandatory) (6) Additional Comments (optional)
10 | Select trade hour 1 from the "Operational Commitment Start Hour Ending EST" drop-down field. | A value of 1 for the "Operational Commitment Start Hour Ending EST" field is displayed upon selection.
11 | Select a Fuel Type from the "Fuel Type" drop-down field. | The selected Fuel Type is displayed.
12 | Enter a number under the "Compensation Amount ($)" field. (Note: This value must be greater than $0.00 and must not exceed 10 digits including no more than 2 decimal places. Otherwise, an error message will be displayed.) | The number is accepted and displayed on the field.
13 | Click the UPLOAD button to upload a file under the "Supporting Document" field. (Note: the filename including its extension must not exceed 100 characters, and the file size must not exceed 2MB. Otherwise an error message will be displayed.) | The supporting document is uploaded.
14 | Add text in the "Additional Comments" field. | The entered text is displayed.
15 | Click the ADD NEW ENTRY button. | The form is refreshed with the added information, and the SUBMIT button is displayed.
16 | Click the SUBMIT button. | A pop-up window appears with the following message, "Are you sure you want to submit this claim?"
17 | Click the YES button. | The form is refreshed with the following message displayed: "This claim has been successfully submitted - Reference #: ##### - 1."
18 | Click the EXIT button. | A pop-up window appears with the following message, "Are you sure you want to leave this page? Data that has not been saved or submitted will be lost."
19 | Click the YES button. | User successfully exits from the Fuel Cost Compensation form and returns to the Submit Settlement Claim form.
20 | Log out. | User is logged out successfully

## S11 - 1-Day Advance Approval
End-to-End Testing: | Test Scenario 11 - 1-Day Advance Approval Outage
Prerequisites: | 1. Valid login credentials for EMI/MIM, Online IESO, IESO Reports Site, Dispatch Service, and CROW/OCSS.
Test Case Name: | S11-TC01: Market Participants are able to submit an outage request within the new submission timelines for the 1-Day Advance Approval Process. This test case will accept the outage request for the equipment.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Log in to the Outage Coordination and Scheduling System (OCSS) and submit a planned outage request 2 business days before the targeted trade date by 10:00 EST for an equipment. In the request, include details such as outage description, purpose description and planned start date. Note: 1) The outage request submitted must be eligible for one-day advance approval. 2) MP must communicate the details of the outage slip for this test case via email. 3) MP will request for the IESO to approve the outage request via email. | The outage submission is processed successfully in CROW/OCSS and labelled as '1-Day Advance Approval' under the assessment eligibility label.
2 | Review the history of the outage requested in CROW/OCSS and confirm that the outage was approved by IESO. | Log in to the Outage Coordination and Scheduling System (OCSS) and submit a planned outage request 2 days before the targeted trade date by 10:00 EST for an equipment. In the request, include details such as outage description, purpose description and planned start date. Note: 1) The outage request submitted must be eligible for one-day advance approval. 2) MP must communicate the details of the outage slip for this test case via email. 3) MP will request for the IESO to approve the outage request via email.
Test Case Name: | S11-TC02: Market Participants are able to submit an outage request within the new submission timelines for the 1-Day Advance Approval Process. This test case will automatically reject the outage request for the equipment.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Log in to the Outage Coordination and Scheduling System (OCSS) and submit a planned outage request 2 business days before the targeted trade date by 10:00 EST for an equipment. In the request, include details such as outage description, purpose description and planned start date. Note: 1) The outage request submitted must be eligible for one-day advance approval. 2) MP must communicate the details of the outage slip for this test case via email. 3) MP will notify the IESO via email to leave the outage request alone for it to be automatically rejected. | MP outage submission is processed successfully in CROW/OCSS.
2 | Review the history of the outage requested in CROW/OCSS and confirm that the outage was auto rejected. | MP is able to verify that the outage is auto rejected.

## S12-Hourly Demand Response-HDR
End-to-End Testing: | Test Scenario 12 - Hourly Demand Response (HDR) Activation
Prerequisites: | 1. Valid login credentials for EMI/MIM, Online IESO, IESO Confidential Sandbox Reports site
2. Market Participant (MP) to provide IESO the below details EOD Friday Jan 24, 2025: - Resource name - Hours of activation
Test Case Name: | S12-TC01: Capacity Market resources can test their HDR (Hourly Demand Response) DAM commitments and the associated impacts on their settlement statements
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | MP should submit RTEM data for an HDR offer through the EMI/MIM application during the RT_INITIAL window in an attempt to get a DAM schedule in advance of the trade date. Note: The IESO advises market participants to review market conditions in the days ahead of the scenario test dates. If the market participant does not feel confident that they can achieve standby or activation notices, while bidding above the $100 demand response bid price threshold, then please submit the information noted in appendix 6 of the test plan so that the IESO can manually trigger standby and activation notices. | Dispatch data submission is processed successfully.
2 | MP to navigate to the following path on the IESO Confidential Sandbox reports site to verify the stand by notice (Private report): Your Files > private > DR-Standby > {MP_Name} Open the latest xxxxxDR-Standby.xml that is generated after the DA_RESTRICTED window. Note: If MP does not receive the stand by notice in the DR-Standby report, MP to check the DAScheduledEnergy2 (DA Schedules Report) and DAHourlyEnergyLMP Reports to determine their Standby status and inform the IESO about any discrepancies. | MP is able to verify their Standby status (set as 'Yes' or 'No') in the DR-Standby report.
3 | MP to navigate to the following path on the IESO Confidential Sandbox Reports site, two hours before the dispatch hour, to verify the Activation notice: Your Files > private > DR-Activation > {MP_Name} Open the latest xxxxxDR-Activation.xml report that is generated. | MP is able to verify the Activation notice on the DR-Activation report.
4 | In the IESO Confidential Sandbox Reports Site, MP is able to download the preliminary and final settlement statements along with the data files for the affected trade date of this test case. | Market Participant is able to download the preliminary and final settlement statements and associated data files from the IESO Confidential Sandbox Reports Site.
5 | Review settlement statements for applicable charges and calculations. | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
6 | Review settlement statements for non-applicable charges and calculations. | Non-applicable charges/payments should not be present in the settlement statements.
7 | Review settlement statements for calculation accuracy. | Charges/payments are calculated accurately.

## S13-OR Activiation
End-to-End Testing: | Test Scenario 13 - Operating Reserve (OR) Activation
Prerequisites: | 1. Valid login credentials for EMI/MIM, Online IESO, IESO Confidential Sandbox Reports site, and Dispatch Service
2. Market Participant (MP) to provide IESO the below details a day prior to the OR Activation request: -Resource name -Hour of activation (note: activation will last at least 15 minutes) *Note* the IESO cannot guarantee the activation of specific MW amounts due to the co0optimization and scheduling of operating reserve.
3. Real-Time Energy Market data for the corresponding market participant, delivery date, resource, and hour are present in the system
4. Daily Dispatch Data (DDD) data is present in the system (if the corresponding RTEM submission resource type is one of the following: Non-Quick Start (NQS) Other, Combustion Turbine (CT) Pseudo-Unit (PSU), Steam Turbine (ST) PSU, CT Non-PSU, ST Non-PSU)
Test Case Name: | S13-TC01: All eligible resources scheduled for Operating Reserve (OR) are able to test OR activation and its impact on settlements in the Real-Time Market (RTEM)
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Market Participant submits economic Operating Reserve dispatch data in EMI/MIM during the RT_INITIAL window. | EMI/MIM submission is processed successfully.
2 | Market Participant receives notification to approve/reject OR Activated schedule in Dispatch Services. Market Participant should approve the OR Activated schedule. Note: Market participants should notify the IESO of any changes to the original ORA time window in case the requested time was not achieved through scheduling. | Market Participant approval is processed successfully
3 | In the IESO Confidential Sandbox Reports Site, Market Participant is able to download the preliminary and final settlement statements along with the data files for the affected trade date of this test case. | Market Participant is able to download the preliminary and final settlement statements and associated data files from the IESO Confidential Sandbox Reports Site.
4 | Review statements for applicable charges and calculations | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
5 | Review statements for non applicable charges and calculations | Market Participant to verify that all non applicable charges/payments should not be present in the settlement statements.
6 | Market Participant to review statements for calculation accuracy | Market Participant is able to verify that the charges/payments are accurately calculated.

## S17-GOG Commitment Advancements
End-to-End Testing: | Test Scenario 17 - Generator Offer Guarantee (GOG) Commitment Advancements and Extensions
Prerequisites | 1. Valid login credentials for EMI/MIM, Online IESO, Reports site, and Dispatch Services.
2. If the "RTEM" data is being submitted by the following resource types: Non-Quick Start (NQS) Other, Combustion Turbine (CT) Pseudo-Unit (PSU), Steam Turbine (ST) PSU, CT Non-PSU, or ST Non-PSU, then the Daily Dispatch Data (DDD) for the corresponding participant, delivery date, and resource should be present in the system.
Test Case Name: | S17-TC01: Resources are able to submit GOG-commitment advancements and extensions for GOG-DAM commitment.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Submit RTEM dispatch data through EMI/MIM during the day-ahead market submission window (RT_INITIAL) in an attempt to get a GOG-DAM commitment scheduled in advance. Note: 1) If the offer prices are lower during the submission, there is a high chance that the resource will get a commitment from DSO. 2) MP must ensure that they have a long lead time to be able to create an advancement. | EMI/MIM submission is processed successfully.
2 | After the day-ahead market run, navigate to the following path in the IESO Confidential Reports Site: Your Files > private > DACommit2 > {MP_Name} Open the latest xxxxxDACommit2.xml that is generated after the DA_RESTRICTED window (after the DAM completion). | MP is able to verify in the report that there is a DA-CMT (Day Ahead Commitment) scheduled for certain hours.
3 | In EMI/MIM, submit another offer with economic prices (lower than the price submitted in test step 1) for the hours preceding the DAM commitment start hour well ahead of the DAM commitment start hour in an attempt to receive an advancement. | EMI/MIM submission is processed successfully.
4 | MP receives an advancement notice in Dispatch Service. Choose to either approve or reject the advancement in Dispatch Service. | MP approval/rejection is processed successfully.
5 | After the start-up notification for the PD commitment/advancement is received, navigate to the following path on the IESO Confidential Reports Site: Your Files > private >PDCommitments > {MP_Name} Open the xxxPDCommitmentsxxx.xml that is generated. Note: 1) MP will receive start-up notification(s) through Dispatch Service once the PD commitment is scheduled. | MP is able to verify in the report that there is a PD-CMT (Pre-Dispatch Commitment) scheduled for the relevant hours.
6 | In EMI/MIM, submit another offer with economic prices (lower than the price submitted in test step 1) for the hours after the DAM commitment end hour well ahead of the DAM commitment end hour in an attempt to receive an extension. | Changes submitted by MP in EMI/MIM are processed successfully
7 | MP confirms that they received an extension notice in Dispatch Service. | MP confirms that extensions are accepted by default.
8 | After the PD commitment/extension is received, navigate to the following path in the IESO Confidential Reports Site: Your Files > private >PDCommitments > {MP_Name} Open the latest xxxPDCommitmentsxxx.xml.xml that is generated. | MP is able to verify in the report that there is a PD-CMT (Pre-Dispatch Commitment) scheduled for the relevant hours.
9 | In the IESO Confidential Sandbox Reports Site, MP is able to download the preliminary and final settlement statements along with the data files for the affected trade date of this test case. | MP is able to download the preliminary and final settlement statements and associated data files from the IESO Confidential Sandbox Reports Site.
10 | Review settlement statements for applicable charges and calculations. | Only applicable charges/payments are present in the settlement statements.
11 | Review settlement statements for non-applicable charges and calculations. | Non-applicable charges/payments should not be present in the settlement statements.
12 | Review settlement statements for calculation accuracy. | Charges/payments are calculated accurately.
Test Case Name: | S17-TC02: Resources are able to submit GOG-commitment advancements and extensions for GOG-PD commitment.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | MP submits RTEM dispatch data through EMI or MIM after the day-ahead market restricted window (DA_RESTRICTED) in an attempt to get a GOG-PD commitment scheduled in advance. Note: 1) If the offer prices are lower during the submission, there is a high chance that the resource will get commitment from DSO 2) MP must ensure that they have a long lead time to be able to create an advancement. | EMI/MIM submission is processed successfully.
2 | After the PD commitment is scheduled, navigate to the following path on the IESO Confidential Reports Site: Your Files > private >PDCommitments > {MP_Name} Open the latest xxxPDCommitmentsxxx.xml.xml that is generated. Note: 1) MP will receive start-up notification through Dispatch Services once the PD commitment is scheduled. | MP is able to verify in the report that there is a PD-CMT (Pre-Dispatch Commitment) scheduled for certain hours.
3 | In EMI/MIM, submit another offer with economic prices (lower than the price submitted in test step 1) for the hours preceding the PD commitment start hour well ahead of the PD commitment start hour in an attempt to receive an advancement. Note: 1) When trying to create an advancement for PD commitments, MPs will need to reduce the lead time after they receive their start-up notification. | EMI/MIM submission is processed successfully.
4 | MP receives an advancement notice in Dispatch Service. Choose to either approve or reject the advancement in Dispatch Service. | MP approval/rejection of the advancement is processed successfully.
5 | After the start-up notification of the PD commitment/advancement is received, navigate to the following path in the IESO Confidential Reports Site: Your Files > private >PDCommitments > {MP_Name} Open the latest xxxPDCommitmentsxxx.xml.xml that is generated. Note: 1) MP will receive start-up notification through Dispatch Service once the PD commitment is scheduled. | MP is able to verify in the report that there is a PD-CMT (Pre-Dispatch Commitment) scheduled for the relevant hours.
6 | In EMI/MIM, submit another offer with economic prices (lower than the price submitted in test step 1) for the hours after the PD commitment end hour well ahead of the PD commitment end hour in an attempt to receive an extension. | Changes submitted by MP to EMI/MIM are processed successfully.
7 | MP receives an extension notice in Dispatch Service. | MP confirms that extensions are accepted by default.
8 | After the PD commitment/extension is received, navigate to the following path in the IESO Confidential Reports Site: Your Files > private >PDCommitments > {MP_Name} Open the latest xxxPDCommitmentsxxx.xml.xml that is generated. | MP is able to verify in the report that there is a PD-CMT (Pre-Dispatch Commitment) scheduled for the relevant hours.
9 | In the IESO Confidential Sandbox Reports Site, MP is able to download the preliminary and final settlement statements along with the data files for the affected trade date of this test case. | MP is able to download the preliminary and final settlement statements and associated data files from the IESO Confidential Sandbox Reports Site.
10 | Review settlement statements for applicable charges and calculations. | Only applicable charges/payments are present in the settlement statements.
11 | Review settlement statements for non-applicable charges and calculations. | Non-applicable charges/payments should not be present in the settlement statements.
12 | Review settlement statements for calculation accuracy. | Charges/payments are calculated accurately.

## S18-GOG with more than 4 hours
End-to-End Testing: | Test Scenario 18 - Generator Offer Guarantee (GOG) Commitment Withdrawn by MP with 4 hours or more of advance
Prerequisites: | 1. Valid login credentials for EMI/MIM, Online IESO, IESO Confidential Reports Site, Dispatch Services
2. DDD for the corresponding participant, delivery date, and resource must be present in the system.
Test Case Name: | S18-TC01: Generator Offer Guarantee (GOG) commitment withdraw by Market participant with 4 Hours or more of advance notice
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Market Participant should submit RTEM data through EMI/MIM during the RT_INITIAL window to get a GOG-DAM commitment scheduled in advance Note: If the offer prices are lower during the submission, there is a high chance that the resource will get commitment from DSO | EMI/MIM submission is processed successfully
2 | Post DAM Run, navigate to the following path on the IESO reports site Your Files > private > DACommit2 > {MP_Name} Then, Open the latest xxxxxDACommit2.xml that is generated after the DA_RESTRICTED window (after the DAM completion) | Market Participant able to verify in the report that there is a DA-CMT scheduled for certain hours
3 | Market Participant to request IESO through email to terminate the DAM commitment that is generated in (step 2), 4 hours ahead of DAM commitment start hour | Market Participant request to terminate the commitment is successfully sent to the IESO Operator through email.
4 | Market Participant should cancel RTEM offers for DAM-committed hours through EMI/MIM, at least 4 hours before the DAM commitment start hour | RTEM offers for the hours that are committed in DAM are cancelled successfully through EMI/MIM.
5 | Once the PD Run completes after the IESO Operator terminates the commitment (MP will receive email notification about the termination), Navigate to the following path on the IESO reports site Your Files > private >PDCommitments > {MP_Name} | 1) If there are no other PD or DA Commitment scheduled for the same resource or other resources of the participant on the given trade date, Market Participant to verify no new PD Commitment report is generated after IESO Operator terminates the commitment and the PD Run is complete. 2)If other PD/DA commitments exist for the same resource (different hours) or other participant resources on the trade date, Market Participant must: 1.Open the PD Commitment report (xxxPDCommitmentsxxx.xml) that is generated after the PD Run is completed, following IESO Operator's commitment termination. 2.Verify terminated hours have no associated commitments
6 | In the IESO Confidential Sandbox Reports site, MP to retrieve preliminary and final settlement statements and associated data files | Market Participant to verify generation and successful retrieval of preliminary and final statements, and associated data files.
7 | Review statement for applicable charges and calculations | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
8 | Review statement for non-applicable charges and calculations | Market Participant to verify that all non-applicable charges/payments should not be present in the settlement statements.
9 | MP to review statements for calculation accuracy | Market Participant can verify that the charges/payments are accurately calculated.

## S19-GOG with less than 4 hours
End-to-End Testing: | Test Scenario 19 - Generator Offer Guarantee (GOG) Commitment Withdrawn by MP with less 4 hours advance notice
Prerequisites: | 1. Valid login credentials for the MRP Energy Market Interface (EMI)/MRP Market Information Management (MIM) system, Online IESO, IESO Confidential Reports Site, and MRP Dispatch Service system in the Sandbox environment.
2. Daily Dispatch Data (DDD) for the corresponding participant, delivery date, and resource must be present in the Market Information Management system.
Test Case Name: | S19-TC01: Generator Offer Guarantee (GOG) DAM Commitment withdrawn by the Market Participant with less than 4 hours of advance notice.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | MP should submit RTEM data through EMI/MIM during the RT_INITIAL window to get a GOG-DAM commitment scheduled in advance Note: If the offer prices are lower during the submission, there is a high chance that the resource will get commitment from DSO | EMI/MIM submission is processed successfully
2 | Post DAM Run, navigate to the following path on the IESO reports site Your Files > private > DACommit2 > {MP_Name} Then, Open the latest xxxxxDACommit2.xml that is generated after the DA_RESTRICTED window (after the DAM completion) | MP able to verify in the report that there is a DA-CMT scheduled for certain hours
3 | Market Participant to E-mail IESO to request termination of the DAM commitment generated in (Step 2), within 4 hours of the commitment start time | Market Participant request to terminate the contract is successfully sent to the IESO Operator through email
4 | MP should cancel their RTEM offers for the hours that are committed in DAM through EMI/MIM within 4 hours of the commitment start time Note: If the some or all the hours that are being cancelled are in the RT_MANDATORY window, then the submission is subjected to approval from the IESO Operator. | RTEM offers for the hours that are committed in DAM are cancelled successfully through EMI/MIM
5 | Once the PD Run completes after the IESO Operator terminates the commitment (MP will receive an email notification about the termination), Navigate to the following path on the IESO reports site Your Files > private >PDCommitments > {MP_Name} | 1) If there are no other PD or DA Commitment scheduled for the same resource or other resources of the participant on the given trade date, MP to verify no new PD Commitment report is generated after IESO Operator terminates the commitment and the PD Run is complete. 2) If other PD/DA commitments exist for the same resource (different hours) or other participant resources on the trade date, Market Participant must: 1.Open the PD Commitment report (xxxPDCommitmentsxxx.xml) that is generated after the PD Run is completed, following IESO Operator's commitment termination. 2.Verify terminated hours have no associated commitments.
6 | In the IESO Confidential Sandbox Reports site, Market Participant to retrieve preliminary and final settlement statements and associated data files | Market Participant to verify generation and successful retrieval of preliminary and final statements, and associated data files.
7 | Review statement for applicable charges and calculations | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
8 | Review statement for non-applicable charges and calculations | Market Participant to verify that no non-applicable charges/payments are present in the settlement statements.
9 | Market Participant to review statements for calculation accuracy | Market Participant can verify that the charges/payments are accurately calculated.
Test Case Name: | S19-TC02: Generator Offer Guarantee (GOG) PD Commitment withdrawn by the Market Participant with less than 4 hours of advance notice
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | MP submits RTEM dispatch data through EMI or MIM after DA_RESTRICTED window Note: If the offer prices are lower during the submission, there is a high chance that the resource will get commitment from DSO | EMI/MIM submission is processed successfully
2 | After the PD commitment is scheduled, navigate to the following path on the IESO reports site Your Files > private >PDCommitments > {MP_Name} Then, Open the latest xxxPDCommitmentsxxx.xml.xml that is generated Note: Market Participant will receive start up notification through Dispatch Services once the PD commitment is scheduled | Market Participant able to verify in the report that there is a PD-CMT scheduled for certain hours
3 | Market Participant to email IESO to request termination of the PD commitment generated in Step 2, within 4 hours of the commitment start time | Market Participant request to terminate the contract is successfully sent to the IESO Operator through email
4 | MP should cancel their RTEM offers for the hours that are committed in PD through EMI/MIM within 4 hours of commitment start time Note: If some or all the hours that are being cancelled are in the RT_MANDATORY window, then the submission is subject to approval from the IESO Operator | RTEM offers for the hours that are committed in PD are cancelled successfully through EMI/MIM.
5 | Once the PD Run completes after the IESO Operator terminates the commitment (MP will receive email notification about the termination), Navigate to the following path on the IESO reports site Your Files > private >PDCommitments > {MP_Name} | 1) If there are no other PD or DA Commitment scheduled for the same resource or other resources of the participant on the given trade date, MP to verify no new PD Commitment report is generated after IESO Operator terminates the commitment and the PD Run is complete. 2) If other PD/DA commitments exist for the same resource (different hours) or other participant resources on the trade date, Market Participant must: 1.Open the PD Commitment report (xxxPDCommitmentsxxx.xml) that is generated after the PD Run is completed, following IESO Operator's commitment termination. 2.Verify terminated hours have no associated commitments.
6 | In the IESO Confidential Sandbox Reports site, MP to retrieve preliminary and final settlement statements and associated data files | Market Participant to verify generation and successful retrieval of preliminary and final statements, and associated data files.
7 | Review statement for applicable charges and calculations | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
8 | Review statement for non-applicable charges and calculations | MP to verify that no non-applicable charges/payments are present in the settlement statements.
9 | Market Participant to review statements for calculation accuracy | Market Participant can verify that the charges/payments are accurately calculated.

## S21-SEAL Constraint
End-to-End Testing: | Test Scenario 21 - Seal Constraint
Prerequisites: | 1. Valid login credentials for EMI/MIM, Online IESO, IESO Confidential Reports Site, and Dispatch Services
2. Market Participant provided the following details to the IESO in advance: - Resource - Time - Constraints type (SEAL)
3. Standing data is present in EMI/MIM for the given resource.
4. If the "RTEM" data is being submitted by the following resource types: Non-Quick Start (NQS) Other, Combustion Turbine (CT) Pseudo-Unit (PSU), Steam Turbine (ST) PSU, CT Non-PSU, ST Non-PSU, then the Daily Dispatch Data (DDD) for the corresponding participant, delivery date, and resource should be present in the system.
Test Case Name: | S21-TC01: Dispatchable generator resources request for constraint due to SEAL and are able to verify its impact on the settlement statements.
Test Step No. | Test Step Description | Test Step Expected Result | Status | Organization Name | User Name | Detected Date | Additional Comments | Attachments / Screenshots
1 | Market Participant submits energy offer RTEM dispatch data through EMI or MIM after the day-ahead market restricted window (DA_RESTRICTED). | Dispatch data submission is processed successfully.
2 | Once the pre-dispatch run is completed, navigate to the following path in the IESO Confidential Reports Site: Your Files > private > PredispSchedules2 > {MP_Name} Open the latest xxxxxPredispSchedules2xxx.xml that is generated. | Market Participant can observe their constraint resource schedule in Pre-dispatch Schedules Report.
3 | MP receives dispatches in Dispatch service application. | MP is able to verify that the dispatches align as expected in the Dispatch Service application.
4 | After the real-time run for the relevant Interval, navigate to the following path on the IESO Confidential Sandbox Reports Site: Your Files > private > ENGYOPRVRealtimeSchedules5Min > {MP_Name} Open the latest xxxxxENGYOPRVRealtimeSchedules5Min.xml that is generated. | 1) MP is able to observe their constraint 5-Minute Energy and Operating Reserve Schedule Report for the interval. 2) MP is able to view the reason code 'SEAL' in the report.
5 | After the real-time run for the relevant hour, navigate to the following path on the IESO Confidential Sandbox Reports Site: Your Files > private > ENGYOPRVRealtimeDispatch > {MP_Name} Open the latest xxxxxENGYOPRVRealtimeDispatch.xml that is generated. | 1) MP is able to view their constraint dispatches for the hour in the Real-Time Energy and Operating Reserve Dispatch Report. 2) MP is able to view the reason code 'SEAL' in the report.
6 | In the IESO Confidential Sandbox Reports Site, MP is able to download the preliminary and final settlement statements along with the data files for the affected trade date of this test case. | MP is able to download the preliminary and final settlement statements and associated data files from the IESO Confidential Sandbox Reports Site.
7 | Review settlement statements for applicable charges and calculations. | Market Participant to verify that only applicable charges/payments are present in the settlement statements.
8 | Review settlement statements for non-applicable charges and calculations. | Market Participant is able to verify all non-applicable charges/payments are not present in the settlement statements.
9 | Review settlement statements for calculation accuracy. | Charges/payments are accurately calculated.